## PWS Deliverables
Title | Deliverable ID | Deliverable | PWS Ref | Task Group | Cadence | Base or Optional | Format | Data Rights | PWS Due Wording | Period | Due Date | Primary Owner | Alternate Owner | Date Submitted | Gov Decision | Decision Date | Link | Notes | PWS Flag
A001 - Initial delivery | A001 | Implementation Approach and Architecture | 6.1 | 6.1 | One-time + updates | Base | Government format | OTA Technical Data | Due Date IAW IMS | Initial delivery |  |  |  |  | Pending |  |  | Due per the IMS: enter date. | Due "IAW IMS" – A017 must exist first (Issue 8).
A002 - Initial delivery | A002 | ZT Governance Plan | 6.1 | 6.1 | One-time + updates | Base | Government format | OTA Technical Data | Due Date IAW IMS | Initial delivery |  |  |  |  | Pending |  |  | Due per the IMS: enter date. | Due "IAW IMS" (Issue 8).
A003 - As needed / event-driven | A003 | eMASS Data Entry | 6.2.1 | 6.2 | As needed | Base | Government format | OTA Technical Data | Due Date IAW IMS | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered.
A004 - Initial delivery | A004 | ATO Documentation/ Artifacts | 6.1, 6.2.1 | 6.1 | One-time + updates | Base | Government format | OTA Technical Data | Due Date IAW IMS | Initial delivery |  |  |  |  | Pending |  |  | Due per the IMS: enter date. | Due "IAW IMS" (Issue 8).
A005 - As needed / event-driven | A005 | POA&Ms including risk acceptance POA&Ms for vulnerabilities that cannot be mitigated and STIGs that cannot be applied. | 6.1, 6.2.1 | 6.1 | As needed | Base | Government format | OTA Technical Data | 30 days post vulnerability identification (if vulnerability cannot be mitigated). To be reviewed every 30 days from initial finding. | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered. | Body says CAT I POA&M if no fix in 1 week; table says 30 days (Issue 3).
A006 - Quarter 1 | A006 | STIG/SRG Checklists | 6.1, 6.2.1 | 6.1 | Quarterly | Base | Government format | OTA Technical Data | Routine Updates | Quarter 1 | 2026-08-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after quarter end.
A006 - Quarter 2 | A006 | STIG/SRG Checklists | 6.1, 6.2.1 | 6.1 | Quarterly | Base | Government format | OTA Technical Data | Routine Updates | Quarter 2 | 2026-11-06 |  |  |  | Pending |  |  | Due date assumes 5 business days after quarter end.
A006 - Quarter 3 | A006 | STIG/SRG Checklists | 6.1, 6.2.1 | 6.1 | Quarterly | Base | Government format | OTA Technical Data | Routine Updates | Quarter 3 | 2027-02-05 |  |  |  | Pending |  |  | Due date assumes 5 business days after quarter end.
A006 - Quarter 4 | A006 | STIG/SRG Checklists | 6.1, 6.2.1 | 6.1 | Quarterly | Base | Government format | OTA Technical Data | Routine Updates | Quarter 4 | 2027-05-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after quarter end.
A007 - ACAS scan wk 1 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 1 | 2026-05-08 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 2 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 2 | 2026-05-15 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 3 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 3 | 2026-05-22 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 4 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 4 | 2026-05-29 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 5 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 5 | 2026-06-05 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 6 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 6 | 2026-06-12 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 7 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 7 | 2026-06-19 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 8 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 8 | 2026-06-26 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 9 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 9 | 2026-07-03 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 10 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 10 | 2026-07-10 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 11 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 11 | 2026-07-17 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 12 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 12 | 2026-07-24 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 13 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 13 | 2026-07-31 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 14 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 14 | 2026-08-07 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 15 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 15 | 2026-08-14 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 16 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 16 | 2026-08-21 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 17 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 17 | 2026-08-28 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 18 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 18 | 2026-09-04 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 19 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 19 | 2026-09-11 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 20 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 20 | 2026-09-18 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 21 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 21 | 2026-09-25 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 22 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 22 | 2026-10-02 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 23 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 23 | 2026-10-09 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 24 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 24 | 2026-10-16 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 25 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 25 | 2026-10-23 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 26 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 26 | 2026-10-30 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 27 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 27 | 2026-11-06 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 28 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 28 | 2026-11-13 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 29 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 29 | 2026-11-20 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 30 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 30 | 2026-11-27 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 31 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 31 | 2026-12-04 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 32 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 32 | 2026-12-11 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 33 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 33 | 2026-12-18 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 34 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 34 | 2026-12-25 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 35 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 35 | 2027-01-01 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 36 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 36 | 2027-01-08 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 37 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 37 | 2027-01-15 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 38 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 38 | 2027-01-22 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 39 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 39 | 2027-01-29 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 40 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 40 | 2027-02-05 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 41 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 41 | 2027-02-12 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 42 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 42 | 2027-02-19 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 43 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 43 | 2027-02-26 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 44 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 44 | 2027-03-05 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 45 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 45 | 2027-03-12 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 46 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 46 | 2027-03-19 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 47 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 47 | 2027-03-26 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 48 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 48 | 2027-04-02 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 49 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 49 | 2027-04-09 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 50 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 50 | 2027-04-16 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 51 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 51 | 2027-04-23 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A007 - ACAS scan wk 52 | A007 | ACAS Scans | 6.1, 6.2.1 | 6.1 | Weekly | Base | Vendor format/ Government Approved | OTA Technical Data | As Needed | ACAS scan wk 52 | 2027-04-30 |  |  |  | Pending |  |  | Friday assumed; PWS says weekly only.
A008 - As needed / event-driven | A008 | System Change Requests Form/ Configuration Change Request | 6.2.1 | 6.2 | As needed | Base | Government Format | OTA Technical Data | As needed | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered.
A009 - As needed / event-driven | A009 | eMASS Package | 6.2.1 | 6.2 | One-time + updates | Base | Government Format | OTA Technical Data | As needed | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered.
A010 - As needed / event-driven | A010 | Status updates on Security patches/hot fixes, OPORD, TASK ORDER, FISMA, PPSM, IAVM and STIGs | 6.2.1 | 6.2 | As needed | Base | Vendor format/ Government Approved | OTA Technical Data | As needed | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered.
A011 - Initial delivery | A011 | Incident Response Plan | 6.2.1 | 6.2 | One-time + updates | Base | Government format | OTA Technical Data | Due Date IAW IMS | Initial delivery |  |  |  |  | Pending |  |  | Due per the IMS: enter date. | Due "IAW IMS" (Issue 8).
A012 - Quarter 1 | A012 | Security Monitoring Reports | 6.2.1 | 6.2 | Quarterly | Base | Government format | OTA Technical Data | Routine Updates | Quarter 1 | 2026-08-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after quarter end. | Same title as A040 (Issue 20).
A012 - Quarter 2 | A012 | Security Monitoring Reports | 6.2.1 | 6.2 | Quarterly | Base | Government format | OTA Technical Data | Routine Updates | Quarter 2 | 2026-11-06 |  |  |  | Pending |  |  | Due date assumes 5 business days after quarter end. | Same title as A040 (Issue 20).
A012 - Quarter 3 | A012 | Security Monitoring Reports | 6.2.1 | 6.2 | Quarterly | Base | Government format | OTA Technical Data | Routine Updates | Quarter 3 | 2027-02-05 |  |  |  | Pending |  |  | Due date assumes 5 business days after quarter end. | Same title as A040 (Issue 20).
A012 - Quarter 4 | A012 | Security Monitoring Reports | 6.2.1 | 6.2 | Quarterly | Base | Government format | OTA Technical Data | Routine Updates | Quarter 4 | 2027-05-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after quarter end. | Same title as A040 (Issue 20).
A013 - Quarter 1 | A013 | Vulnerability Scan Reports | 6.2.1 | 6.2 | Quarterly | Base | Government format | OTA Technical Data | Routine Updates | Quarter 1 | 2026-08-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after quarter end.
A013 - Quarter 2 | A013 | Vulnerability Scan Reports | 6.2.1 | 6.2 | Quarterly | Base | Government format | OTA Technical Data | Routine Updates | Quarter 2 | 2026-11-06 |  |  |  | Pending |  |  | Due date assumes 5 business days after quarter end.
A013 - Quarter 3 | A013 | Vulnerability Scan Reports | 6.2.1 | 6.2 | Quarterly | Base | Government format | OTA Technical Data | Routine Updates | Quarter 3 | 2027-02-05 |  |  |  | Pending |  |  | Due date assumes 5 business days after quarter end.
A013 - Quarter 4 | A013 | Vulnerability Scan Reports | 6.2.1 | 6.2 | Quarterly | Base | Government format | OTA Technical Data | Routine Updates | Quarter 4 | 2027-05-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after quarter end.
A014 - 90 days after award | A014 | Compliance Documentation | 6.2.1 | 6.2 | Per package | Base | Vendor Determined Format | OTA Work | 90 Days after award | 90 days after award | 2026-08-02 |  |  |  | Pending
A015 - Initial delivery | A015 | Security Assessment Report | 6.2.1 | 6.2 | Per package | Base | Vendor Determined Format | OTA Work | ICW Accreditation | Initial delivery |  |  |  |  | Pending |  |  | In concert with accreditation.
A016 - As needed / event-driven | A016 | Briefings Slides | 6.1, 6.2.2, 6.3.2.1, 6.3.2.4, 6.3.3.1 | 6.1 | As needed | Base | Vendor Determined Format | OTA Technical Data | As determined by the Government | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered.
A017 - Month 1: May 2026 | A017 | Integrated Master Schedule | 6.3.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 1: May 2026 | 2026-06-05 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A017 - Month 2: Jun 2026 | A017 | Integrated Master Schedule | 6.3.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 2: Jun 2026 | 2026-07-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A017 - Month 3: Jul 2026 | A017 | Integrated Master Schedule | 6.3.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 3: Jul 2026 | 2026-08-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A017 - Month 4: Aug 2026 | A017 | Integrated Master Schedule | 6.3.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 4: Aug 2026 | 2026-09-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A017 - Month 5: Sep 2026 | A017 | Integrated Master Schedule | 6.3.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 5: Sep 2026 | 2026-10-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A017 - Month 6: Oct 2026 | A017 | Integrated Master Schedule | 6.3.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 6: Oct 2026 | 2026-11-06 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A017 - Month 7: Nov 2026 | A017 | Integrated Master Schedule | 6.3.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 7: Nov 2026 | 2026-12-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A017 - Month 8: Dec 2026 | A017 | Integrated Master Schedule | 6.3.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 8: Dec 2026 | 2027-01-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A017 - Month 9: Jan 2027 | A017 | Integrated Master Schedule | 6.3.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 9: Jan 2027 | 2027-02-05 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A017 - Month 10: Feb 2027 | A017 | Integrated Master Schedule | 6.3.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 10: Feb 2027 | 2027-03-05 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A017 - Month 11: Mar 2027 | A017 | Integrated Master Schedule | 6.3.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 11: Mar 2027 | 2027-04-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A017 - Month 12: Apr 2027 | A017 | Integrated Master Schedule | 6.3.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 12: Apr 2027 | 2027-05-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A018 - Month 1: May 2026 | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | 6.3.1.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 1: May 2026 | 2026-06-05 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A018 - Month 2: Jun 2026 | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | 6.3.1.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 2: Jun 2026 | 2026-07-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A018 - Month 3: Jul 2026 | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | 6.3.1.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 3: Jul 2026 | 2026-08-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A018 - Month 4: Aug 2026 | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | 6.3.1.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 4: Aug 2026 | 2026-09-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A018 - Month 5: Sep 2026 | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | 6.3.1.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 5: Sep 2026 | 2026-10-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A018 - Month 6: Oct 2026 | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | 6.3.1.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 6: Oct 2026 | 2026-11-06 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A018 - Month 7: Nov 2026 | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | 6.3.1.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 7: Nov 2026 | 2026-12-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A018 - Month 8: Dec 2026 | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | 6.3.1.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 8: Dec 2026 | 2027-01-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A018 - Month 9: Jan 2027 | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | 6.3.1.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 9: Jan 2027 | 2027-02-05 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A018 - Month 10: Feb 2027 | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | 6.3.1.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 10: Feb 2027 | 2027-03-05 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A018 - Month 11: Mar 2027 | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | 6.3.1.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 11: Mar 2027 | 2027-04-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A018 - Month 12: Apr 2027 | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | 6.3.1.1 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | As determined by the Government | Month 12: Apr 2027 | 2027-05-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end.
A019 - WAR wk 1 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 1 | 2026-05-08 |  |  |  | Pending
A019 - WAR wk 2 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 2 | 2026-05-15 |  |  |  | Pending
A019 - WAR wk 3 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 3 | 2026-05-22 |  |  |  | Pending
A019 - WAR wk 4 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 4 | 2026-05-29 |  |  |  | Pending
A019 - WAR wk 5 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 5 | 2026-06-05 |  |  |  | Pending
A019 - WAR wk 6 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 6 | 2026-06-12 |  |  |  | Pending
A019 - WAR wk 7 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 7 | 2026-06-19 |  |  |  | Pending
A019 - WAR wk 8 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 8 | 2026-06-26 |  |  |  | Pending
A019 - WAR wk 9 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 9 | 2026-07-03 |  |  |  | Pending
A019 - WAR wk 10 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 10 | 2026-07-10 |  |  |  | Pending
A019 - WAR wk 11 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 11 | 2026-07-17 |  |  |  | Pending
A019 - WAR wk 12 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 12 | 2026-07-24 |  |  |  | Pending
A019 - WAR wk 13 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 13 | 2026-07-31 |  |  |  | Pending
A019 - WAR wk 14 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 14 | 2026-08-07 |  |  |  | Pending
A019 - WAR wk 15 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 15 | 2026-08-14 |  |  |  | Pending
A019 - WAR wk 16 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 16 | 2026-08-21 |  |  |  | Pending
A019 - WAR wk 17 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 17 | 2026-08-28 |  |  |  | Pending
A019 - WAR wk 18 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 18 | 2026-09-04 |  |  |  | Pending
A019 - WAR wk 19 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 19 | 2026-09-11 |  |  |  | Pending
A019 - WAR wk 20 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 20 | 2026-09-18 |  |  |  | Pending
A019 - WAR wk 21 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 21 | 2026-09-25 |  |  |  | Pending
A019 - WAR wk 22 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 22 | 2026-10-02 |  |  |  | Pending
A019 - WAR wk 23 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 23 | 2026-10-09 |  |  |  | Pending
A019 - WAR wk 24 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 24 | 2026-10-16 |  |  |  | Pending
A019 - WAR wk 25 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 25 | 2026-10-23 |  |  |  | Pending
A019 - WAR wk 26 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 26 | 2026-10-30 |  |  |  | Pending
A019 - WAR wk 27 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 27 | 2026-11-06 |  |  |  | Pending
A019 - WAR wk 28 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 28 | 2026-11-13 |  |  |  | Pending
A019 - WAR wk 29 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 29 | 2026-11-20 |  |  |  | Pending
A019 - WAR wk 30 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 30 | 2026-11-27 |  |  |  | Pending
A019 - WAR wk 31 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 31 | 2026-12-04 |  |  |  | Pending
A019 - WAR wk 32 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 32 | 2026-12-11 |  |  |  | Pending
A019 - WAR wk 33 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 33 | 2026-12-18 |  |  |  | Pending
A019 - WAR wk 34 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 34 | 2026-12-25 |  |  |  | Pending
A019 - WAR wk 35 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 35 | 2027-01-01 |  |  |  | Pending
A019 - WAR wk 36 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 36 | 2027-01-08 |  |  |  | Pending
A019 - WAR wk 37 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 37 | 2027-01-15 |  |  |  | Pending
A019 - WAR wk 38 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 38 | 2027-01-22 |  |  |  | Pending
A019 - WAR wk 39 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 39 | 2027-01-29 |  |  |  | Pending
A019 - WAR wk 40 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 40 | 2027-02-05 |  |  |  | Pending
A019 - WAR wk 41 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 41 | 2027-02-12 |  |  |  | Pending
A019 - WAR wk 42 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 42 | 2027-02-19 |  |  |  | Pending
A019 - WAR wk 43 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 43 | 2027-02-26 |  |  |  | Pending
A019 - WAR wk 44 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 44 | 2027-03-05 |  |  |  | Pending
A019 - WAR wk 45 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 45 | 2027-03-12 |  |  |  | Pending
A019 - WAR wk 46 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 46 | 2027-03-19 |  |  |  | Pending
A019 - WAR wk 47 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 47 | 2027-03-26 |  |  |  | Pending
A019 - WAR wk 48 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 48 | 2027-04-02 |  |  |  | Pending
A019 - WAR wk 49 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 49 | 2027-04-09 |  |  |  | Pending
A019 - WAR wk 50 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 50 | 2027-04-16 |  |  |  | Pending
A019 - WAR wk 51 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 51 | 2027-04-23 |  |  |  | Pending
A019 - WAR wk 52 | A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | 6.3 | Weekly | Base | Vendor Determined Format | OTA Work | Every Friday | WAR wk 52 | 2027-04-30 |  |  |  | Pending
A020 - Month 1: May 2026 | A020 | Technical Library Documentation Report | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 1: May 2026 | 2026-06-05 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A020 - Month 2: Jun 2026 | A020 | Technical Library Documentation Report | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 2: Jun 2026 | 2026-07-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A020 - Month 3: Jul 2026 | A020 | Technical Library Documentation Report | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 3: Jul 2026 | 2026-08-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A020 - Month 4: Aug 2026 | A020 | Technical Library Documentation Report | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 4: Aug 2026 | 2026-09-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A020 - Month 5: Sep 2026 | A020 | Technical Library Documentation Report | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 5: Sep 2026 | 2026-10-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A020 - Month 6: Oct 2026 | A020 | Technical Library Documentation Report | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 6: Oct 2026 | 2026-11-06 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A020 - Month 7: Nov 2026 | A020 | Technical Library Documentation Report | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 7: Nov 2026 | 2026-12-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A020 - Month 8: Dec 2026 | A020 | Technical Library Documentation Report | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 8: Dec 2026 | 2027-01-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A020 - Month 9: Jan 2027 | A020 | Technical Library Documentation Report | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 9: Jan 2027 | 2027-02-05 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A020 - Month 10: Feb 2027 | A020 | Technical Library Documentation Report | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 10: Feb 2027 | 2027-03-05 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A020 - Month 11: Mar 2027 | A020 | Technical Library Documentation Report | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 11: Mar 2027 | 2027-04-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A020 - Month 12: Apr 2027 | A020 | Technical Library Documentation Report | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 12: Apr 2027 | 2027-05-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A021 - Month 1: May 2026 | A021 | Technical Briefing/ Presentation | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 1: May 2026 | 2026-06-05 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A021 - Month 2: Jun 2026 | A021 | Technical Briefing/ Presentation | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 2: Jun 2026 | 2026-07-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A021 - Month 3: Jul 2026 | A021 | Technical Briefing/ Presentation | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 3: Jul 2026 | 2026-08-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A021 - Month 4: Aug 2026 | A021 | Technical Briefing/ Presentation | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 4: Aug 2026 | 2026-09-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A021 - Month 5: Sep 2026 | A021 | Technical Briefing/ Presentation | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 5: Sep 2026 | 2026-10-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A021 - Month 6: Oct 2026 | A021 | Technical Briefing/ Presentation | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 6: Oct 2026 | 2026-11-06 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A021 - Month 7: Nov 2026 | A021 | Technical Briefing/ Presentation | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 7: Nov 2026 | 2026-12-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A021 - Month 8: Dec 2026 | A021 | Technical Briefing/ Presentation | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 8: Dec 2026 | 2027-01-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A021 - Month 9: Jan 2027 | A021 | Technical Briefing/ Presentation | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 9: Jan 2027 | 2027-02-05 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A021 - Month 10: Feb 2027 | A021 | Technical Briefing/ Presentation | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 10: Feb 2027 | 2027-03-05 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A021 - Month 11: Mar 2027 | A021 | Technical Briefing/ Presentation | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 11: Mar 2027 | 2027-04-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A021 - Month 12: Apr 2027 | A021 | Technical Briefing/ Presentation | 6.3.1.7 | 6.3 | Monthly | Base | Vendor Determined Format | OTA Work | ICW MSR | Month 12: Apr 2027 | 2027-05-07 |  |  |  | Pending |  |  | Due date assumes 5 business days after month end. | "ICW MSR" is undefined (Issue 7).
A022 - As needed / event-driven | A022 | Knowledge Management Site | 6.3.1.7 | 6.3 | As needed | Base | Vendor Determined Format | OTA Work | ICW MSR | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered. | "ICW MSR" is undefined (Issue 7).
A023 - As needed / event-driven | A023 | Whitepapers | 6.3.2.1, 6.3.2.3, 6.3.3.1 | 6.3 | As needed | Base | Vendor Determined Format | OTA Work | ICW MSR | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered. | Table omits 6.3.2.4, where the body lists it (Issue 5).
A024 - As needed / event-driven | A024 | DoDAF Artifacts/Diagrams (e.g., OV, SV) | 6.1, 6.3.2.4, 6.3.3.1 | 6.1 | As needed | Base | Vendor Determined Format | OTA Technical Data | As determined by the Government | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered.
A025 - As needed / event-driven | A025 | Engineering Artifacts (e.g., Network/System Diagrams) | 6.1, 6.3.2.4, 6.3.4.1.3, 6.3.4.1.4, 6.3.4.1.5 | 6.1 | As needed | Base | Government format | OTA Technical Data | Within 10 business days after assignment | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered. | Near-duplicate of A032 (Issue 20).
A026 - Initial delivery | A026 | Concept of Operations (CONOPS) | 6.1 | 6.1 | One-time + updates | Base | Vendor Determined/ Govt Approved Format | OTA Technical Data | 60 days post deployment | Initial delivery |  |  |  |  | Pending |  |  | 60 days post deployment: enter date.
A027 - 90 days after award | A027 | Network Modernization Plan | 6.3.2.2 | 6.3 | One-time + updates | Base | Vendor Determined Format | OTA Technical Data | 90 Days after contract award | 90 days after award | 2026-08-02 |  |  |  | Pending
A028 - Initial delivery | A028 | ZT Traceability Matrix | 6.3.2.3 | 6.3 | One-time + updates | Base | Vendor Determined Format | OTA Technical Data | ICW MSR | Initial delivery |  |  |  |  | Pending |  |  | Due per the IMS: enter date. | "ICW MSR" is undefined (Issue 7).
A029 - Initial delivery | A029 | ZT Gap Analysis | 6.3.2.3 | 6.3 | One-time + updates | Base | Vendor Determined Format | OTA Technical Data | As determined by the Government | Initial delivery |  |  |  |  | Pending |  |  | Due per the IMS: enter date.
A030 - Initial delivery | A030 | Zero Trust Architecture Design Document | 6.3.2.3 | 6.3 | One-time + updates | Base | Vendor Determined Format | OTA Technical Data | As determined by the Government | Initial delivery |  |  |  |  | Pending |  |  | Due per the IMS: enter date.
A031 - As needed / event-driven | A031 | Implementation Plan | 6.3.2.5, 6.3.3.2, 6.3.3.3 | 6.3 | As needed | Base | Vendor format | OTA Technical Data | 30 days before Implementation | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered.
A032 - As needed / event-driven | A032 | Engineering Artifacts (e.g., Network/System Diagrams) | 6.3.2.5, 6.3.3.1, 6.3.3.2, 6.3.3.3 | 6.3 | As needed | Base | Government format | OTA Technical Data | Within 10 business days after assignment | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered. | Near-duplicate of A025 (Issue 20).
A033 - As needed / event-driven | A033 | ASIs | 6.3.2.5, 6.3.3.2, 6.3.3.3 | 6.3 | One-time | Base | Government format | OTA Technical Data | 10 days upon expected outage unless otherwise noted by the Government (must receive Gov’t approval) | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered.
A034 - Initial delivery | A034 | Site Survey Reports | 6.3.2.6, 6.3.3.1 | 6.3 | One-time | Base | Vendor format/ Government Approved | OTA Technical Data | IAW IMS | Initial delivery |  |  |  |  | Pending |  |  | Due per the IMS: enter date. | Table cites 6.3.2.6, which names no deliverables (Issue 4).
A035 - As needed / event-driven | A035 | ITSM/ Change Tickets | 6.3.4.1.1, 6.3.4.1.2 | 6.3 | One-time + updates | Base + Optional | Government format | OTA Technical Data | 10 days prior to necessary change | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered. | Table omits the 24x7 paragraph (Issue 6).
A036 - As needed / event-driven | A036 | Metrics Report | 6.3.4.1.2 | 6.3 | One-time | Optional Priced | Vendor Determined/ Govt Approved format | OTA Technical Data | 30 Days after Implementation | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered. | Table omits the 24x7 paragraph (Issue 6).
A037 - As needed / event-driven | A037 | Help Desk Report | 6.3.4.1.2 | 6.3 | One-time + updates | Optional Priced | Vendor Determined/ Govt Approved format | OTA Technical Data | 24 hours upon request | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered. | Table omits the 24x7 paragraph (Issue 6).
A038 - 30 days after award | A038 | Test Plans | 6.3.4.1.3, 6.3.4.1.4 | 6.3 | One-time + updates | Base | Vendor Determined/ Govt Approved format | OTA Technical Data | 30 days after contract award | 30 days after award | 2026-06-03 |  |  |  | Pending |  |  | See PWS Flag. | Due 30 days after award, before anything exists to test (Issue 9).
A039 - 30 days after award | A039 | Test Reports | 6.3.4.1.3, 6.3.4.1.4 | 6.3 | One-time + updates | Base | Vendor Determined/ Govt Approved format | OTA Technical Data | 30 days after contract award | 30 days after award | 2026-06-03 |  |  |  | Pending |  |  | See PWS Flag. | Due 30 days after award, before anything exists to test (Issue 9).
A040 - 90 days after award (optional PNSOC) | A040 | Security Monitoring Reports | 6.3.4.2 | 6.3 | One-time + updates | Optional Priced | Vendor Determined Format | OTA Technical Data | 90 Days after award | 90 days after award (optional PNSOC) | 2026-08-02 |  |  |  | Pending |  |  | Only if PNSOC option exercised. | Same title as A012; one-time due date for an ongoing optional service (Issue 9).
A041 - Initial draft at kickoff | A041 | Transition-In Plan | 6.3.1.3 | 6.3 | One-time | Base | Vendor Determined Format | OTA Technical Data | Initial Draft at Project Kickoff Meeting Final Draft 5 business days after contract award | Initial draft at kickoff | 2026-05-04 |  |  |  | Pending |  |  |  | Body: 30 days after kickoff; table: draft at kickoff, final 5 business days after award (Issue 1).
A041 - Final draft: 5 business days after award | A041 | Transition-In Plan | 6.3.1.3 | 6.3 | One-time | Base | Vendor Determined Format | OTA Technical Data | Initial Draft at Project Kickoff Meeting Final Draft 5 business days after contract award | Final draft: 5 business days after award | 2026-05-11 |  |  |  | Pending |  |  |  | Body: 30 days after kickoff; table: draft at kickoff, final 5 business days after award (Issue 1).
A042 - 120 days before end (body wording) | A042 | Transition-Out Plan | 6.3.1.3 | 6.3 | One-time | Base | Vendor Determined Format | OTA Technical Data | T-30 Days (30 Days Prior to Contract End) | 120 days before end (body wording) | 2029-06-01 |  |  |  | Pending |  |  | Table says T-30; earlier date used. | Body: 120 calendar days before end; table: T-30 (Issue 2).
A043 - End of contract | A043 | Task Order Closeout | 6.3.1.3 | 6.3 | One-time | Base | Vendor Determined Format | OTA Technical Data | End of Contract | End of contract | 2029-09-29 |  |  |  | Pending
A044 - As needed / event-driven | A044 | Logistics Deliverables | 6.3.1.4 | 6.3 | As needed | Base | Vendor Determined Format | OTA Technical Data | ICW MSR | As needed / event-driven |  |  |  |  | Pending |  |  | Add a new item each time this is delivered. | "ICW MSR" is undefined (Issue 7).