## PWS Deliverables Tracker
THUNDERDOME
Month | Sub Task Number | Paragraph / Section | Frequency | Category | Primary Accountable POC | Secondary Accountable POC | Format of Deliverable | ID | Deliverable | Period / Event | Due Date | Day | Days Until Due | Date Submitted | Gov Inspect-By | Status Flow 1 | Status Flow 2 | Status Flow 3 | Flag | PWS Refs | PWS Due Wording / Notes | Category | Status Flow 1 | Status Flow 2 | Status Flow 3 | Frequency | Settings (edit the yellow cells)
Sep | 6.3.1.3 | Transition Planning | One-Time | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A041 | A041 Transition-In Plan | Initial draft at kickoff | 2026-09-02 | Wed | -41 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.3.1.3 | Body says 30 days after kickoff = 2 Oct 2026. Flag: Body: 30 days after kickoff | Program Mgmt | Received | Reviewed | Accepted | Weekly | Clock start (PWS date) | 2026-09-02
Sep | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 1 | 2026-09-04 | Fri | -39 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.1, 6.2.1 |  | Engineering | Not Received | Not Reviewed | Returned | Monthly | Monthly/quarterly due offset (business days) | 5
Sep | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 1 | 2026-09-04 | Fri | -39 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.3.1.2, 6.3.1.4 |  | Operations |  | Demonstrated | Returned, but Fixed | Quarterly | Gov inspection window (business days) | 5
Sep | 6.3.1.3 | Transition Planning | One-Time | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A041 | A041 Transition-In Plan | Final draft: 5 business days after award | 2026-09-09 | Wed | -34 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.3.1.3 | Labor Day not excluded. |  |  | Not Demonstrated |  | One-Time | Resubmission window (business days) | 10
Sep | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 2 | 2026-09-11 | Fri | -32 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.1, 6.2.1 | [5 empty] | One-Time + Updates | End of base period | 2027-05-03
Sep | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 2 | 2026-09-11 | Fri | -32 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.3.1.2, 6.3.1.4 | [5 empty] | Per Package | End of final option year | 2029-09-29
Sep | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 3 | 2026-09-18 | Fri | -25 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.1, 6.2.1 | [5 empty] | As Needed | Today | 2026-10-13
Sep | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 3 | 2026-09-18 | Fri | -25 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.3.1.2, 6.3.1.4 | [5 empty] | None named
Sep | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 4 | 2026-09-25 | Fri | -18 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.1, 6.2.1 | [6 empty] | Holidays are not excluded from business-day math.
Sep | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 4 | 2026-09-25 | Fri | -18 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.3.1.2, 6.3.1.4
Oct | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 5 | 2026-10-02 | Fri | -11 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.1, 6.2.1
Oct | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 5 | 2026-10-02 | Fri | -11 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.3.1.2, 6.3.1.4
Oct | 6.3.4.1.3 | Vendor Lab Testing | One-Time | Operations | Brian Abrigo | Chris Kuznicki | Vendor / Gov approved | A038 | A038 Test Plans | 30 days after award | 2026-10-02 | Fri | -11 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.3.4.1.3, 6.3.4.1.4 | Flag: Due before anything exists to test
Oct | 6.3.4.1.3 | Vendor Lab Testing | One-Time | Operations | Brian Abrigo | Chris Kuznicki | Vendor / Gov approved | A039 | A039 Test Reports | 30 days after award | 2026-10-02 | Fri | -11 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.3.4.1.3, 6.3.4.1.4 | Flag: Due before anything exists to test
Oct | 6.1 | Zero Trust AI Implementation | Quarterly | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A006 | A006 STIG/SRG Checklists | Qtr ending 30 Sep 2026 | 2026-10-07 | Wed | -6 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.1, 6.2.1
Oct | 6.2.1 | Cybersecurity Engineering / A&A | Quarterly | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A012 | A012 Security Monitoring Reports | Qtr ending 30 Sep 2026 | 2026-10-07 | Wed | -6 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.2.1 | Flag: Same title as A040
Oct | 6.2.1 | Cybersecurity Engineering / A&A | Quarterly | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A013 | A013 Vulnerability Scan Reports | Qtr ending 30 Sep 2026 | 2026-10-07 | Wed | -6 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.2.1
Oct | 6.3.1 | Task Order Mgmt / PMO Support for PMN | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A017 | A017 Integrated Master Schedule | Sep 2026 | 2026-10-07 | Wed | -6 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.3.1
Oct | 6.3.1.1 | Monthly Progress Report | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A018 | A018 Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | Sep 2026 | 2026-10-07 | Wed | -6 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.3.1.1
Oct | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A020 | A020 Technical Library Documentation Report | Sep 2026 | 2026-10-07 | Wed | -6 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.3.1.7 | Flag: ICW MSR = Monthly Status Report; confirm it equals the MPR
Oct | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A021 | A021 Technical Briefing/ Presentation | Sep 2026 | 2026-10-07 | Wed | -6 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.3.1.7 | Flag: ICW MSR = Monthly Status Report; confirm it equals the MPR
Oct | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 6 | 2026-10-09 | Fri | -4 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.1, 6.2.1
Oct | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 6 | 2026-10-09 | Fri | -4 |  |  | Not Received | Not Reviewed |  | OVERDUE | 6.3.1.2, 6.3.1.4
Oct | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 7 | 2026-10-16 | Fri | 3 |  |  | Not Received | Not Reviewed |  | Due within 7 days | 6.1, 6.2.1
Oct | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 7 | 2026-10-16 | Fri | 3 |  |  | Not Received | Not Reviewed |  | Due within 7 days | 6.3.1.2, 6.3.1.4
Oct | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 8 | 2026-10-23 | Fri | 10 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Oct | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 8 | 2026-10-23 | Fri | 10 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Oct | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 9 | 2026-10-30 | Fri | 17 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Oct | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 9 | 2026-10-30 | Fri | 17 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Nov | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 10 | 2026-11-06 | Fri | 24 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Nov | 6.3.1 | Task Order Mgmt / PMO Support for PMN | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A017 | A017 Integrated Master Schedule | Oct 2026 | 2026-11-06 | Fri | 24 |  |  | Not Received | Not Reviewed |  |  | 6.3.1
Nov | 6.3.1.1 | Monthly Progress Report | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A018 | A018 Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | Oct 2026 | 2026-11-06 | Fri | 24 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.1
Nov | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 10 | 2026-11-06 | Fri | 24 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Nov | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A020 | A020 Technical Library Documentation Report | Oct 2026 | 2026-11-06 | Fri | 24 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.7
Nov | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A021 | A021 Technical Briefing/ Presentation | Oct 2026 | 2026-11-06 | Fri | 24 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.7
Nov | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 11 | 2026-11-13 | Fri | 31 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Nov | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 11 | 2026-11-13 | Fri | 31 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Nov | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 12 | 2026-11-20 | Fri | 38 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Nov | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 12 | 2026-11-20 | Fri | 38 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Nov | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 13 | 2026-11-27 | Fri | 45 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Nov | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 13 | 2026-11-27 | Fri | 45 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Dec | 6.2.1 | Cybersecurity Engineering / A&A | One-Time | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor format | A014 | A014 Compliance Documentation | 90 days after award | 2026-12-01 | Tue | 49 |  |  | Not Received | Not Reviewed |  |  | 6.2.1
Dec | 6.3.2.2 | Network Transformation and Modernization Support | One-Time | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor format | A027 | A027 Network Modernization Plan | 90 days after award | 2026-12-01 | Tue | 49 |  |  | Not Received | Not Reviewed |  |  | 6.3.2.2
Dec | 6.3.4.2 | PNSOC Support (Optional) | One-Time | Operations | Brian Abrigo | Chris Kuznicki | Vendor format | A040 | A040 Security Monitoring Reports | 90 days after award (PNSOC option) | 2026-12-01 | Tue | 49 |  |  | Not Received | Not Reviewed |  |  | 6.3.4.2 | Only if the PNSOC option is exercised. Flag: Same title as A012; one-time date for ongoing service
Dec | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 14 | 2026-12-04 | Fri | 52 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Dec | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 14 | 2026-12-04 | Fri | 52 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Dec | 6.3.1 | Task Order Mgmt / PMO Support for PMN | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A017 | A017 Integrated Master Schedule | Nov 2026 | 2026-12-07 | Mon | 55 |  |  | Not Received | Not Reviewed |  |  | 6.3.1
Dec | 6.3.1.1 | Monthly Progress Report | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A018 | A018 Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | Nov 2026 | 2026-12-07 | Mon | 55 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.1
Dec | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A020 | A020 Technical Library Documentation Report | Nov 2026 | 2026-12-07 | Mon | 55 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.7
Dec | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A021 | A021 Technical Briefing/ Presentation | Nov 2026 | 2026-12-07 | Mon | 55 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.7
Dec | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 15 | 2026-12-11 | Fri | 59 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Dec | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 15 | 2026-12-11 | Fri | 59 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Dec | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 16 | 2026-12-18 | Fri | 66 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Dec | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 16 | 2026-12-18 | Fri | 66 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Dec | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 17 | 2026-12-25 | Fri | 73 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Dec | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 17 | 2026-12-25 | Fri | 73 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Jan | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 18 | 2027-01-01 | Fri | 80 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Jan | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 18 | 2027-01-01 | Fri | 80 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Jan | 6.3.1.3 | Transition Planning | One-Time | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A042 | A042 Transition-Out Plan | 120 days before end: base year only | 2027-01-03 | Sun | 82 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.3 | Table says T-30 (=BaseEnd-30). Flag: Body: 120 days before end; table: T-30
Jan | 6.1 | Zero Trust AI Implementation | Quarterly | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A006 | A006 STIG/SRG Checklists | Qtr ending 31 Dec 2026 | 2027-01-07 | Thu | 86 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Jan | 6.2.1 | Cybersecurity Engineering / A&A | Quarterly | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A012 | A012 Security Monitoring Reports | Qtr ending 31 Dec 2026 | 2027-01-07 | Thu | 86 |  |  | Not Received | Not Reviewed |  |  | 6.2.1
Jan | 6.2.1 | Cybersecurity Engineering / A&A | Quarterly | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A013 | A013 Vulnerability Scan Reports | Qtr ending 31 Dec 2026 | 2027-01-07 | Thu | 86 |  |  | Not Received | Not Reviewed |  |  | 6.2.1
Jan | 6.3.1 | Task Order Mgmt / PMO Support for PMN | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A017 | A017 Integrated Master Schedule | Dec 2026 | 2027-01-07 | Thu | 86 |  |  | Not Received | Not Reviewed |  |  | 6.3.1
Jan | 6.3.1.1 | Monthly Progress Report | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A018 | A018 Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | Dec 2026 | 2027-01-07 | Thu | 86 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.1
Jan | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A020 | A020 Technical Library Documentation Report | Dec 2026 | 2027-01-07 | Thu | 86 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.7
Jan | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A021 | A021 Technical Briefing/ Presentation | Dec 2026 | 2027-01-07 | Thu | 86 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.7
Jan | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 19 | 2027-01-08 | Fri | 87 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Jan | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 19 | 2027-01-08 | Fri | 87 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Jan | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 20 | 2027-01-15 | Fri | 94 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Jan | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 20 | 2027-01-15 | Fri | 94 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Jan | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 21 | 2027-01-22 | Fri | 101 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Jan | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 21 | 2027-01-22 | Fri | 101 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Jan | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 22 | 2027-01-29 | Fri | 108 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Jan | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 22 | 2027-01-29 | Fri | 108 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Feb | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 23 | 2027-02-05 | Fri | 115 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Feb | 6.3.1 | Task Order Mgmt / PMO Support for PMN | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A017 | A017 Integrated Master Schedule | Jan 2027 | 2027-02-05 | Fri | 115 |  |  | Not Received | Not Reviewed |  |  | 6.3.1
Feb | 6.3.1.1 | Monthly Progress Report | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A018 | A018 Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | Jan 2027 | 2027-02-05 | Fri | 115 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.1
Feb | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 23 | 2027-02-05 | Fri | 115 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Feb | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A020 | A020 Technical Library Documentation Report | Jan 2027 | 2027-02-05 | Fri | 115 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.7
Feb | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A021 | A021 Technical Briefing/ Presentation | Jan 2027 | 2027-02-05 | Fri | 115 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.7
Feb | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 24 | 2027-02-12 | Fri | 122 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Feb | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 24 | 2027-02-12 | Fri | 122 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Feb | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 25 | 2027-02-19 | Fri | 129 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Feb | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 25 | 2027-02-19 | Fri | 129 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Feb | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 26 | 2027-02-26 | Fri | 136 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Feb | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 26 | 2027-02-26 | Fri | 136 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Mar | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 27 | 2027-03-05 | Fri | 143 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Mar | 6.3.1 | Task Order Mgmt / PMO Support for PMN | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A017 | A017 Integrated Master Schedule | Feb 2027 | 2027-03-05 | Fri | 143 |  |  | Not Received | Not Reviewed |  |  | 6.3.1
Mar | 6.3.1.1 | Monthly Progress Report | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A018 | A018 Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | Feb 2027 | 2027-03-05 | Fri | 143 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.1
Mar | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 27 | 2027-03-05 | Fri | 143 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Mar | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A020 | A020 Technical Library Documentation Report | Feb 2027 | 2027-03-05 | Fri | 143 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.7
Mar | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A021 | A021 Technical Briefing/ Presentation | Feb 2027 | 2027-03-05 | Fri | 143 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.7
Mar | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 28 | 2027-03-12 | Fri | 150 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Mar | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 28 | 2027-03-12 | Fri | 150 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Mar | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 29 | 2027-03-19 | Fri | 157 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Mar | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 29 | 2027-03-19 | Fri | 157 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Mar | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 30 | 2027-03-26 | Fri | 164 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Mar | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 30 | 2027-03-26 | Fri | 164 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Apr | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 31 | 2027-04-02 | Fri | 171 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Apr | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 31 | 2027-04-02 | Fri | 171 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Apr | 6.1 | Zero Trust AI Implementation | Quarterly | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A006 | A006 STIG/SRG Checklists | Qtr ending 31 Mar 2027 | 2027-04-07 | Wed | 176 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Apr | 6.2.1 | Cybersecurity Engineering / A&A | Quarterly | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A012 | A012 Security Monitoring Reports | Qtr ending 31 Mar 2027 | 2027-04-07 | Wed | 176 |  |  | Not Received | Not Reviewed |  |  | 6.2.1
Apr | 6.2.1 | Cybersecurity Engineering / A&A | Quarterly | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A013 | A013 Vulnerability Scan Reports | Qtr ending 31 Mar 2027 | 2027-04-07 | Wed | 176 |  |  | Not Received | Not Reviewed |  |  | 6.2.1
Apr | 6.3.1 | Task Order Mgmt / PMO Support for PMN | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A017 | A017 Integrated Master Schedule | Mar 2027 | 2027-04-07 | Wed | 176 |  |  | Not Received | Not Reviewed |  |  | 6.3.1
Apr | 6.3.1.1 | Monthly Progress Report | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A018 | A018 Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | Mar 2027 | 2027-04-07 | Wed | 176 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.1
Apr | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A020 | A020 Technical Library Documentation Report | Mar 2027 | 2027-04-07 | Wed | 176 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.7
Apr | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A021 | A021 Technical Briefing/ Presentation | Mar 2027 | 2027-04-07 | Wed | 176 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.7
Apr | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 32 | 2027-04-09 | Fri | 178 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Apr | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 32 | 2027-04-09 | Fri | 178 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Apr | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 33 | 2027-04-16 | Fri | 185 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Apr | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 33 | 2027-04-16 | Fri | 185 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Apr | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 34 | 2027-04-23 | Fri | 192 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Apr | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 34 | 2027-04-23 | Fri | 192 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
Apr | 6.1 | Zero Trust AI Implementation | Weekly | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A007 | A007 ACAS Scans | Wk 35 | 2027-04-30 | Fri | 199 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Apr | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 | A019 Weekly Activity Report (WAR) | Wk 35 | 2027-04-30 | Fri | 199 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.2, 6.3.1.4
May | 6.3.1.3 | Transition Planning | One-Time | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A043 | A043 Task Order Closeout | End of agreement: base year only | 2027-05-03 | Mon | 202 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.3
May | 6.3.1 | Task Order Mgmt / PMO Support for PMN | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A017 | A017 Integrated Master Schedule | Apr 2027 | 2027-05-07 | Fri | 206 |  |  | Not Received | Not Reviewed |  |  | 6.3.1
May | 6.3.1.1 | Monthly Progress Report | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A018 | A018 Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | Apr 2027 | 2027-05-07 | Fri | 206 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.1
May | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A020 | A020 Technical Library Documentation Report | Apr 2027 | 2027-05-07 | Fri | 206 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.7
May | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A021 | A021 Technical Briefing/ Presentation | Apr 2027 | 2027-05-07 | Fri | 206 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.7
Jul | 6.1 | Zero Trust AI Implementation | Quarterly | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A006 | A006 STIG/SRG Checklists | Qtr ending 30 Jun 2027 | 2027-07-07 | Wed | 267 |  |  | Not Received | Not Reviewed |  |  | 6.1, 6.2.1
Jul | 6.2.1 | Cybersecurity Engineering / A&A | Quarterly | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A012 | A012 Security Monitoring Reports | Qtr ending 30 Jun 2027 | 2027-07-07 | Wed | 267 |  |  | Not Received | Not Reviewed |  |  | 6.2.1
Jul | 6.2.1 | Cybersecurity Engineering / A&A | Quarterly | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A013 | A013 Vulnerability Scan Reports | Qtr ending 30 Jun 2027 | 2027-07-07 | Wed | 267 |  |  | Not Received | Not Reviewed |  |  | 6.2.1
Jun | 6.3.1.3 | Transition Planning | One-Time | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A042 | A042 Transition-Out Plan | 120 days before end: all options | 2029-06-01 | Fri | 962 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.3 | Table says T-30 (=FinalEnd-30).
Sep | 6.3.1.3 | Transition Planning | One-Time | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A043 | A043 Task Order Closeout | End of agreement: all options | 2029-09-29 | Sat | 1082 |  |  | Not Received | Not Reviewed |  |  | 6.3.1.3
| 6.1 | Zero Trust AI Implementation | One-Time + Updates | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A001 | A001 Implementation Approach and Architecture | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.1 | PWS due: IAW IMS. Freq: One-Time, update as needed Flag: Due "IAW IMS"; IMS must exist first
| 6.1 | Zero Trust AI Implementation | One-Time + Updates | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A002 | A002 ZT Governance Plan | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.1 | PWS due: IAW IMS. Freq: One-Time, update as needed Flag: Due "IAW IMS"
| 6.2.1 | Cybersecurity Engineering / A&A | As Needed | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A003 | A003 eMASS Data Entry | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.2.1 | PWS due: IAW IMS. Freq: As Needed
| 6.1 | Zero Trust AI Implementation | One-Time + Updates | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A004 | A004 ATO Documentation/ Artifacts | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.1, 6.2.1 | PWS due: IAW IMS. Freq: One-Time, update as needed Flag: Due "IAW IMS"
| 6.1 | Zero Trust AI Implementation | As Needed | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A005 | A005 POA&Ms including risk acceptance POA&Ms for vulnerabilities that cannot be mitigated and STIGs that cannot be applied. | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.1, 6.2.1 | PWS due: 30 days post vulnerability identification (if vulnerability cannot be mitigated). Freq: As Needed Flag: Body: CAT I POA&M if no fix in 1 week
| 6.2.1 | Cybersecurity Engineering / A&A | As Needed | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A008 | A008 System Change Requests Form/ Configuration Change Request | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.2.1 | PWS due: As needed. Freq: As required
| 6.2.1 | Cybersecurity Engineering / A&A | One-Time + Updates | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A009 | A009 eMASS Package | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.2.1 | PWS due: As needed. Freq: One-Time per package, update as needed
| 6.2.1 | Cybersecurity Engineering / A&A | As Needed | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A010 | A010 Status updates on Security patches/hot fixes, OPORD, TASK ORDER, FISMA, PPSM, IAVM and STIGs | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.2.1 | PWS due: As needed. Freq: As required
| 6.2.1 | Cybersecurity Engineering / A&A | One-Time + Updates | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A011 | A011 Incident Response Plan | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.2.1 | PWS due: IAW IMS. Freq: One-Time, update as needed Flag: Due "IAW IMS"
| 6.2.1 | Cybersecurity Engineering / A&A | Per Package | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor format | A015 | A015 Security Assessment Report | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.2.1 | PWS due: ICW Accreditation. Freq: One per accreditation package
| 6.1 | Zero Trust AI Implementation | As Needed | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor format | A016 | A016 Briefings Slides | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.1, 6.2.2, 6.3.2.1, 6.3.2.4, 6.3.3.1 | PWS due: As determined by the Government. Freq: As required
| 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | As Needed | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A022 | A022 Knowledge Management Site | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.3.1.7 | PWS due: ICW MSR. Freq: Updated, as needed Flag: ICW MSR = Monthly Status Report; confirm it equals the MPR
| 6.3.2.1 | Analysis of Alternatives | As Needed | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor format | A023 | A023 Whitepapers | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.3.2.1, 6.3.2.3, 6.3.3.1 | PWS due: ICW MSR. Freq: As needed Flag: Table omits this paragraph (6.3.2.4)
| 6.1 | Zero Trust AI Implementation | As Needed | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor format | A024 | A024 DoDAF Artifacts/Diagrams (e.g., OV, SV) | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.1, 6.3.2.4, 6.3.3.1 | PWS due: As determined by the Government. Freq: As needed
| 6.1 | Zero Trust AI Implementation | As Needed | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A025 | A025 Engineering Artifacts (e.g., Network/System Diagrams) | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.1, 6.3.2.4, 6.3.4.1.3, 6.3.4.1.4, 6.3.4.1.5 | PWS due: Within 10 business days after assignment. Freq: As needed Flag: Near-duplicate of A032
| 6.1 | Zero Trust AI Implementation | One-Time + Updates | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A026 | A026 Concept of Operations (CONOPS) | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.1 | PWS due: 60 days post deployment. Freq: Once, updated yearly or with major change
| 6.3.2.3 | Zero Trust Policy Assessment | One-Time + Updates | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor format | A028 | A028 ZT Traceability Matrix | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.3.2.3 | PWS due: ICW MSR. Freq: One-Time, updated yearly or with major change Flag: ICW MSR = Monthly Status Report; confirm it equals the MPR
| 6.3.2.3 | Zero Trust Policy Assessment | One-Time + Updates | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor format | A029 | A029 ZT Gap Analysis | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.3.2.3 | PWS due: As determined by the Government. Freq: One-Time, updated yearly or with major change
| 6.3.2.3 | Zero Trust Policy Assessment | One-Time + Updates | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor format | A030 | A030 Zero Trust Architecture Design Document | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.3.2.3 | PWS due: As determined by the Government. Freq: One-Time, updated yearly or with major change
| 6.3.2.5 | AppSS Integration, Implementation and Cutover | As Needed | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor format | A031 | A031 Implementation Plan | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.3.2.5, 6.3.3.2, 6.3.3.3 | PWS due: 30 days before Implementation. Freq: As needed
| 6.3.2.5 | AppSS Integration, Implementation and Cutover | As Needed | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A032 | A032 Engineering Artifacts (e.g., Network/System Diagrams) | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.3.2.5, 6.3.3.1, 6.3.3.2, 6.3.3.3 | PWS due: Within 10 business days after assignment. Freq: As needed Flag: Near-duplicate of A025
| 6.3.2.5 | AppSS Integration, Implementation and Cutover | One-Time | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A033 | A033 ASIs | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.3.2.5, 6.3.3.2, 6.3.3.3 | PWS due: 10 days upon expected outage unless otherwise noted by the Government (must receive Gov’t approval). Freq: One-Time
| 6.3.3.1 | Site Specific Advanced Engineering Services | One-Time | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor / Gov approved | A034 | A034 Site Survey Reports | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.3.2.6, 6.3.3.1 | PWS due: IAW IMS. Freq: One-Time Flag: Table also cites 6.3.2.6
| 6.3.4.1.1 | 8x5 Tier III Engineering | One-Time + Updates | Operations | Brian Abrigo | Chris Kuznicki | Government format | A035 | A035 ITSM/ Change Tickets | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.3.4.1.1, 6.3.4.1.2 | PWS due: 10 days prior to necessary change. Freq: One-Time, updated as needed Flag: Table omits this 24x7 paragraph
| 6.3.4.1.2 | Change Mgmt and Help Desk Support (Optional) | One-Time | Operations | Brian Abrigo | Chris Kuznicki | Vendor / Gov approved | A036 | A036 Metrics Report | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.3.4.1.2 | PWS due: 30 Days after Implementation. Freq: One-Time Flag: Table omits this 24x7 paragraph
| 6.3.4.1.2 | Change Mgmt and Help Desk Support (Optional) | One-Time + Updates | Operations | Brian Abrigo | Chris Kuznicki | Vendor / Gov approved | A037 | A037 Help Desk Report | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.3.4.1.2 | PWS due: 24 hours upon request. Freq: One-Time, updated as needed Flag: Table omits this 24x7 paragraph
| 6.3.1.4 | HW / SW Maintenance Support (Logistics) | As Needed | Operations | Brian Abrigo | Chris Kuznicki | Vendor format | A044 | A044 Logistics Deliverables | Event-driven: add a row per delivery | [5 empty] | Not Received | Not Reviewed |  |  | 6.3.1.4 | PWS due: ICW MSR. Freq: Updated as needed Flag: ICW MSR = Monthly Status Report; confirm it equals the MPR
| 6.3.1.5 | Communications | None named | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | n/a | — | None named in PWS | — | [8 empty] | Gap: no deliverable |  | PWS requires: Marketing material, engagement strategy. No deliverable ID or due date.
| 6.3.1.6 | Cyber Capacity | None named | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | n/a | — | None named in PWS | — | [8 empty] | Gap: no deliverable |  | PWS requires: Capacity-building objectives and engagements. No deliverable ID or due date.
| 6.3.2.6 | MPE Enterprise Management Services | None named | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | n/a | — | None named in PWS | — | [8 empty] | Gap: no deliverable |  | PWS requires: SME governance support to MPE / CISO (PWS table cites A034 here; body does not). No deliverable ID or due date.
| 6.3.3.4 | Operational VDI Deployment and Integration | None named | Engineering | Chris Kuznicki | CW4 Michael Butler | n/a | — | None named in PWS | — | [8 empty] | Gap: no deliverable |  | PWS requires: VDI baseline and templates. No deliverable ID or due date.
| 6.3.3.4.1 | DCS Enabled Mission Applications | None named | Engineering | Chris Kuznicki | CW4 Michael Butler | n/a | — | None named in PWS | — | [8 empty] | Gap: no deliverable |  | PWS requires: Data-aware environment, DCS toolsets. No deliverable ID or due date.
| 6.3.3.5 | Identity and Access Management | None named | Engineering | Chris Kuznicki | CW4 Michael Butler | n/a | — | None named in PWS | — | [8 empty] | Gap: no deliverable |  | PWS requires: MFA, RBAC, AD / CAC integration. No deliverable ID or due date.
| 6.3.3.6 | Secure Enclave Migration | None named | Engineering | Chris Kuznicki | CW4 Michael Butler | n/a | — | None named in PWS | — | [8 empty] | Gap: no deliverable |  | PWS requires: "Comprehensive migration plan" with milestones and rollback. No deliverable ID or due date.
| 6.3.3.7 | Exercise Support | None named | Operations | Brian Abrigo | Chris Kuznicki | n/a | — | None named in PWS | — | [8 empty] | Gap: no deliverable |  | PWS requires: Exercise architecture and design documentation. No deliverable ID or due date.
Formulas:
Gov Inspect-By = IF([Date Submitted]="","",WORKDAY([Date Submitted],ReviewDays))