## Tracker
Thunderdome ZT Production OTA – Deliverable Tracker
Agreement HC1084-26-9-2023 ¦ Vendor: Booz Allen Hamilton ¦ PWS as of 02 Sep 2026 ¦ Clock start 02 Sep 2026
Government POCs |  | Primary: Christine Y. Shigeta (christine.y.shigeta.civ@us.navy.mil) ¦ Secondary: Brian Abrigo, AOR (brian.k.abrigo.civ@us.navy.mil)
At a glance |  | Overdue | Due within 7 days | Awaiting Gov decision | Accepted (recorded) | Accepted: who/when missing | PWS paragraphs with no deliverable
|  | 23 | 2 | 0 | 0 | 0 | 8
Lists (dropdown sources)
Month | Sub Task Number | Paragraph / Section | Frequency | Category | Primary POC | Secondary POC | Format of Deliverable | Deliverable 1 | Deliverable 2 | Deliverable 3 | Deliverable 4 | Deliverable 5 | Status Flow 1 | Status Flow 2 | Status Flow 3 | Accepted By | Date Accepted | Category | Status Flow 1 | Status Flow 2 | Status Flow 3 | Frequency | Month | People
Oct | 6.1 | Zero Trust AI Implementation (1 of 2) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Government format | A001 Implementation Approach and Architecture | A002 ZT Governance Plan | A004 ATO Documentation/ Artifacts | A005 POA&Ms including risk acceptance POA&Ms for vulnerabilities that cannot be mitigated and STIGs that cannot be applied. | A006 STIG/SRG Checklists | Not Received | Not Reviewed |  |  |  | Program Mgmt | Received | Reviewed | Accepted | Weekly | Jan | Christine Y. Shigeta
[7 empty] | Due / Frequency (per PWS) | Due: IAW IMS Freq: One-Time, update as needed Flag: Due "IAW IMS"; IMS must exist first | Due: IAW IMS Freq: One-Time, update as needed Flag: Due "IAW IMS" | Due: IAW IMS Freq: One-Time, update as needed Flag: Due "IAW IMS" | Due: 30 days post vulnerability identification (if vulnerability cannot be mitigated) Freq: As Needed Flag: Body: CAT I POA&M if no fix in 1 week | Due: Routine Updates Freq: Quarterly Dates: see Quarterly tab | [5 empty] | Engineering | Not Received | Not Reviewed | Returned | Monthly | Feb | Brian Abrigo
Oct | 6.1 | Zero Trust AI Implementation (2 of 2) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A007 ACAS Scans | A016 Briefings Slides | A024 DoDAF Artifacts/Diagrams (e.g., OV, SV) | A025 Engineering Artifacts (e.g., Network/System Diagrams) | A026 Concept of Operations (CONOPS) | Not Received | Not Reviewed |  |  |  | Operations |  | Demonstrated | Returned, but Fixed | Quarterly | Mar
[7 empty] | Due / Frequency (per PWS) | Due: As Needed Freq: Weekly Dates: see Weekly tab | Due: As determined by the Government Freq: As required | Due: As determined by the Government Freq: As needed | Due: Within 10 business days after assignment Freq: As needed Flag: Near-duplicate of A032 | Due: 60 days post deployment Freq: Once, updated yearly or with major change | [7 empty] | Not Demonstrated |  | One-Time | Apr
Oct | 6.2.1 | Cybersecurity Engineering / A&A (1 of 3) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A003 eMASS Data Entry | A004 ATO Documentation/ Artifacts | A005 POA&Ms including risk acceptance POA&Ms for vulnerabilities that cannot be mitigated and STIGs that cannot be applied. | A006 STIG/SRG Checklists | A007 ACAS Scans | Not Received | Not Reviewed | [7 empty] | One-Time + Updates | May
[7 empty] | Due / Frequency (per PWS) | Due: IAW IMS Freq: As Needed | Due: IAW IMS Freq: One-Time, update as needed | Due: 30 days post vulnerability identification (if vulnerability cannot be mitigated) Freq: As Needed | Due: Routine Updates Freq: Quarterly Dates: see Quarterly tab | Due: As Needed Freq: Weekly Dates: see Weekly tab | [9 empty] | Per Package | Jun
Oct | 6.2.1 | Cybersecurity Engineering / A&A (2 of 3) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A008 System Change Requests Form/ Configuration Change Request | A009 eMASS Package | A010 Status updates on Security patches/hot fixes, OPORD, TASK ORDER, FISMA, PPSM, IAVM and STIGs | A011 Incident Response Plan | A012 Security Monitoring Reports | Not Received | Not Reviewed | [7 empty] | As Needed | Jul
[7 empty] | Due / Frequency (per PWS) | Due: As needed Freq: As required | Due: As needed Freq: One-Time per package, update as needed | Due: As needed Freq: As required | Due: IAW IMS Freq: One-Time, update as needed Flag: Due "IAW IMS" | Due: Routine Updates Freq: Quarterly Dates: see Quarterly tab Flag: Same title as A040 | [9 empty] | Mixed (see due row) | Aug
Oct | 6.2.1 | Cybersecurity Engineering / A&A (3 of 3) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A013 Vulnerability Scan Reports | A014 Compliance Documentation | A015 Security Assessment Report |  |  | Not Received | Not Reviewed | [7 empty] | None named | Sep
[7 empty] | Due / Frequency (per PWS) | Due: Routine Updates Freq: Quarterly Dates: see Quarterly tab | Due: 90 Days after award Freq: One per accreditation package Date: Tue 1 Dec 2026 | Due: ICW Accreditation Freq: One per accreditation package | [12 empty] | Oct
Oct | 6.2.2 | Partner Nation Coordination / Country Desk Officer Support | As Needed | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Vendor format | A016 Briefings Slides |  |  |  |  | Not Received | Not Reviewed | [8 empty] | Nov
[7 empty] | Due / Frequency (per PWS) | Due: As determined by the Government Freq: As required | [14 empty] | Dec
Oct | 6.3.1 | Task Order Mgmt / PMO Support for PMN | Monthly | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Vendor format | A017 Integrated Master Schedule |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: As determined by the Government Freq: One per month Dates: see Monthly tab
Oct | 6.3.1.1 | Monthly Progress Report | Monthly | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Vendor format | A018 Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: As determined by the Government Freq: One per month Dates: see Monthly tab
Oct | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Vendor format | A019 Weekly Activity Report (WAR) |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: Every Friday Freq: Weekly Dates: see Weekly tab
Oct | 6.3.1.3 | Transition Planning | One-Time | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Vendor format | A041 Transition-In Plan | A042 Transition-Out Plan | A043 Task Order Closeout |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: Initial Draft at Project Kickoff Meeting Final Draft 5 business days after contract award Freq: One-Time Date: draft Wed 2 Sep, final Wed 9 Sep 2026 Flag: Body: 30 days after kickoff | Due: T-30 Days (30 Days Prior to Contract End) Freq: One-Time Date: Sun 3 Jan 2027 (base year only) or Fri 1 Jun 2029 Flag: Body: 120 days before end; table: T-30 | Due: End of Contract Freq: One-Time Date: Mon 3 May 2027 (base year only) or Sat 29 Sep 2029
Oct | 6.3.1.4 | HW / SW Maintenance Support (Logistics) | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Vendor format | A019 Weekly Activity Report (WAR) | A044 Logistics Deliverables |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: Every Friday Freq: Weekly Dates: see Weekly tab | Due: ICW MSR Freq: Updated as needed Flag: ICW MSR = Monthly Status Report; confirm it equals the MPR
Oct | 6.3.1.5 | Communications | None named | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: Marketing material, engagement strategy. No deliverable ID or due date.
Oct | 6.3.1.6 | Cyber Capacity | None named | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: Capacity-building objectives and engagements. No deliverable ID or due date.
Oct | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Mixed (see due row) | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Vendor format | A020 Technical Library Documentation Report | A021 Technical Briefing/ Presentation | A022 Knowledge Management Site |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: ICW MSR Freq: Once per month Dates: see Monthly tab Flag: ICW MSR = Monthly Status Report; confirm it equals the MPR | Due: ICW MSR Freq: One per month Dates: see Monthly tab Flag: ICW MSR = Monthly Status Report; confirm it equals the MPR | Due: ICW MSR Freq: Updated, as needed Flag: ICW MSR = Monthly Status Report; confirm it equals the MPR
Oct | 6.3.2.1 | Analysis of Alternatives | As Needed | Engineering | Christine Y. Shigeta | Brian Abrigo | Vendor format | A016 Briefings Slides | A023 Whitepapers |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: As determined by the Government Freq: As required | Due: ICW MSR Freq: As needed
Oct | 6.3.2.2 | Network Transformation and Modernization Support | One-Time + Updates | Engineering | Christine Y. Shigeta | Brian Abrigo | Vendor format | A027 Network Modernization Plan |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 90 Days after contract award Freq: One-Time, updated yearly or with major change Date: Tue 1 Dec 2026
Oct | 6.3.2.3 | Zero Trust Policy Assessment | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Vendor format | A023 Whitepapers | A028 ZT Traceability Matrix | A029 ZT Gap Analysis | A030 Zero Trust Architecture Design Document |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: ICW MSR Freq: As needed | Due: ICW MSR Freq: One-Time, updated yearly or with major change Flag: ICW MSR = Monthly Status Report; confirm it equals the MPR | Due: As determined by the Government Freq: One-Time, updated yearly or with major change | Due: As determined by the Government Freq: One-Time, updated yearly or with major change
Oct | 6.3.2.4 | Architecture, Design and Engineering | As Needed | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A016 Briefings Slides | A023 Whitepapers | A024 DoDAF Artifacts/Diagrams (e.g., OV, SV) | A025 Engineering Artifacts (e.g., Network/System Diagrams) |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: As determined by the Government Freq: As required | Due: ICW MSR Freq: As needed Flag: Table omits this paragraph (6.3.2.4) | Due: As determined by the Government Freq: As needed | Due: Within 10 business days after assignment Freq: As needed
Oct | 6.3.2.5 | AppSS Integration, Implementation and Cutover | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A031 Implementation Plan | A032 Engineering Artifacts (e.g., Network/System Diagrams) | A033 ASIs |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 30 days before Implementation Freq: As needed | Due: Within 10 business days after assignment Freq: As needed Flag: Near-duplicate of A025 | Due: 10 days upon expected outage unless otherwise noted by the Government (must receive Gov’t approval) Freq: One-Time
Oct | 6.3.2.6 | MPE Enterprise Management Services | None named | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: SME governance support to MPE / CISO (PWS table cites A034 here; body does not). No deliverable ID or due date.
Oct | 6.3.3.1 | Site Specific Advanced Engineering Services | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A016 Briefings Slides | A023 Whitepapers | A024 DoDAF Artifacts/Diagrams (e.g., OV, SV) | A032 Engineering Artifacts (e.g., Network/System Diagrams) | A034 Site Survey Reports | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: As determined by the Government Freq: As required | Due: ICW MSR Freq: As needed | Due: As determined by the Government Freq: As needed | Due: Within 10 business days after assignment Freq: As needed | Due: IAW IMS Freq: One-Time Flag: Table also cites 6.3.2.6
Oct | 6.3.3.2 | Cutover of Existing Solutions | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A031 Implementation Plan | A032 Engineering Artifacts (e.g., Network/System Diagrams) | A033 ASIs |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 30 days before Implementation Freq: As needed | Due: Within 10 business days after assignment Freq: As needed | Due: 10 days upon expected outage unless otherwise noted by the Government (must receive Gov’t approval) Freq: One-Time
Oct | 6.3.3.3 | Cutover of New ZT Solutions | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A031 Implementation Plan | A032 Engineering Artifacts (e.g., Network/System Diagrams) | A033 ASIs |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 30 days before Implementation Freq: As needed | Due: Within 10 business days after assignment Freq: As needed | Due: 10 days upon expected outage unless otherwise noted by the Government (must receive Gov’t approval) Freq: One-Time
Oct | 6.3.3.4 | Operational VDI Deployment and Integration | None named | Engineering | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: VDI baseline and templates. No deliverable ID or due date.
Oct | 6.3.3.4.1 | DCS Enabled Mission Applications | None named | Engineering | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: Data-aware environment, DCS toolsets. No deliverable ID or due date.
Oct | 6.3.3.5 | Identity and Access Management | None named | Engineering | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: MFA, RBAC, AD / CAC integration. No deliverable ID or due date.
Oct | 6.3.3.6 | Secure Enclave Migration | None named | Engineering | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: "Comprehensive migration plan" with milestones and rollback. No deliverable ID or due date.
Oct | 6.3.3.7 | Exercise Support | None named | Operations | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: Exercise architecture and design documentation. No deliverable ID or due date.
Oct | 6.3.4.1.1 | 8x5 Tier III Engineering | One-Time + Updates | Operations | Christine Y. Shigeta | Brian Abrigo | Government format | A035 ITSM/ Change Tickets |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 10 days prior to necessary change Freq: One-Time, updated as needed
Oct | 6.3.4.1.2 | Change Mgmt and Help Desk Support (Optional) | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A035 ITSM/ Change Tickets | A036 Metrics Report | A037 Help Desk Report |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 10 days prior to necessary change Freq: One-Time, updated as needed | Due: 30 Days after Implementation Freq: One-Time | Due: 24 hours upon request Freq: One-Time, updated as needed
Oct | 6.3.4.1.x | 24x7 Tier III Engineering and Help Desk (Optional) | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A035 ITSM/ Change Tickets | A036 Metrics Report | A037 Help Desk Report |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 10 days prior to necessary change Freq: One-Time, updated as needed Flag: Table omits this 24x7 paragraph | Due: 30 Days after Implementation Freq: One-Time Flag: Table omits this 24x7 paragraph | Due: 24 hours upon request Freq: One-Time, updated as needed Flag: Table omits this 24x7 paragraph
Oct | 6.3.4.1.3 | Vendor Lab Testing | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A025 Engineering Artifacts (e.g., Network/System Diagrams) | A038 Test Plans | A039 Test Reports |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: Within 10 business days after assignment Freq: As needed | Due: 30 days after contract award Freq: One-Time, updated as needed Date: Fri 2 Oct 2026 Flag: Due before anything exists to test | Due: 30 days after contract award Freq: One-Time, updated as needed Date: Fri 2 Oct 2026 Flag: Due before anything exists to test
Oct | 6.3.4.1.4 | Government Lab Support | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A025 Engineering Artifacts (e.g., Network/System Diagrams) | A038 Test Plans | A039 Test Reports |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: Within 10 business days after assignment Freq: As needed | Due: 30 days after contract award Freq: One-Time, updated as needed Date: Fri 2 Oct 2026 | Due: 30 days after contract award Freq: One-Time, updated as needed Date: Fri 2 Oct 2026
Oct | 6.3.4.1.5 | DevSecOps (Optional) | As Needed | Engineering | Christine Y. Shigeta | Brian Abrigo | Government format | A025 Engineering Artifacts (e.g., Network/System Diagrams) |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: Within 10 business days after assignment Freq: As needed
Oct | 6.3.4.2 | PNSOC Support (Optional) | One-Time + Updates | Operations | Christine Y. Shigeta | Brian Abrigo | Vendor format | A040 Security Monitoring Reports |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 90 Days after award Freq: One-Time, updated yearly or with major change Date: Tue 1 Dec 2026 Flag: Same title as A012; one-time date for ongoing service
Accepted By / Date Accepted here is per task row. Recurring deliverables record acceptance per period on the Weekly, Monthly and Quarterly tabs; the Daily tab shows everything in date order.

## Weekly
Weekly Deliverables – due every Friday
Agreement HC1084-26-9-2023 ¦ Vendor: Booz Allen Hamilton ¦ PWS as of 02 Sep 2026 ¦ Clock start 02 Sep 2026
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Accepted | Overdue | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35
| Due (Friday) | [6 empty] | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | 2026-10-23 | 2026-10-30 | 2026-11-06 | 2026-11-13 | 2026-11-20 | 2026-11-27 | 2026-12-04 | 2026-12-11 | 2026-12-18 | 2026-12-25 | 2027-01-01 | 2027-01-08 | 2027-01-15 | 2027-01-22 | 2027-01-29 | 2027-02-05 | 2027-02-12 | 2027-02-19 | 2027-02-26 | 2027-03-05 | 2027-03-12 | 2027-03-19 | 2027-03-26 | 2027-04-02 | 2027-04-09 | 2027-04-16 | 2027-04-23 | 2027-04-30
A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 6
Accepted by
Date accepted
A007 | ACAS Scans | 6.1, 6.2.1 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 6
Accepted by
Date accepted
Set Status to Submitted, Accepted, Returned or N/A. When Accepted, record who accepted and the date (the cells turn yellow until you do). A blank Status past its Friday turns red. A019 is explicit in the PWS; Friday for A007 is assumed.
Formulas:
Overdue = SUMPRODUCT((I5:AQ5<TODAY())*([Wk 1]:[Wk 35]=""))

## Monthly
Monthly Deliverables – due 5 business days after month end
Agreement HC1084-26-9-2023 ¦ Vendor: Booz Allen Hamilton ¦ PWS as of 02 Sep 2026 ¦ Clock start 02 Sep 2026
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Accepted | Overdue | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01
| Due | [6 empty] | 2026-10-07 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07 | 2027-05-07
A017 | Integrated Master Schedule | 6.3.1 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 1
Accepted by
Date accepted
A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | 6.3.1.1 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 1
Accepted by
Date accepted
A020 | Technical Library Documentation Report | 6.3.1.7 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 1
Accepted by
Date accepted
A021 | Technical Briefing/ Presentation | 6.3.1.7 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 1
Accepted by
Date accepted
Set Status, then record who accepted and when. The PWS says "as determined by the Government" or "with the Monthly Status Report"; the 5-business-day offset is an assumption set on the Daily tab. Holidays are not excluded.

## Quarterly
Quarterly Deliverables – federal fiscal quarters, due 5 business days after quarter end
Agreement HC1084-26-9-2023 ¦ Vendor: Booz Allen Hamilton ¦ PWS as of 02 Sep 2026 ¦ Clock start 02 Sep 2026
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Accepted | Overdue | 2026-09-30 | 2026-12-31 | 2027-03-31 | 2027-06-30
| Due | [6 empty] | 2026-10-07 | 2027-01-07 | 2027-04-07 | 2027-07-07
A006 | STIG/SRG Checklists | 6.1, 6.2.1 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 1
Accepted by
Date accepted
A012 | Security Monitoring Reports | 6.2.1 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 1
Accepted by
Date accepted
A013 | Vulnerability Scan Reports | 6.2.1 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 1
Accepted by
Date accepted
The PWS says "Quarterly / routine updates" without defining the quarter; federal fiscal quarters are assumed. Confirm with the COR. The last column falls after the base year ends.

## Daily
Daily Agenda – what is due, in date order
Agreement HC1084-26-9-2023 ¦ Vendor: Booz Allen Hamilton ¦ PWS as of 02 Sep 2026 ¦ Clock start 02 Sep 2026
Settings (edit the yellow cells)
Due Date | Day | ID | Deliverable | Source | Status | Accepted By | Date Accepted | Days Until Due | Flag | Notes | Clock start (PWS date) | 2026-09-02
2026-09-02 | Wed | A041 | Transition-In Plan – initial draft | One-time |  |  |  | -41 | OVERDUE | At kickoff (table). Body says 30 days after kickoff = 2 Oct 2026. | Monthly / quarterly due offset (business days) | 5
2026-09-04 | Fri | A007 | ACAS Scans – Wk 1 | Weekly |  |  |  | -39 | OVERDUE |  | Gov inspection window (business days) | 5
2026-09-04 | Fri | A019 | Weekly Activity Report (WAR) – Wk 1 | Weekly |  |  |  | -39 | OVERDUE |  | Resubmission window (business days) | 10
2026-09-09 | Wed | A041 | Transition-In Plan – final draft | One-time |  |  |  | -34 | OVERDUE | 5 business days after award (table). Labor Day not excluded. | End of base period | 2027-05-03
2026-09-11 | Fri | A007 | ACAS Scans – Wk 2 | Weekly |  |  |  | -32 | OVERDUE |  | End of final option year | 2029-09-29
2026-09-11 | Fri | A019 | Weekly Activity Report (WAR) – Wk 2 | Weekly |  |  |  | -32 | OVERDUE |  | Today | 2026-10-13
2026-09-18 | Fri | A007 | ACAS Scans – Wk 3 | Weekly |  |  |  | -25 | OVERDUE
2026-09-18 | Fri | A019 | Weekly Activity Report (WAR) – Wk 3 | Weekly |  |  |  | -25 | OVERDUE |  | Dates on the other tabs recalculate from these cells. Holidays are not excluded.
2026-09-25 | Fri | A007 | ACAS Scans – Wk 4 | Weekly |  |  |  | -18 | OVERDUE
2026-09-25 | Fri | A019 | Weekly Activity Report (WAR) – Wk 4 | Weekly |  |  |  | -18 | OVERDUE
2026-10-02 | Fri | A007 | ACAS Scans – Wk 5 | Weekly |  |  |  | -11 | OVERDUE
2026-10-02 | Fri | A019 | Weekly Activity Report (WAR) – Wk 5 | Weekly |  |  |  | -11 | OVERDUE
2026-10-02 | Fri | A038 | Test Plans | One-time |  |  |  | -11 | OVERDUE | 30 days after award
2026-10-02 | Fri | A039 | Test Reports | One-time |  |  |  | -11 | OVERDUE | 30 days after award
2026-10-07 | Wed | A006 | STIG/SRG Checklists – Qtr ending 30 Sep 2026 | Quarterly |  |  |  | -6 | OVERDUE
2026-10-07 | Wed | A012 | Security Monitoring Reports – Qtr ending 30 Sep 2026 | Quarterly |  |  |  | -6 | OVERDUE
2026-10-07 | Wed | A013 | Vulnerability Scan Reports – Qtr ending 30 Sep 2026 | Quarterly |  |  |  | -6 | OVERDUE
2026-10-07 | Wed | A017 | Integrated Master Schedule – Sep 2026 | Monthly |  |  |  | -6 | OVERDUE
2026-10-07 | Wed | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Sep 2026 | Monthly |  |  |  | -6 | OVERDUE
2026-10-07 | Wed | A020 | Technical Library Documentation Report – Sep 2026 | Monthly |  |  |  | -6 | OVERDUE
2026-10-07 | Wed | A021 | Technical Briefing/ Presentation – Sep 2026 | Monthly |  |  |  | -6 | OVERDUE
2026-10-09 | Fri | A007 | ACAS Scans – Wk 6 | Weekly |  |  |  | -4 | OVERDUE
2026-10-09 | Fri | A019 | Weekly Activity Report (WAR) – Wk 6 | Weekly |  |  |  | -4 | OVERDUE
2026-10-16 | Fri | A007 | ACAS Scans – Wk 7 | Weekly |  |  |  | 3 | Due within 7 days
2026-10-16 | Fri | A019 | Weekly Activity Report (WAR) – Wk 7 | Weekly |  |  |  | 3 | Due within 7 days
2026-10-23 | Fri | A007 | ACAS Scans – Wk 8 | Weekly |  |  |  | 10
2026-10-23 | Fri | A019 | Weekly Activity Report (WAR) – Wk 8 | Weekly |  |  |  | 10
2026-10-30 | Fri | A007 | ACAS Scans – Wk 9 | Weekly |  |  |  | 17
2026-10-30 | Fri | A019 | Weekly Activity Report (WAR) – Wk 9 | Weekly |  |  |  | 17
2026-11-06 | Fri | A007 | ACAS Scans – Wk 10 | Weekly |  |  |  | 24
2026-11-06 | Fri | A017 | Integrated Master Schedule – Oct 2026 | Monthly |  |  |  | 24
2026-11-06 | Fri | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Oct 2026 | Monthly |  |  |  | 24
2026-11-06 | Fri | A019 | Weekly Activity Report (WAR) – Wk 10 | Weekly |  |  |  | 24
2026-11-06 | Fri | A020 | Technical Library Documentation Report – Oct 2026 | Monthly |  |  |  | 24
2026-11-06 | Fri | A021 | Technical Briefing/ Presentation – Oct 2026 | Monthly |  |  |  | 24
2026-11-13 | Fri | A007 | ACAS Scans – Wk 11 | Weekly |  |  |  | 31
2026-11-13 | Fri | A019 | Weekly Activity Report (WAR) – Wk 11 | Weekly |  |  |  | 31
2026-11-20 | Fri | A007 | ACAS Scans – Wk 12 | Weekly |  |  |  | 38
2026-11-20 | Fri | A019 | Weekly Activity Report (WAR) – Wk 12 | Weekly |  |  |  | 38
2026-11-27 | Fri | A007 | ACAS Scans – Wk 13 | Weekly |  |  |  | 45
2026-11-27 | Fri | A019 | Weekly Activity Report (WAR) – Wk 13 | Weekly |  |  |  | 45
2026-12-01 | Tue | A014 | Compliance Documentation | One-time |  |  |  | 49 |  | 90 days after award
2026-12-01 | Tue | A027 | Network Modernization Plan | One-time |  |  |  | 49 |  | 90 days after award
2026-12-01 | Tue | A040 | Security Monitoring Reports (PNSOC option) | One-time |  |  |  | 49 |  | Only if the PNSOC option is exercised
2026-12-04 | Fri | A007 | ACAS Scans – Wk 14 | Weekly |  |  |  | 52
2026-12-04 | Fri | A019 | Weekly Activity Report (WAR) – Wk 14 | Weekly |  |  |  | 52
2026-12-07 | Mon | A017 | Integrated Master Schedule – Nov 2026 | Monthly |  |  |  | 55
2026-12-07 | Mon | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Nov 2026 | Monthly |  |  |  | 55
2026-12-07 | Mon | A020 | Technical Library Documentation Report – Nov 2026 | Monthly |  |  |  | 55
2026-12-07 | Mon | A021 | Technical Briefing/ Presentation – Nov 2026 | Monthly |  |  |  | 55
2026-12-11 | Fri | A007 | ACAS Scans – Wk 15 | Weekly |  |  |  | 59
2026-12-11 | Fri | A019 | Weekly Activity Report (WAR) – Wk 15 | Weekly |  |  |  | 59
2026-12-18 | Fri | A007 | ACAS Scans – Wk 16 | Weekly |  |  |  | 66
2026-12-18 | Fri | A019 | Weekly Activity Report (WAR) – Wk 16 | Weekly |  |  |  | 66
2026-12-25 | Fri | A007 | ACAS Scans – Wk 17 | Weekly |  |  |  | 73
2026-12-25 | Fri | A019 | Weekly Activity Report (WAR) – Wk 17 | Weekly |  |  |  | 73
2027-01-01 | Fri | A007 | ACAS Scans – Wk 18 | Weekly |  |  |  | 80
2027-01-01 | Fri | A019 | Weekly Activity Report (WAR) – Wk 18 | Weekly |  |  |  | 80
2027-01-03 | Sun | A042 | Transition-Out Plan – base year only | One-time |  |  |  | 82 |  | Body: 120 days before end. Table says T-30.
2027-01-07 | Thu | A006 | STIG/SRG Checklists – Qtr ending 31 Dec 2026 | Quarterly |  |  |  | 86
2027-01-07 | Thu | A012 | Security Monitoring Reports – Qtr ending 31 Dec 2026 | Quarterly |  |  |  | 86
2027-01-07 | Thu | A013 | Vulnerability Scan Reports – Qtr ending 31 Dec 2026 | Quarterly |  |  |  | 86
2027-01-07 | Thu | A017 | Integrated Master Schedule – Dec 2026 | Monthly |  |  |  | 86
2027-01-07 | Thu | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Dec 2026 | Monthly |  |  |  | 86
2027-01-07 | Thu | A020 | Technical Library Documentation Report – Dec 2026 | Monthly |  |  |  | 86
2027-01-07 | Thu | A021 | Technical Briefing/ Presentation – Dec 2026 | Monthly |  |  |  | 86
2027-01-08 | Fri | A007 | ACAS Scans – Wk 19 | Weekly |  |  |  | 87
2027-01-08 | Fri | A019 | Weekly Activity Report (WAR) – Wk 19 | Weekly |  |  |  | 87
2027-01-15 | Fri | A007 | ACAS Scans – Wk 20 | Weekly |  |  |  | 94
2027-01-15 | Fri | A019 | Weekly Activity Report (WAR) – Wk 20 | Weekly |  |  |  | 94
2027-01-22 | Fri | A007 | ACAS Scans – Wk 21 | Weekly |  |  |  | 101
2027-01-22 | Fri | A019 | Weekly Activity Report (WAR) – Wk 21 | Weekly |  |  |  | 101
2027-01-29 | Fri | A007 | ACAS Scans – Wk 22 | Weekly |  |  |  | 108
2027-01-29 | Fri | A019 | Weekly Activity Report (WAR) – Wk 22 | Weekly |  |  |  | 108
2027-02-05 | Fri | A007 | ACAS Scans – Wk 23 | Weekly |  |  |  | 115
2027-02-05 | Fri | A017 | Integrated Master Schedule – Jan 2027 | Monthly |  |  |  | 115
2027-02-05 | Fri | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Jan 2027 | Monthly |  |  |  | 115
2027-02-05 | Fri | A019 | Weekly Activity Report (WAR) – Wk 23 | Weekly |  |  |  | 115
2027-02-05 | Fri | A020 | Technical Library Documentation Report – Jan 2027 | Monthly |  |  |  | 115
2027-02-05 | Fri | A021 | Technical Briefing/ Presentation – Jan 2027 | Monthly |  |  |  | 115
2027-02-12 | Fri | A007 | ACAS Scans – Wk 24 | Weekly |  |  |  | 122
2027-02-12 | Fri | A019 | Weekly Activity Report (WAR) – Wk 24 | Weekly |  |  |  | 122
2027-02-19 | Fri | A007 | ACAS Scans – Wk 25 | Weekly |  |  |  | 129
2027-02-19 | Fri | A019 | Weekly Activity Report (WAR) – Wk 25 | Weekly |  |  |  | 129
2027-02-26 | Fri | A007 | ACAS Scans – Wk 26 | Weekly |  |  |  | 136
2027-02-26 | Fri | A019 | Weekly Activity Report (WAR) – Wk 26 | Weekly |  |  |  | 136
2027-03-05 | Fri | A007 | ACAS Scans – Wk 27 | Weekly |  |  |  | 143
2027-03-05 | Fri | A017 | Integrated Master Schedule – Feb 2027 | Monthly |  |  |  | 143
2027-03-05 | Fri | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Feb 2027 | Monthly |  |  |  | 143
2027-03-05 | Fri | A019 | Weekly Activity Report (WAR) – Wk 27 | Weekly |  |  |  | 143
2027-03-05 | Fri | A020 | Technical Library Documentation Report – Feb 2027 | Monthly |  |  |  | 143
2027-03-05 | Fri | A021 | Technical Briefing/ Presentation – Feb 2027 | Monthly |  |  |  | 143
2027-03-12 | Fri | A007 | ACAS Scans – Wk 28 | Weekly |  |  |  | 150
2027-03-12 | Fri | A019 | Weekly Activity Report (WAR) – Wk 28 | Weekly |  |  |  | 150
2027-03-19 | Fri | A007 | ACAS Scans – Wk 29 | Weekly |  |  |  | 157
2027-03-19 | Fri | A019 | Weekly Activity Report (WAR) – Wk 29 | Weekly |  |  |  | 157
2027-03-26 | Fri | A007 | ACAS Scans – Wk 30 | Weekly |  |  |  | 164
2027-03-26 | Fri | A019 | Weekly Activity Report (WAR) – Wk 30 | Weekly |  |  |  | 164
2027-04-02 | Fri | A007 | ACAS Scans – Wk 31 | Weekly |  |  |  | 171
2027-04-02 | Fri | A019 | Weekly Activity Report (WAR) – Wk 31 | Weekly |  |  |  | 171
2027-04-07 | Wed | A006 | STIG/SRG Checklists – Qtr ending 31 Mar 2027 | Quarterly |  |  |  | 176
2027-04-07 | Wed | A012 | Security Monitoring Reports – Qtr ending 31 Mar 2027 | Quarterly |  |  |  | 176
2027-04-07 | Wed | A013 | Vulnerability Scan Reports – Qtr ending 31 Mar 2027 | Quarterly |  |  |  | 176
2027-04-07 | Wed | A017 | Integrated Master Schedule – Mar 2027 | Monthly |  |  |  | 176
2027-04-07 | Wed | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Mar 2027 | Monthly |  |  |  | 176
2027-04-07 | Wed | A020 | Technical Library Documentation Report – Mar 2027 | Monthly |  |  |  | 176
2027-04-07 | Wed | A021 | Technical Briefing/ Presentation – Mar 2027 | Monthly |  |  |  | 176
2027-04-09 | Fri | A007 | ACAS Scans – Wk 32 | Weekly |  |  |  | 178
2027-04-09 | Fri | A019 | Weekly Activity Report (WAR) – Wk 32 | Weekly |  |  |  | 178
2027-04-16 | Fri | A007 | ACAS Scans – Wk 33 | Weekly |  |  |  | 185
2027-04-16 | Fri | A019 | Weekly Activity Report (WAR) – Wk 33 | Weekly |  |  |  | 185
2027-04-23 | Fri | A007 | ACAS Scans – Wk 34 | Weekly |  |  |  | 192
2027-04-23 | Fri | A019 | Weekly Activity Report (WAR) – Wk 34 | Weekly |  |  |  | 192
2027-04-30 | Fri | A007 | ACAS Scans – Wk 35 | Weekly |  |  |  | 199
2027-04-30 | Fri | A019 | Weekly Activity Report (WAR) – Wk 35 | Weekly |  |  |  | 199
2027-05-03 | Mon | A043 | Task Order Closeout – base year only | One-time |  |  |  | 202 |  | End of agreement
2027-05-07 | Fri | A017 | Integrated Master Schedule – Apr 2027 | Monthly |  |  |  | 206
2027-05-07 | Fri | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Apr 2027 | Monthly |  |  |  | 206
2027-05-07 | Fri | A020 | Technical Library Documentation Report – Apr 2027 | Monthly |  |  |  | 206
2027-05-07 | Fri | A021 | Technical Briefing/ Presentation – Apr 2027 | Monthly |  |  |  | 206
2027-07-07 | Wed | A006 | STIG/SRG Checklists – Qtr ending 30 Jun 2027 | Quarterly |  |  |  | 267
2027-07-07 | Wed | A012 | Security Monitoring Reports – Qtr ending 30 Jun 2027 | Quarterly |  |  |  | 267
2027-07-07 | Wed | A013 | Vulnerability Scan Reports – Qtr ending 30 Jun 2027 | Quarterly |  |  |  | 267
2029-06-01 | Fri | A042 | Transition-Out Plan – all options | One-time |  |  |  | 962 |  | Body: 120 days before end. Table says T-30.
2029-09-29 | Sat | A043 | Task Order Closeout – all options | One-time |  |  |  | 1082 |  | End of agreement