## Tracker
Thunderdome ZT Production OTA – Deliverable Tracker
Agreement HC1084-26-9-2023 ¦ Vendor: Booz Allen Hamilton ¦ PWS as of 02 Sep 2026 ¦ Clock start 02 Sep 2026
Government POCs |  | COR / Primary: Christine Y. Shigeta (christine.y.shigeta.civ@us.navy.mil) ¦ Secondary: Brian Abrigo, AOR (brian.k.abrigo.civ@us.navy.mil) ¦ Second acceptor: J698
At a glance |  | Overdue | Due within 7 days | Awaiting COR / J698 | Fully accepted | Returned: resubmit | PWS paragraphs with no deliverable
|  | 23 | 2 | 0 | 0 | 0 | 8
Lists (dropdown sources). Add names below the last entry, then widen the range if needed.
Month | Sub Task Number | Paragraph / Section | Frequency | Category | Primary POC | Secondary POC | Format of Deliverable | Deliverable 1 | Deliverable 2 | Deliverable 3 | Deliverable 4 | Deliverable 5 | Status Flow 1 | Status Flow 2 | Status Flow 3 | COR Accepted By | COR Date Accepted | J698 Accepted By | J698 Date Accepted | Category | Status Flow 1 | Status Flow 2 | Status Flow 3 | Frequency | Month | COR Acceptors | J698 Acceptors
Oct | 6.1 | Zero Trust AI Implementation (1 of 2) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Government format | A001 Implementation Approach and Architecture | A002 ZT Governance Plan | A004 ATO Documentation/ Artifacts | A005 POA&Ms including risk acceptance POA&Ms for vulnerabilities that cannot be mitigated and STIGs that cannot be applied. | A006 STIG/SRG Checklists | Not Received | Not Reviewed | [5 empty] | Program Mgmt | Received | Reviewed | Accepted | Weekly | Jan | Christine Y. Shigeta | J698
[7 empty] | Due / Frequency (per PWS) | Due: IAW IMS Freq: One-Time, update as needed Flag: Due "IAW IMS"; IMS must exist first | Due: IAW IMS Freq: One-Time, update as needed Flag: Due "IAW IMS" | Due: IAW IMS Freq: One-Time, update as needed Flag: Due "IAW IMS" | Due: 30 days post vulnerability identification (if vulnerability cannot be mitigated) Freq: As Needed Flag: Body: CAT I POA&M if no fix in 1 week | Due: Routine Updates Freq: Quarterly Dates: see Quarterly tab | [7 empty] | Engineering | Not Received | Not Reviewed | Returned | Monthly | Feb | Brian Abrigo
Oct | 6.1 | Zero Trust AI Implementation (2 of 2) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A007 ACAS Scans | A016 Briefings Slides | A024 DoDAF Artifacts/Diagrams (e.g., OV, SV) | A025 Engineering Artifacts (e.g., Network/System Diagrams) | A026 Concept of Operations (CONOPS) | Not Received | Not Reviewed | [5 empty] | Operations |  | Demonstrated | Returned, but Fixed | Quarterly | Mar
[7 empty] | Due / Frequency (per PWS) | Due: As Needed Freq: Weekly Dates: see Weekly tab | Due: As determined by the Government Freq: As required | Due: As determined by the Government Freq: As needed | Due: Within 10 business days after assignment Freq: As needed Flag: Near-duplicate of A032 | Due: 60 days post deployment Freq: Once, updated yearly or with major change | [9 empty] | Not Demonstrated |  | One-Time | Apr
Oct | 6.2.1 | Cybersecurity Engineering / A&A (1 of 3) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A003 eMASS Data Entry | A004 ATO Documentation/ Artifacts | A005 POA&Ms including risk acceptance POA&Ms for vulnerabilities that cannot be mitigated and STIGs that cannot be applied. | A006 STIG/SRG Checklists | A007 ACAS Scans | Not Received | Not Reviewed | [9 empty] | One-Time + Updates | May
[7 empty] | Due / Frequency (per PWS) | Due: IAW IMS Freq: As Needed | Due: IAW IMS Freq: One-Time, update as needed | Due: 30 days post vulnerability identification (if vulnerability cannot be mitigated) Freq: As Needed | Due: Routine Updates Freq: Quarterly Dates: see Quarterly tab | Due: As Needed Freq: Weekly Dates: see Weekly tab | [11 empty] | Per Package | Jun
Oct | 6.2.1 | Cybersecurity Engineering / A&A (2 of 3) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A008 System Change Requests Form/ Configuration Change Request | A009 eMASS Package | A010 Status updates on Security patches/hot fixes, OPORD, TASK ORDER, FISMA, PPSM, IAVM and STIGs | A011 Incident Response Plan | A012 Security Monitoring Reports | Not Received | Not Reviewed | [9 empty] | As Needed | Jul
[7 empty] | Due / Frequency (per PWS) | Due: As needed Freq: As required | Due: As needed Freq: One-Time per package, update as needed | Due: As needed Freq: As required | Due: IAW IMS Freq: One-Time, update as needed Flag: Due "IAW IMS" | Due: Routine Updates Freq: Quarterly Dates: see Quarterly tab Flag: Same title as A040 | [11 empty] | Mixed (see due row) | Aug
Oct | 6.2.1 | Cybersecurity Engineering / A&A (3 of 3) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A013 Vulnerability Scan Reports | A014 Compliance Documentation | A015 Security Assessment Report |  |  | Not Received | Not Reviewed | [9 empty] | None named | Sep
[7 empty] | Due / Frequency (per PWS) | Due: Routine Updates Freq: Quarterly Dates: see Quarterly tab | Due: 90 Days after award Freq: One per accreditation package Date: Tue 1 Dec 2026 | Due: ICW Accreditation Freq: One per accreditation package | [14 empty] | Oct
Oct | 6.2.2 | Partner Nation Coordination / Country Desk Officer Support | As Needed | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Vendor format | A016 Briefings Slides |  |  |  |  | Not Received | Not Reviewed | [10 empty] | Nov
[7 empty] | Due / Frequency (per PWS) | Due: As determined by the Government Freq: As required | [16 empty] | Dec
Oct | 6.3.1 | Task Order Mgmt / PMO Support for PMN | Monthly | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Vendor format | A017 Integrated Master Schedule |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: As determined by the Government Freq: One per month Dates: see Monthly tab
Oct | 6.3.1.1 | Monthly Progress Report | Monthly | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Vendor format | A018 Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: As determined by the Government Freq: One per month Dates: see Monthly tab
Oct | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Vendor format | A019 Weekly Activity Report (WAR) |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: Every Friday Freq: Weekly Dates: see Weekly tab
Oct | 6.3.1.3 | Transition Planning | One-Time | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Vendor format | A041 Transition-In Plan | A042 Transition-Out Plan | A043 Task Order Closeout |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: Initial Draft at Project Kickoff Meeting Final Draft 5 business days after contract award Freq: One-Time Date: draft Wed 2 Sep, final Wed 9 Sep 2026 Flag: Body: 30 days after kickoff | Due: T-30 Days (30 Days Prior to Contract End) Freq: One-Time Date: Sun 3 Jan 2027 (base year only) or Fri 1 Jun 2029 Flag: Body: 120 days before end; table: T-30 | Due: End of Contract Freq: One-Time Date: Mon 3 May 2027 (base year only) or Sat 29 Sep 2029
Oct | 6.3.1.4 | HW / SW Maintenance Support (Logistics) | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Vendor format | A019 Weekly Activity Report (WAR) | A044 Logistics Deliverables |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: Every Friday Freq: Weekly Dates: see Weekly tab | Due: ICW MSR Freq: Updated as needed Flag: ICW MSR = Monthly Status Report; confirm it equals the MPR
Oct | 6.3.1.5 | Communications | None named | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: Marketing material, engagement strategy. No deliverable ID or due date.
Oct | 6.3.1.6 | Cyber Capacity | None named | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: Capacity-building objectives and engagements. No deliverable ID or due date.
Oct | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Mixed (see due row) | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Vendor format | A020 Technical Library Documentation Report | A021 Technical Briefing/ Presentation | A022 Knowledge Management Site |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: ICW MSR Freq: Once per month Dates: see Monthly tab Flag: ICW MSR = Monthly Status Report; confirm it equals the MPR | Due: ICW MSR Freq: One per month Dates: see Monthly tab Flag: ICW MSR = Monthly Status Report; confirm it equals the MPR | Due: ICW MSR Freq: Updated, as needed Flag: ICW MSR = Monthly Status Report; confirm it equals the MPR
Oct | 6.3.2.1 | Analysis of Alternatives | As Needed | Engineering | Christine Y. Shigeta | Brian Abrigo | Vendor format | A016 Briefings Slides | A023 Whitepapers |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: As determined by the Government Freq: As required | Due: ICW MSR Freq: As needed
Oct | 6.3.2.2 | Network Transformation and Modernization Support | One-Time + Updates | Engineering | Christine Y. Shigeta | Brian Abrigo | Vendor format | A027 Network Modernization Plan |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 90 Days after contract award Freq: One-Time, updated yearly or with major change Date: Tue 1 Dec 2026
Oct | 6.3.2.3 | Zero Trust Policy Assessment | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Vendor format | A023 Whitepapers | A028 ZT Traceability Matrix | A029 ZT Gap Analysis | A030 Zero Trust Architecture Design Document |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: ICW MSR Freq: As needed | Due: ICW MSR Freq: One-Time, updated yearly or with major change Flag: ICW MSR = Monthly Status Report; confirm it equals the MPR | Due: As determined by the Government Freq: One-Time, updated yearly or with major change | Due: As determined by the Government Freq: One-Time, updated yearly or with major change
Oct | 6.3.2.4 | Architecture, Design and Engineering | As Needed | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A016 Briefings Slides | A023 Whitepapers | A024 DoDAF Artifacts/Diagrams (e.g., OV, SV) | A025 Engineering Artifacts (e.g., Network/System Diagrams) |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: As determined by the Government Freq: As required | Due: ICW MSR Freq: As needed Flag: Table omits this paragraph (6.3.2.4) | Due: As determined by the Government Freq: As needed | Due: Within 10 business days after assignment Freq: As needed
Oct | 6.3.2.5 | AppSS Integration, Implementation and Cutover | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A031 Implementation Plan | A032 Engineering Artifacts (e.g., Network/System Diagrams) | A033 ASIs |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 30 days before Implementation Freq: As needed | Due: Within 10 business days after assignment Freq: As needed Flag: Near-duplicate of A025 | Due: 10 days upon expected outage unless otherwise noted by the Government (must receive Gov’t approval) Freq: One-Time
Oct | 6.3.2.6 | MPE Enterprise Management Services | None named | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: SME governance support to MPE / CISO (PWS table cites A034 here; body does not). No deliverable ID or due date.
Oct | 6.3.3.1 | Site Specific Advanced Engineering Services | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A016 Briefings Slides | A023 Whitepapers | A024 DoDAF Artifacts/Diagrams (e.g., OV, SV) | A032 Engineering Artifacts (e.g., Network/System Diagrams) | A034 Site Survey Reports | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: As determined by the Government Freq: As required | Due: ICW MSR Freq: As needed | Due: As determined by the Government Freq: As needed | Due: Within 10 business days after assignment Freq: As needed | Due: IAW IMS Freq: One-Time Flag: Table also cites 6.3.2.6
Oct | 6.3.3.2 | Cutover of Existing Solutions | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A031 Implementation Plan | A032 Engineering Artifacts (e.g., Network/System Diagrams) | A033 ASIs |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 30 days before Implementation Freq: As needed | Due: Within 10 business days after assignment Freq: As needed | Due: 10 days upon expected outage unless otherwise noted by the Government (must receive Gov’t approval) Freq: One-Time
Oct | 6.3.3.3 | Cutover of New ZT Solutions | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A031 Implementation Plan | A032 Engineering Artifacts (e.g., Network/System Diagrams) | A033 ASIs |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 30 days before Implementation Freq: As needed | Due: Within 10 business days after assignment Freq: As needed | Due: 10 days upon expected outage unless otherwise noted by the Government (must receive Gov’t approval) Freq: One-Time
Oct | 6.3.3.4 | Operational VDI Deployment and Integration | None named | Engineering | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: VDI baseline and templates. No deliverable ID or due date.
Oct | 6.3.3.4.1 | DCS Enabled Mission Applications | None named | Engineering | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: Data-aware environment, DCS toolsets. No deliverable ID or due date.
Oct | 6.3.3.5 | Identity and Access Management | None named | Engineering | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: MFA, RBAC, AD / CAC integration. No deliverable ID or due date.
Oct | 6.3.3.6 | Secure Enclave Migration | None named | Engineering | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: "Comprehensive migration plan" with milestones and rollback. No deliverable ID or due date.
Oct | 6.3.3.7 | Exercise Support | None named | Operations | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per PWS) | PWS requires: Exercise architecture and design documentation. No deliverable ID or due date.
Oct | 6.3.4.1.1 | 8x5 Tier III Engineering | One-Time + Updates | Operations | Christine Y. Shigeta | Brian Abrigo | Government format | A035 ITSM/ Change Tickets |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 10 days prior to necessary change Freq: One-Time, updated as needed
Oct | 6.3.4.1.2 | Change Mgmt and Help Desk Support (Optional) | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A035 ITSM/ Change Tickets | A036 Metrics Report | A037 Help Desk Report |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 10 days prior to necessary change Freq: One-Time, updated as needed | Due: 30 Days after Implementation Freq: One-Time | Due: 24 hours upon request Freq: One-Time, updated as needed
Oct | 6.3.4.1.x | 24x7 Tier III Engineering and Help Desk (Optional) | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A035 ITSM/ Change Tickets | A036 Metrics Report | A037 Help Desk Report |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 10 days prior to necessary change Freq: One-Time, updated as needed Flag: Table omits this 24x7 paragraph | Due: 30 Days after Implementation Freq: One-Time Flag: Table omits this 24x7 paragraph | Due: 24 hours upon request Freq: One-Time, updated as needed Flag: Table omits this 24x7 paragraph
Oct | 6.3.4.1.3 | Vendor Lab Testing | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A025 Engineering Artifacts (e.g., Network/System Diagrams) | A038 Test Plans | A039 Test Reports |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: Within 10 business days after assignment Freq: As needed | Due: 30 days after contract award Freq: One-Time, updated as needed Date: Fri 2 Oct 2026 Flag: Due before anything exists to test | Due: 30 days after contract award Freq: One-Time, updated as needed Date: Fri 2 Oct 2026 Flag: Due before anything exists to test
Oct | 6.3.4.1.4 | Government Lab Support | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | A025 Engineering Artifacts (e.g., Network/System Diagrams) | A038 Test Plans | A039 Test Reports |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: Within 10 business days after assignment Freq: As needed | Due: 30 days after contract award Freq: One-Time, updated as needed Date: Fri 2 Oct 2026 | Due: 30 days after contract award Freq: One-Time, updated as needed Date: Fri 2 Oct 2026
Oct | 6.3.4.1.5 | DevSecOps (Optional) | As Needed | Engineering | Christine Y. Shigeta | Brian Abrigo | Government format | A025 Engineering Artifacts (e.g., Network/System Diagrams) |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: Within 10 business days after assignment Freq: As needed
Oct | 6.3.4.2 | PNSOC Support (Optional) | One-Time + Updates | Operations | Christine Y. Shigeta | Brian Abrigo | Vendor format | A040 Security Monitoring Reports |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per PWS) | Due: 90 Days after award Freq: One-Time, updated yearly or with major change Date: Tue 1 Dec 2026 Flag: Same title as A012; one-time date for ongoing service
Task rows record the two Government acceptances once per row (COR, then J698). Recurring deliverables record them per period on the Weekly, Monthly and Quarterly tabs. A task is fully accepted when both dates are filled in.

## Weekly
Weekly Deliverables – due every Friday
Agreement HC1084-26-9-2023 ¦ Vendor: Booz Allen Hamilton ¦ PWS as of 02 Sep 2026 ¦ Clock start 02 Sep 2026
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Fully accepted | Overdue | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35
| Due (Friday) | [6 empty] | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | 2026-10-23 | 2026-10-30 | 2026-11-06 | 2026-11-13 | 2026-11-20 | 2026-11-27 | 2026-12-04 | 2026-12-11 | 2026-12-18 | 2026-12-25 | 2027-01-01 | 2027-01-08 | 2027-01-15 | 2027-01-22 | 2027-01-29 | 2027-02-05 | 2027-02-12 | 2027-02-19 | 2027-02-26 | 2027-03-05 | 2027-03-12 | 2027-03-19 | 2027-03-26 | 2027-04-02 | 2027-04-09 | 2027-04-16 | 2027-04-23 | 2027-04-30
A019 | Weekly Activity Report (WAR) | 6.3.1.2, 6.3.1.4 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 6
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
A007 | ACAS Scans | 6.1, 6.2.1 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 6
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
How to fill a period: click the cell next to Status and pick from the dropdown (arrow appears on click). Click COR accepted by to pick Christine or Brian (or type a name), then enter the date. Do the same for J698. When both dates are in, the column turns green and Result reads "Fully accepted". A name without a date (or the reverse) turns yellow. A019 is explicit in the PWS; Friday for A007 is assumed.
Formulas:
Overdue = SUMPRODUCT((I5:AQ5<TODAY())*((([Wk 1]:[Wk 35]="")+([Wk 1]:[Wk 35]="In Progress"))>0)*(((I8:AQ8="")+(I10:AQ10=""))>0))

## Monthly
Monthly Deliverables – due 5 business days after month end
Agreement HC1084-26-9-2023 ¦ Vendor: Booz Allen Hamilton ¦ PWS as of 02 Sep 2026 ¦ Clock start 02 Sep 2026
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Fully accepted | Overdue | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01
| Due | [6 empty] | 2026-10-07 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07 | 2027-05-07
A017 | Integrated Master Schedule | 6.3.1 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 1
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) | 6.3.1.1 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 1
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
A020 | Technical Library Documentation Report | 6.3.1.7 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 1
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
A021 | Technical Briefing/ Presentation | 6.3.1.7 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 1
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
How to fill a period: click the cell next to Status and pick from the dropdown (arrow appears on click). Click COR accepted by to pick Christine or Brian (or type a name), then enter the date. Do the same for J698. When both dates are in, the column turns green and Result reads "Fully accepted". A name without a date (or the reverse) turns yellow. The 5-business-day offset is an assumption (Daily tab settings); the PWS says "as determined by the Government" or "with the Monthly Status Report".

## Quarterly
Quarterly Deliverables – federal fiscal quarters, due 5 business days after quarter end
Agreement HC1084-26-9-2023 ¦ Vendor: Booz Allen Hamilton ¦ PWS as of 02 Sep 2026 ¦ Clock start 02 Sep 2026
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Fully accepted | Overdue | 2026-09-30 | 2026-12-31 | 2027-03-31 | 2027-06-30
| Due | [6 empty] | 2026-10-07 | 2027-01-07 | 2027-04-07 | 2027-07-07
A006 | STIG/SRG Checklists | 6.1, 6.2.1 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 1
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
A012 | Security Monitoring Reports | 6.2.1 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 1
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
A013 | Vulnerability Scan Reports | 6.2.1 | Christine Y. Shigeta | Brian Abrigo | Status | 0 | 1
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
How to fill a period: click the cell next to Status and pick from the dropdown (arrow appears on click). Click COR accepted by to pick Christine or Brian (or type a name), then enter the date. Do the same for J698. When both dates are in, the column turns green and Result reads "Fully accepted". A name without a date (or the reverse) turns yellow. Federal fiscal quarters are assumed; confirm with the COR.

## Daily
Daily Agenda – what is due, in date order
Agreement HC1084-26-9-2023 ¦ Vendor: Booz Allen Hamilton ¦ PWS as of 02 Sep 2026 ¦ Clock start 02 Sep 2026
Settings (edit the yellow cells)
Due Date | Day | ID | Deliverable | Source | Status | COR Accepted By | COR Date Accepted | J698 Accepted By | J698 Date Accepted | Result | Days Until Due | Flag | Notes | Clock start (PWS date) | 2026-09-02
2026-09-02 | Wed | A041 | Transition-In Plan – initial draft | One-time | [6 empty] | -41 | OVERDUE | At kickoff (table). Body says 30 days after kickoff = 2 Oct 2026. | Monthly / quarterly due offset (business days) | 5
2026-09-04 | Fri | A007 | ACAS Scans – Wk 1 | Weekly | [6 empty] | -39 | OVERDUE |  | Gov inspection window (business days) | 5
2026-09-04 | Fri | A019 | Weekly Activity Report (WAR) – Wk 1 | Weekly | [6 empty] | -39 | OVERDUE |  | Resubmission window (business days) | 10
2026-09-09 | Wed | A041 | Transition-In Plan – final draft | One-time | [6 empty] | -34 | OVERDUE | 5 business days after award (table). Labor Day not excluded. | End of base period | 2027-05-03
2026-09-11 | Fri | A007 | ACAS Scans – Wk 2 | Weekly | [6 empty] | -32 | OVERDUE |  | End of final option year | 2029-09-29
2026-09-11 | Fri | A019 | Weekly Activity Report (WAR) – Wk 2 | Weekly | [6 empty] | -32 | OVERDUE |  | Today | 2026-10-13
2026-09-18 | Fri | A007 | ACAS Scans – Wk 3 | Weekly | [6 empty] | -25 | OVERDUE
2026-09-18 | Fri | A019 | Weekly Activity Report (WAR) – Wk 3 | Weekly | [6 empty] | -25 | OVERDUE |  | Dates on the other tabs recalculate from these cells. Holidays are not excluded.
2026-09-25 | Fri | A007 | ACAS Scans – Wk 4 | Weekly | [6 empty] | -18 | OVERDUE
2026-09-25 | Fri | A019 | Weekly Activity Report (WAR) – Wk 4 | Weekly | [6 empty] | -18 | OVERDUE
2026-10-02 | Fri | A007 | ACAS Scans – Wk 5 | Weekly | [6 empty] | -11 | OVERDUE
2026-10-02 | Fri | A019 | Weekly Activity Report (WAR) – Wk 5 | Weekly | [6 empty] | -11 | OVERDUE
2026-10-02 | Fri | A038 | Test Plans | One-time | [6 empty] | -11 | OVERDUE | 30 days after award
2026-10-02 | Fri | A039 | Test Reports | One-time | [6 empty] | -11 | OVERDUE | 30 days after award
2026-10-07 | Wed | A006 | STIG/SRG Checklists – Qtr ending 30 Sep 2026 | Quarterly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | A012 | Security Monitoring Reports – Qtr ending 30 Sep 2026 | Quarterly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | A013 | Vulnerability Scan Reports – Qtr ending 30 Sep 2026 | Quarterly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | A017 | Integrated Master Schedule – Sep 2026 | Monthly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Sep 2026 | Monthly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | A020 | Technical Library Documentation Report – Sep 2026 | Monthly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | A021 | Technical Briefing/ Presentation – Sep 2026 | Monthly | [6 empty] | -6 | OVERDUE
2026-10-09 | Fri | A007 | ACAS Scans – Wk 6 | Weekly | [6 empty] | -4 | OVERDUE
2026-10-09 | Fri | A019 | Weekly Activity Report (WAR) – Wk 6 | Weekly | [6 empty] | -4 | OVERDUE
2026-10-16 | Fri | A007 | ACAS Scans – Wk 7 | Weekly | [6 empty] | 3 | Due within 7 days
2026-10-16 | Fri | A019 | Weekly Activity Report (WAR) – Wk 7 | Weekly | [6 empty] | 3 | Due within 7 days
2026-10-23 | Fri | A007 | ACAS Scans – Wk 8 | Weekly | [6 empty] | 10
2026-10-23 | Fri | A019 | Weekly Activity Report (WAR) – Wk 8 | Weekly | [6 empty] | 10
2026-10-30 | Fri | A007 | ACAS Scans – Wk 9 | Weekly | [6 empty] | 17
2026-10-30 | Fri | A019 | Weekly Activity Report (WAR) – Wk 9 | Weekly | [6 empty] | 17
2026-11-06 | Fri | A007 | ACAS Scans – Wk 10 | Weekly | [6 empty] | 24
2026-11-06 | Fri | A017 | Integrated Master Schedule – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | A019 | Weekly Activity Report (WAR) – Wk 10 | Weekly | [6 empty] | 24
2026-11-06 | Fri | A020 | Technical Library Documentation Report – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | A021 | Technical Briefing/ Presentation – Oct 2026 | Monthly | [6 empty] | 24
2026-11-13 | Fri | A007 | ACAS Scans – Wk 11 | Weekly | [6 empty] | 31
2026-11-13 | Fri | A019 | Weekly Activity Report (WAR) – Wk 11 | Weekly | [6 empty] | 31
2026-11-20 | Fri | A007 | ACAS Scans – Wk 12 | Weekly | [6 empty] | 38
2026-11-20 | Fri | A019 | Weekly Activity Report (WAR) – Wk 12 | Weekly | [6 empty] | 38
2026-11-27 | Fri | A007 | ACAS Scans – Wk 13 | Weekly | [6 empty] | 45
2026-11-27 | Fri | A019 | Weekly Activity Report (WAR) – Wk 13 | Weekly | [6 empty] | 45
2026-12-01 | Tue | A014 | Compliance Documentation | One-time | [6 empty] | 49 |  | 90 days after award
2026-12-01 | Tue | A027 | Network Modernization Plan | One-time | [6 empty] | 49 |  | 90 days after award
2026-12-01 | Tue | A040 | Security Monitoring Reports (PNSOC option) | One-time | [6 empty] | 49 |  | Only if the PNSOC option is exercised
2026-12-04 | Fri | A007 | ACAS Scans – Wk 14 | Weekly | [6 empty] | 52
2026-12-04 | Fri | A019 | Weekly Activity Report (WAR) – Wk 14 | Weekly | [6 empty] | 52
2026-12-07 | Mon | A017 | Integrated Master Schedule – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | A020 | Technical Library Documentation Report – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | A021 | Technical Briefing/ Presentation – Nov 2026 | Monthly | [6 empty] | 55
2026-12-11 | Fri | A007 | ACAS Scans – Wk 15 | Weekly | [6 empty] | 59
2026-12-11 | Fri | A019 | Weekly Activity Report (WAR) – Wk 15 | Weekly | [6 empty] | 59
2026-12-18 | Fri | A007 | ACAS Scans – Wk 16 | Weekly | [6 empty] | 66
2026-12-18 | Fri | A019 | Weekly Activity Report (WAR) – Wk 16 | Weekly | [6 empty] | 66
2026-12-25 | Fri | A007 | ACAS Scans – Wk 17 | Weekly | [6 empty] | 73
2026-12-25 | Fri | A019 | Weekly Activity Report (WAR) – Wk 17 | Weekly | [6 empty] | 73
2027-01-01 | Fri | A007 | ACAS Scans – Wk 18 | Weekly | [6 empty] | 80
2027-01-01 | Fri | A019 | Weekly Activity Report (WAR) – Wk 18 | Weekly | [6 empty] | 80
2027-01-03 | Sun | A042 | Transition-Out Plan – base year only | One-time | [6 empty] | 82 |  | Body: 120 days before end. Table says T-30.
2027-01-07 | Thu | A006 | STIG/SRG Checklists – Qtr ending 31 Dec 2026 | Quarterly | [6 empty] | 86
2027-01-07 | Thu | A012 | Security Monitoring Reports – Qtr ending 31 Dec 2026 | Quarterly | [6 empty] | 86
2027-01-07 | Thu | A013 | Vulnerability Scan Reports – Qtr ending 31 Dec 2026 | Quarterly | [6 empty] | 86
2027-01-07 | Thu | A017 | Integrated Master Schedule – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | A020 | Technical Library Documentation Report – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | A021 | Technical Briefing/ Presentation – Dec 2026 | Monthly | [6 empty] | 86
2027-01-08 | Fri | A007 | ACAS Scans – Wk 19 | Weekly | [6 empty] | 87
2027-01-08 | Fri | A019 | Weekly Activity Report (WAR) – Wk 19 | Weekly | [6 empty] | 87
2027-01-15 | Fri | A007 | ACAS Scans – Wk 20 | Weekly | [6 empty] | 94
2027-01-15 | Fri | A019 | Weekly Activity Report (WAR) – Wk 20 | Weekly | [6 empty] | 94
2027-01-22 | Fri | A007 | ACAS Scans – Wk 21 | Weekly | [6 empty] | 101
2027-01-22 | Fri | A019 | Weekly Activity Report (WAR) – Wk 21 | Weekly | [6 empty] | 101
2027-01-29 | Fri | A007 | ACAS Scans – Wk 22 | Weekly | [6 empty] | 108
2027-01-29 | Fri | A019 | Weekly Activity Report (WAR) – Wk 22 | Weekly | [6 empty] | 108
2027-02-05 | Fri | A007 | ACAS Scans – Wk 23 | Weekly | [6 empty] | 115
2027-02-05 | Fri | A017 | Integrated Master Schedule – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | A019 | Weekly Activity Report (WAR) – Wk 23 | Weekly | [6 empty] | 115
2027-02-05 | Fri | A020 | Technical Library Documentation Report – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | A021 | Technical Briefing/ Presentation – Jan 2027 | Monthly | [6 empty] | 115
2027-02-12 | Fri | A007 | ACAS Scans – Wk 24 | Weekly | [6 empty] | 122
2027-02-12 | Fri | A019 | Weekly Activity Report (WAR) – Wk 24 | Weekly | [6 empty] | 122
2027-02-19 | Fri | A007 | ACAS Scans – Wk 25 | Weekly | [6 empty] | 129
2027-02-19 | Fri | A019 | Weekly Activity Report (WAR) – Wk 25 | Weekly | [6 empty] | 129
2027-02-26 | Fri | A007 | ACAS Scans – Wk 26 | Weekly | [6 empty] | 136
2027-02-26 | Fri | A019 | Weekly Activity Report (WAR) – Wk 26 | Weekly | [6 empty] | 136
2027-03-05 | Fri | A007 | ACAS Scans – Wk 27 | Weekly | [6 empty] | 143
2027-03-05 | Fri | A017 | Integrated Master Schedule – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | A019 | Weekly Activity Report (WAR) – Wk 27 | Weekly | [6 empty] | 143
2027-03-05 | Fri | A020 | Technical Library Documentation Report – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | A021 | Technical Briefing/ Presentation – Feb 2027 | Monthly | [6 empty] | 143
2027-03-12 | Fri | A007 | ACAS Scans – Wk 28 | Weekly | [6 empty] | 150
2027-03-12 | Fri | A019 | Weekly Activity Report (WAR) – Wk 28 | Weekly | [6 empty] | 150
2027-03-19 | Fri | A007 | ACAS Scans – Wk 29 | Weekly | [6 empty] | 157
2027-03-19 | Fri | A019 | Weekly Activity Report (WAR) – Wk 29 | Weekly | [6 empty] | 157
2027-03-26 | Fri | A007 | ACAS Scans – Wk 30 | Weekly | [6 empty] | 164
2027-03-26 | Fri | A019 | Weekly Activity Report (WAR) – Wk 30 | Weekly | [6 empty] | 164
2027-04-02 | Fri | A007 | ACAS Scans – Wk 31 | Weekly | [6 empty] | 171
2027-04-02 | Fri | A019 | Weekly Activity Report (WAR) – Wk 31 | Weekly | [6 empty] | 171
2027-04-07 | Wed | A006 | STIG/SRG Checklists – Qtr ending 31 Mar 2027 | Quarterly | [6 empty] | 176
2027-04-07 | Wed | A012 | Security Monitoring Reports – Qtr ending 31 Mar 2027 | Quarterly | [6 empty] | 176
2027-04-07 | Wed | A013 | Vulnerability Scan Reports – Qtr ending 31 Mar 2027 | Quarterly | [6 empty] | 176
2027-04-07 | Wed | A017 | Integrated Master Schedule – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | A020 | Technical Library Documentation Report – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | A021 | Technical Briefing/ Presentation – Mar 2027 | Monthly | [6 empty] | 176
2027-04-09 | Fri | A007 | ACAS Scans – Wk 32 | Weekly | [6 empty] | 178
2027-04-09 | Fri | A019 | Weekly Activity Report (WAR) – Wk 32 | Weekly | [6 empty] | 178
2027-04-16 | Fri | A007 | ACAS Scans – Wk 33 | Weekly | [6 empty] | 185
2027-04-16 | Fri | A019 | Weekly Activity Report (WAR) – Wk 33 | Weekly | [6 empty] | 185
2027-04-23 | Fri | A007 | ACAS Scans – Wk 34 | Weekly | [6 empty] | 192
2027-04-23 | Fri | A019 | Weekly Activity Report (WAR) – Wk 34 | Weekly | [6 empty] | 192
2027-04-30 | Fri | A007 | ACAS Scans – Wk 35 | Weekly | [6 empty] | 199
2027-04-30 | Fri | A019 | Weekly Activity Report (WAR) – Wk 35 | Weekly | [6 empty] | 199
2027-05-03 | Mon | A043 | Task Order Closeout – base year only | One-time | [6 empty] | 202 |  | End of agreement
2027-05-07 | Fri | A017 | Integrated Master Schedule – Apr 2027 | Monthly | [6 empty] | 206
2027-05-07 | Fri | A018 | Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) – Apr 2027 | Monthly | [6 empty] | 206
2027-05-07 | Fri | A020 | Technical Library Documentation Report – Apr 2027 | Monthly | [6 empty] | 206
2027-05-07 | Fri | A021 | Technical Briefing/ Presentation – Apr 2027 | Monthly | [6 empty] | 206
2027-07-07 | Wed | A006 | STIG/SRG Checklists – Qtr ending 30 Jun 2027 | Quarterly | [6 empty] | 267
2027-07-07 | Wed | A012 | Security Monitoring Reports – Qtr ending 30 Jun 2027 | Quarterly | [6 empty] | 267
2027-07-07 | Wed | A013 | Vulnerability Scan Reports – Qtr ending 30 Jun 2027 | Quarterly | [6 empty] | 267
2029-06-01 | Fri | A042 | Transition-Out Plan – all options | One-time | [6 empty] | 962 |  | Body: 120 days before end. Table says T-30.
2029-09-29 | Sat | A043 | Task Order Closeout – all options | One-time | [6 empty] | 1082 |  | End of agreement