## PWS Deliverables Tracker
THUNDERDOME
Month | Performance Req Section | Sub Task Number | Paragraph / Section | Frequency | Category | Primary Accountable POC | Secondary Accountable POC | Format of Deliverable | Deliverable 1 | Deliverable 2 | Deliverable 3 | Deliverable 4 | Deliverable 5 | Status Flow 1 | Status Flow 2 | Status Flow 3 | Category | Status Flow 1 | Status Flow 2 | Status Flow 3 | Frequency | Month
Oct | 6.1 | 6.1 | Zero Trust AI Implementation (1 of 2) | Mixed (see due row) | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A001 Implementation Approach and Architecture | A002 ZT Governance Plan | A004 ATO Documentation/ Artifacts | A005 POA&Ms including risk acceptance POA&Ms for vulnerabilities that cannot be mitigated and STIGs that cannot be applied. | A006 STIG/SRG Checklists | Not Received | Not Reviewed |  | Program Mgmt | Received | Reviewed | Accepted | Weekly | Jan
[8 empty] | PWS Due Date / Frequency | Due: IAW IMS Freq: One-Time, update as needed Flag: Due "IAW IMS"; IMS must exist first | Due: IAW IMS Freq: One-Time, update as needed Flag: Due "IAW IMS" | Due: IAW IMS Freq: One-Time, update as needed Flag: Due "IAW IMS" | Due: 30 days post vulnerability identification (if vulnerability cannot be mitigated) Freq: As Needed Flag: Body: CAT I POA&M if no fix in 1 week | Due: Routine Updates Freq: Quarterly |  |  |  | Engineering | Not Received | Not Reviewed | Returned | Monthly | Feb
Oct | 6.1 | 6.1 | Zero Trust AI Implementation (2 of 2) | Mixed (see due row) | Engineering | Chris Kuznicki | CW4 Michael Butler | Mixed (see deliverables) | A007 ACAS Scans | A016 Briefings Slides | A024 DoDAF Artifacts/Diagrams (e.g., OV, SV) | A025 Engineering Artifacts (e.g., Network/System Diagrams) | A026 Concept of Operations (CONOPS) | Not Received | Not Reviewed |  | Operations |  | Demonstrated | Returned, but Fixed | Quarterly | Mar
[8 empty] | PWS Due Date / Frequency | Due: As Needed Freq: Weekly | Due: As determined by the Government Freq: As required | Due: As determined by the Government Freq: As needed | Due: Within 10 business days after assignment Freq: As needed Flag: Near-duplicate of A032 | Due: 60 days post deployment Freq: Once, updated yearly or with major change | [5 empty] | Not Demonstrated |  | One-Time | Apr
Oct | 6.2 | 6.2.1 | Cybersecurity Engineering / A&A (1 of 3) | Mixed (see due row) | Engineering | Chris Kuznicki | CW4 Michael Butler | Mixed (see deliverables) | A003 eMASS Data Entry | A004 ATO Documentation/ Artifacts | A005 POA&Ms including risk acceptance POA&Ms for vulnerabilities that cannot be mitigated and STIGs that cannot be applied. | A006 STIG/SRG Checklists | A007 ACAS Scans | Not Received | Not Reviewed | [5 empty] | One-Time + Updates | May
[8 empty] | PWS Due Date / Frequency | Due: IAW IMS Freq: As Needed | Due: IAW IMS Freq: One-Time, update as needed | Due: 30 days post vulnerability identification (if vulnerability cannot be mitigated) Freq: As Needed | Due: Routine Updates Freq: Quarterly | Due: As Needed Freq: Weekly | [7 empty] | Per Package | Jun
Oct | 6.2 | 6.2.1 | Cybersecurity Engineering / A&A (2 of 3) | Mixed (see due row) | Engineering | Chris Kuznicki | CW4 Michael Butler | Mixed (see deliverables) | A008 System Change Requests Form/ Configuration Change Request | A009 eMASS Package | A010 Status updates on Security patches/hot fixes, OPORD, TASK ORDER, FISMA, PPSM, IAVM and STIGs | A011 Incident Response Plan | A012 Security Monitoring Reports | Not Received | Not Reviewed | [5 empty] | As Needed | Jul
[8 empty] | PWS Due Date / Frequency | Due: As needed Freq: As required | Due: As needed Freq: One-Time per package, update as needed | Due: As needed Freq: As required | Due: IAW IMS Freq: One-Time, update as needed Flag: Due "IAW IMS" | Due: Routine Updates Freq: Quarterly Flag: Same title as A040 | [7 empty] | Mixed (see due row) | Aug
Oct | 6.2 | 6.2.1 | Cybersecurity Engineering / A&A (3 of 3) | Mixed (see due row) | Engineering | Chris Kuznicki | CW4 Michael Butler | Mixed (see deliverables) | A013 Vulnerability Scan Reports | A014 Compliance Documentation | A015 Security Assessment Report |  |  | Not Received | Not Reviewed | [5 empty] | None named | Sep
[8 empty] | PWS Due Date / Frequency | Due: Routine Updates Freq: Quarterly | Due: 90 Days after award Freq: One per accreditation package | Due: ICW Accreditation Freq: One per accreditation package | [10 empty] | Oct
Oct | 6.2 | 6.2.2 | Partner Nation Coordination / Country Desk Officer Support | As Needed | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A016 Briefings Slides |  |  |  |  | Not Received | Not Reviewed | [6 empty] | Nov
[8 empty] | PWS Due Date / Frequency | Due: As determined by the Government Freq: As required | [12 empty] | Dec
Oct | 6.3 | 6.3.1 | Task Order Mgmt / PMO Support for PMN | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A017 Integrated Master Schedule |  |  |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: As determined by the Government Freq: One per month
Oct | 6.3 | 6.3.1.1 | Monthly Progress Report | Monthly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A018 Monthly Progress Report (MPR) (including Invoice Data, ODC Data, Travel Data) |  |  |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: As determined by the Government Freq: One per month
Oct | 6.3 | 6.3.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A019 Weekly Activity Report (WAR) |  |  |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: Every Friday Freq: Weekly
Oct | 6.3 | 6.3.1.3 | Transition Planning | One-Time | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A041 Transition-In Plan | A042 Transition-Out Plan | A043 Task Order Closeout |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: Initial Draft at Project Kickoff Meeting Final Draft 5 business days after contract award Freq: One-Time Flag: Body: 30 days after kickoff | Due: T-30 Days (30 Days Prior to Contract End) Freq: One-Time Flag: Body: 120 days before end; table: T-30 | Due: End of Contract Freq: One-Time
Oct | 6.3 | 6.3.1.4 | HW / SW Maintenance Support (Logistics) | Mixed (see due row) | Operations | Brian Abrigo | Chris Kuznicki | Vendor format | A019 Weekly Activity Report (WAR) | A044 Logistics Deliverables |  |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: Every Friday Freq: Weekly | Due: ICW MSR Freq: Updated as needed Flag: "ICW MSR" undefined
Oct | 6.3 | 6.3.1.5 | Communications | None named | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | n/a | None named in PWS
[8 empty] | PWS Due Date / Frequency | PWS requires: Marketing material, engagement strategy. No deliverable ID or due date.
Oct | 6.3 | 6.3.1.6 | Cyber Capacity | None named | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | n/a | None named in PWS
[8 empty] | PWS Due Date / Frequency | PWS requires: Capacity-building objectives and engagements. No deliverable ID or due date.
Oct | 6.3 | 6.3.1.7 | Knowledge Mgmt, Technical Documentation and Meeting Support | Mixed (see due row) | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | Vendor format | A020 Technical Library Documentation Report | A021 Technical Briefing/ Presentation | A022 Knowledge Management Site |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: ICW MSR Freq: Once per month Flag: "ICW MSR" undefined | Due: ICW MSR Freq: One per month Flag: "ICW MSR" undefined | Due: ICW MSR Freq: Updated, as needed Flag: "ICW MSR" undefined
Oct | 6.3 | 6.3.2.1 | Analysis of Alternatives | As Needed | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor format | A016 Briefings Slides | A023 Whitepapers |  |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: As determined by the Government Freq: As required | Due: ICW MSR Freq: As needed
Oct | 6.3 | 6.3.2.2 | Network Transformation and Modernization Support | One-Time + Updates | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor format | A027 Network Modernization Plan |  |  |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: 90 Days after contract award Freq: One-Time, updated yearly or with major change
Oct | 6.3 | 6.3.2.3 | Zero Trust Policy Assessment | Mixed (see due row) | Engineering | Chris Kuznicki | CW4 Michael Butler | Vendor format | A023 Whitepapers | A028 ZT Traceability Matrix | A029 ZT Gap Analysis | A030 Zero Trust Architecture Design Document |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: ICW MSR Freq: As needed | Due: ICW MSR Freq: One-Time, updated yearly or with major change Flag: "ICW MSR" undefined | Due: As determined by the Government Freq: One-Time, updated yearly or with major change | Due: As determined by the Government Freq: One-Time, updated yearly or with major change
Oct | 6.3 | 6.3.2.4 | Architecture, Design and Engineering | As Needed | Engineering | Chris Kuznicki | CW4 Michael Butler | Mixed (see deliverables) | A016 Briefings Slides | A023 Whitepapers | A024 DoDAF Artifacts/Diagrams (e.g., OV, SV) | A025 Engineering Artifacts (e.g., Network/System Diagrams) |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: As determined by the Government Freq: As required | Due: ICW MSR Freq: As needed Flag: Table omits this paragraph (6.3.2.4) | Due: As determined by the Government Freq: As needed | Due: Within 10 business days after assignment Freq: As needed
Oct | 6.3 | 6.3.2.5 | AppSS Integration, Implementation and Cutover | Mixed (see due row) | Engineering | Chris Kuznicki | CW4 Michael Butler | Mixed (see deliverables) | A031 Implementation Plan | A032 Engineering Artifacts (e.g., Network/System Diagrams) | A033 ASIs |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: 30 days before Implementation Freq: As needed | Due: Within 10 business days after assignment Freq: As needed Flag: Near-duplicate of A025 | Due: 10 days upon expected outage unless otherwise noted by the Government (must receive Gov’t approval) Freq: One-Time
Oct | 6.3 | 6.3.2.6 | MPE Enterprise Management Services | None named | Program Mgmt | Dr Marvina Harring | Donovan Cozzens | n/a | None named in PWS
[8 empty] | PWS Due Date / Frequency | PWS requires: SME governance support to MPE / CISO (PWS table cites A034 here; body does not). No deliverable ID or due date.
Oct | 6.3 | 6.3.3.1 | Site Specific Advanced Engineering Services | Mixed (see due row) | Engineering | Chris Kuznicki | CW4 Michael Butler | Mixed (see deliverables) | A016 Briefings Slides | A023 Whitepapers | A024 DoDAF Artifacts/Diagrams (e.g., OV, SV) | A032 Engineering Artifacts (e.g., Network/System Diagrams) | A034 Site Survey Reports | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: As determined by the Government Freq: As required | Due: ICW MSR Freq: As needed | Due: As determined by the Government Freq: As needed | Due: Within 10 business days after assignment Freq: As needed | Due: IAW IMS Freq: One-Time Flag: Table also cites 6.3.2.6
Oct | 6.3 | 6.3.3.2 | Cutover of Existing Solutions | Mixed (see due row) | Engineering | Chris Kuznicki | CW4 Michael Butler | Mixed (see deliverables) | A031 Implementation Plan | A032 Engineering Artifacts (e.g., Network/System Diagrams) | A033 ASIs |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: 30 days before Implementation Freq: As needed | Due: Within 10 business days after assignment Freq: As needed | Due: 10 days upon expected outage unless otherwise noted by the Government (must receive Gov’t approval) Freq: One-Time
Oct | 6.3 | 6.3.3.3 | Cutover of New ZT Solutions | Mixed (see due row) | Engineering | Chris Kuznicki | CW4 Michael Butler | Mixed (see deliverables) | A031 Implementation Plan | A032 Engineering Artifacts (e.g., Network/System Diagrams) | A033 ASIs |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: 30 days before Implementation Freq: As needed | Due: Within 10 business days after assignment Freq: As needed | Due: 10 days upon expected outage unless otherwise noted by the Government (must receive Gov’t approval) Freq: One-Time
Oct | 6.3 | 6.3.3.4 | Operational VDI Deployment and Integration | None named | Engineering | Chris Kuznicki | CW4 Michael Butler | n/a | None named in PWS
[8 empty] | PWS Due Date / Frequency | PWS requires: VDI baseline and templates. No deliverable ID or due date.
Oct | 6.3 | 6.3.3.4.1 | DCS Enabled Mission Applications | None named | Engineering | Chris Kuznicki | CW4 Michael Butler | n/a | None named in PWS
[8 empty] | PWS Due Date / Frequency | PWS requires: Data-aware environment, DCS toolsets. No deliverable ID or due date.
Oct | 6.3 | 6.3.3.5 | Identity and Access Management | None named | Engineering | Chris Kuznicki | CW4 Michael Butler | n/a | None named in PWS
[8 empty] | PWS Due Date / Frequency | PWS requires: MFA, RBAC, AD / CAC integration. No deliverable ID or due date.
Oct | 6.3 | 6.3.3.6 | Secure Enclave Migration | None named | Engineering | Chris Kuznicki | CW4 Michael Butler | n/a | None named in PWS
[8 empty] | PWS Due Date / Frequency | PWS requires: "Comprehensive migration plan" with milestones and rollback. No deliverable ID or due date.
Oct | 6.3 | 6.3.3.7 | Exercise Support | None named | Operations | Brian Abrigo | Chris Kuznicki | n/a | None named in PWS
[8 empty] | PWS Due Date / Frequency | PWS requires: Exercise architecture and design documentation. No deliverable ID or due date.
Oct | 6.3 | 6.3.4.1.1 | 8x5 Tier III Engineering | One-Time + Updates | Operations | Brian Abrigo | Chris Kuznicki | Government format | A035 ITSM/ Change Tickets |  |  |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: 10 days prior to necessary change Freq: One-Time, updated as needed
Oct | 6.3 | 6.3.4.1.2 | Change Mgmt and Help Desk Support (Optional) | Mixed (see due row) | Operations | Brian Abrigo | Chris Kuznicki | Mixed (see deliverables) | A035 ITSM/ Change Tickets | A036 Metrics Report | A037 Help Desk Report |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: 10 days prior to necessary change Freq: One-Time, updated as needed | Due: 30 Days after Implementation Freq: One-Time | Due: 24 hours upon request Freq: One-Time, updated as needed
Oct | 6.3 | 6.3.4.1.x | 24x7 Tier III Engineering and Help Desk (Optional) | Mixed (see due row) | Operations | Brian Abrigo | Chris Kuznicki | Mixed (see deliverables) | A035 ITSM/ Change Tickets | A036 Metrics Report | A037 Help Desk Report |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: 10 days prior to necessary change Freq: One-Time, updated as needed Flag: Table omits this 24x7 paragraph | Due: 30 Days after Implementation Freq: One-Time Flag: Table omits this 24x7 paragraph | Due: 24 hours upon request Freq: One-Time, updated as needed Flag: Table omits this 24x7 paragraph
Oct | 6.3 | 6.3.4.1.3 | Vendor Lab Testing | Mixed (see due row) | Operations | Brian Abrigo | Chris Kuznicki | Mixed (see deliverables) | A025 Engineering Artifacts (e.g., Network/System Diagrams) | A038 Test Plans | A039 Test Reports |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: Within 10 business days after assignment Freq: As needed | Due: 30 days after contract award Freq: One-Time, updated as needed Flag: Due before anything exists to test | Due: 30 days after contract award Freq: One-Time, updated as needed Flag: Due before anything exists to test
Oct | 6.3 | 6.3.4.1.4 | Government Lab Support | Mixed (see due row) | Operations | Brian Abrigo | Chris Kuznicki | Mixed (see deliverables) | A025 Engineering Artifacts (e.g., Network/System Diagrams) | A038 Test Plans | A039 Test Reports |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: Within 10 business days after assignment Freq: As needed | Due: 30 days after contract award Freq: One-Time, updated as needed | Due: 30 days after contract award Freq: One-Time, updated as needed
Oct | 6.3 | 6.3.4.1.5 | DevSecOps (Optional) | As Needed | Engineering | Chris Kuznicki | CW4 Michael Butler | Government format | A025 Engineering Artifacts (e.g., Network/System Diagrams) |  |  |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: Within 10 business days after assignment Freq: As needed
Oct | 6.3 | 6.3.4.2 | PNSOC Support (Optional) | One-Time + Updates | Operations | Brian Abrigo | Chris Kuznicki | Vendor format | A040 Security Monitoring Reports |  |  |  |  | Not Received | Not Reviewed
[8 empty] | PWS Due Date / Frequency | Due: 90 Days after award Freq: One-Time, updated yearly or with major change Flag: Same title as A012; one-time date for ongoing service