## Tracker
MPE PACOM TO 32 Bridge – Deliverable Tracker
PWS: Mission Partner Environment (MPE) Engineering Services for USPACOM ¦ Contract 47QTCK-18-D-0017 ¦ SOS International LLC ¦ Follow-on to HC1047-18-D-0002 / HC1047-23-F0032
Government POCs |  | COR / Alternate COR / Property Administrator: see DITCO Additional Text G1 (not in this file). Acceptors below are carried over from the Thunderdome tracker – edit the lists on the Tracker tab.
At a glance |  | Overdue | Due within 7 days | Awaiting COR / J698 | Fully accepted | Returned: resubmit | PWS paragraphs with no deliverable
|  | 0 | 0 | 0 | 0 | 0 | 2
Lists (dropdown sources). Names you type into an Accepted By cell do not have to be on a list.
Month | Sub Task Number | Paragraph / Section | Frequency | Category | Primary POC | Secondary POC | Format of Deliverable | Deliverable 1 | Deliverable 2 | Deliverable 3 | Deliverable 4 | Deliverable 5 | Status Flow 1 | Status Flow 2 | Status Flow 3 | COR Accepted By | COR Date Accepted | J698 Accepted By | J698 Date Accepted | Category | Status Flow 1 | Status Flow 2 | Status Flow 3 | Frequency | Month | COR Acceptors | J698 Acceptors
Nov | 6.1.1 | Monthly Progress Report | Monthly | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | B01 Monthly Progress Report (MPR) | B02 90-Day Action Plan | B03 Contractor Performance Report (CPR) |  |  | Not Received | Not Reviewed | [5 empty] | Engineering | Received | Reviewed | Accepted | Weekly | Jan | Christine Y. Shigeta | J698
[7 empty] | Due / Frequency (per document) | Due: 10th day of each month; if the 10th day falls on a weekend or holiday, submit on the first business day following Freq: Monthly, on 10th workday | Due: 3 business days prior to the CPR meeting Freq: Final – 60 business days after award, and monthly updates thereafter Final plan: 60 business days after award (see Daily Agenda) Flag: CPR meeting date is not fixed in the PWS; 15th of the month assumed (settings). | Due: Within 5 business days of a CPR meeting Freq: Monthly, within 5 business days after CPR Flag: Assumes CPR meeting on the day set in settings. | [9 empty] | Operations | Not Received | Not Reviewed | Returned | Monthly | Feb | Brian Abrigo
Nov | 6.1.2 | Weekly Activity Report | Weekly | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | MS Word | B04 Weekly Activity Report (WAR) |  |  |  |  | Not Received | Not Reviewed | [5 empty] | Program Mgmt |  | Demonstrated | Returned, but Fixed | Quarterly | Mar | Primary COR (DITCO G1)
[7 empty] | Due / Frequency (per document) | Due: COB every Friday Freq: Friday Recurring weekly | [13 empty] | Not Demonstrated |  | Annual | Apr | Alternate COR (DITCO G1)
Nov | 6.1.3 | Transition-out Plan and Task Order Close Out | One-Time | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | MS Office Suite of Products | B05 Transition- out Plan |  |  |  |  | Not Received | Not Reviewed | [9 empty] | Daily (standing) | May
[7 empty] | Due / Frequency (per document) | Due: 120 calendar days prior to the end of this task order Freq: 120 calendar days prior to the end of a Task Order Dates: see Daily Agenda (120 days before end) | [15 empty] | One-Time | Jun
Nov | 6.2.1 | System Engineering and Development Support | As Needed | Engineering | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | B06 Technical Reports | B07 Technical Presentations | B08 Design Documentation | B09 Software Documentation | B10 Engineering Notes | Not Received | Not Reviewed | [9 empty] | One-Time + Updates | Jul
[7 empty] | Due / Frequency (per document) | Due: As specified in 90-day Action Plan Freq: As required by the COR and Government Project Lead | Due: Drafts within three (3) business days of government requirement; Finals within three (3) business days of receipt of approved draft, with any markups, from Government Freq: Drafts within three (3) business days of Government requirement; Finals within three (3) business days of receipt of approved draft, with any markups, from Government | Due: As specified in 90-day Action Plan Freq: As required by the COR and Government Project Lead | Due: As specified in 90-day Action Plan Freq: As required by the COR and Government Project Lead | Due: As specified in 90-day Action Plan Freq: As required by the COR and Government Project Lead | [11 empty] | As Needed | Aug
Nov | 6.2.2 | Installation and Operations Testing | As Needed | Operations | Christine Y. Shigeta | Brian Abrigo | MS Office Suite of Products | B11 Test Script | B12 Test Report | B13 COTS and GOTS Cost/Benefit Analysis |  |  | Not Received | Not Reviewed | [9 empty] | Mixed (see due row) | Sep
[7 empty] | Due / Frequency (per document) | Due: 30 business days before testing Freq: As required by the COR and Government Project Lead | Due: 20 business days after testing is completed Freq: As required by the COR and Government Project Lead | Due: As specified in 90 business days Action Plan Freq: As required by the COR and Government Project Lead | [13 empty] | None named | Oct
Nov | 6.2.3 | New System Capabilities Implementation and Support | As Needed | Engineering | Christine Y. Shigeta | Brian Abrigo | MS Office Suite of Products | B14 New Capabilities Demonstration Technical Report |  |  |  |  | Not Received | Not Reviewed | [10 empty] | Nov
[7 empty] | Due / Frequency (per document) | Due: 20 business days after demonstration is completed Freq: As required by the COR and Government Project Lead | [16 empty] | Dec
Nov | 6.2.4 | Technical System Software and Training Support | As Needed | Operations | Christine Y. Shigeta | Brian Abrigo | MS Office Suite of Products | B15 Training Materials |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: 30 business days before training delivery Freq: 30 days prior to any on- site, schoolhouse, or CBT
Nov | 6.2.5 | Technical Documentation and Meeting Support | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | MS Office Suite of Products | B16 Technical Library Documentation Report | B17 Technical Briefing/ Presentation |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: 10th day of each month; if the 10th day falls on a weekend or holiday, submit on the first business day following Freq: 10th day of each month | Due: Drafts within three (3) business days of government requirement; Finals within three (3) business days of receipt of approved draft, with any markups, from Government Freq: Drafts within three (3) business days of Government requirement; Finals within three (3) business days of receipt of approved draft, with any markups, from Government
Nov | 6.2.6 | Test and Evaluation / Verify and Validate | As Needed | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Mixed (see deliverables) | B18 Test and Evaluation V&V Report | B19 Technical Procedures Documentation | B20 Engineering Change Proposals (ECP) | B21 Test Scenarios | B22 Test Results | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: As specified in 90-day Action Plan Freq: As required by the COR and Government Project Lead | Due: As specified in 90-day Action Plan Freq: As required by the COR and Government Project Lead | Due: Within ten (10) business days of identified need as a result of testing or operational shortfalls Freq: Within ten (10) business days of identified need as a result of testing or operational shortfalls | Due: 30 business days prior to a test event Freq: 30 business days prior to a test event | Due: Within five (5) business days after a test event Freq: Within five (5) business days after a test event
Nov | 6.2.7 | System and Software / Hardware Interface Req | As Needed | Engineering | Christine Y. Shigeta | Brian Abrigo | Government format | B23 Interface Control Document (ICD) |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: As specified in 90-day Action Plan Freq: As required by the COR and Government Project Lead
Nov | 6.2.8 | Network Management | As Needed | Operations | Christine Y. Shigeta | Brian Abrigo | Vendor format | B24 Network Management. Technical Report |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: As specified in 90-day Action Plan Freq: As required by the COR and Government Project Lead
Nov | 6.2.9 | Knowledge Management | As Needed | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Vendor format | B25 Knowledge Management Artifacts |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: Within five (5) business days of event Freq: Within five (5) business days of event
Nov | 6.2.10 | Remote Field Services | None named | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per document) | PWS requires Field Service Engineer management, operations and maintenance at theater bases (Hawaii, Japan, Guam, Korea, Alaska, Australia, CONUS). No deliverable in Section 11.
Nov | 6.3.1 | Network Security Management | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Government format | B26 Authorization and Accreditation (A&A) Packages | B27 Network Security Test Procedures | B28 Information Assurance Compliance Report |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: As required by the COR Freq: Monthly, if required by the COR and Government Project Lead Flag: Monthly only if the COR requires it. Mark N/A in months it is not required. | Due: As specified in 90-day Action Plan Freq: As required by the COR and Government Project Lead | Due: As specified in 90-day Action Plan Freq: As required by the COR and Government Project Lead
Nov | 6.3.2 | Connections to Network | Monthly | Operations | Christine Y. Shigeta | Brian Abrigo | MS Office Suite of Products | B29 Network Installation / De-installation Report |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: As required by the COR Freq: Monthly, if required by the COR and Government Project Lead Flag: Monthly only if the COR requires it. Mark N/A in months it is not required.
Nov | 6.3.3 | Touch Labor Services | Monthly | Operations | Christine Y. Shigeta | Brian Abrigo | MS Office Suite of Products | B30 IAVA Compliance Report | B31 COMSEC Management Procedures Report |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: As part of the MPR Freq: Monthly | Due: As required by the COR Freq: Monthly, if required by the COR Flag: Monthly only if the COR requires it. Mark N/A in months it is not required.
Nov | 6.3.4 | Handling of Non-Public Information | None named | Operations | Christine Y. Shigeta | Brian Abrigo | n/a | None named in PWS
[7 empty] | Due / Frequency (per document) | PWS requires protection of non-public DoD information (DoDI 8582.01). Duty only; no deliverable in Section 11.
Nov | 6.4.1 | Operations (MPE Enterprise Mgmt) | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | MS Office Suite of Products | B32 Technical Documentation & Report(s) | B33 Trip Report |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: As required by the COR Freq: Monthly, if required by the COR Flag: Monthly only if the COR requires it. Mark N/A in months it is not required. | Due: Within five (5) business days of event Freq: Within five (5) business days of event
Nov | 6.5.1 | Customer Specific Requirements – Direct Support | Weekly | Operations | Christine Y. Shigeta | Brian Abrigo | MS Word | B34 Weekly Activity Report (WAR) |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: COB every Friday Freq: Friday Recurring weekly Flag: WAR is listed twice in Section 11 (6.1.2 and 6.5.1); both are tracked.
Nov | 16.c | Non-Disclosure Agreement Report | Monthly | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | MS Office Suite of Products | B35 Non-Disclosure Agreement Report |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: In accordance with the MPR schedule Freq: As part of the MPR
Task rows record the two Government acceptances once per row. Recurring deliverables record them per period on the Weekly and Monthly tabs. Fully accepted = both dates filled in.

## Weekly
Weekly Deliverables – due every Friday (COB)
PWS: Mission Partner Environment (MPE) Engineering Services for USPACOM ¦ Contract 47QTCK-18-D-0017 ¦ SOS International LLC ¦ Follow-on to HC1047-18-D-0002 / HC1047-23-F0032
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Fully accepted | Overdue | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35 | Wk 36 | Wk 37 | Wk 38 | Wk 39 | Wk 40 | Wk 41 | Wk 42 | Wk 43 | Wk 44 | Wk 45 | Wk 46 | Wk 47 | Wk 48 | Wk 49 | Wk 50 | Wk 51 | Wk 52
B04 | Weekly Activity Report (WAR) | 6.1.2 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-11-13 | 2026-11-20 | 2026-11-27 | 2026-12-04 | 2026-12-11 | 2026-12-18 | 2026-12-25 | 2027-01-01 | 2027-01-08 | 2027-01-15 | 2027-01-22 | 2027-01-29 | 2027-02-05 | 2027-02-12 | 2027-02-19 | 2027-02-26 | 2027-03-05 | 2027-03-12 | 2027-03-19 | 2027-03-26 | 2027-04-02 | 2027-04-09 | 2027-04-16 | 2027-04-23 | 2027-04-30 | 2027-05-07 | 2027-05-14 | 2027-05-21 | 2027-05-28 | 2027-06-04 | 2027-06-11 | 2027-06-18 | 2027-06-25 | 2027-07-02 | 2027-07-09 | 2027-07-16 | 2027-07-23 | 2027-07-30 | 2027-08-06 | 2027-08-13 | 2027-08-20 | 2027-08-27 | 2027-09-03 | 2027-09-10 | 2027-09-17 | 2027-09-24 | 2027-10-01 | 2027-10-08 | 2027-10-15 | 2027-10-22 | 2027-10-29
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
B34 | Weekly Activity Report (WAR) | 6.5.1 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-11-13 | 2026-11-20 | 2026-11-27 | 2026-12-04 | 2026-12-11 | 2026-12-18 | 2026-12-25 | 2027-01-01 | 2027-01-08 | 2027-01-15 | 2027-01-22 | 2027-01-29 | 2027-02-05 | 2027-02-12 | 2027-02-19 | 2027-02-26 | 2027-03-05 | 2027-03-12 | 2027-03-19 | 2027-03-26 | 2027-04-02 | 2027-04-09 | 2027-04-16 | 2027-04-23 | 2027-04-30 | 2027-05-07 | 2027-05-14 | 2027-05-21 | 2027-05-28 | 2027-06-04 | 2027-06-11 | 2027-06-18 | 2027-06-25 | 2027-07-02 | 2027-07-09 | 2027-07-16 | 2027-07-23 | 2027-07-30 | 2027-08-06 | 2027-08-13 | 2027-08-20 | 2027-08-27 | 2027-09-03 | 2027-09-10 | 2027-09-17 | 2027-09-24 | 2027-10-01 | 2027-10-08 | 2027-10-15 | 2027-10-22 | 2027-10-29
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
Set Status, then record who accepted it and when. Friday COB is explicit in the PWS (Section 11).
Formulas:
Overdue = SUMPRODUCT(([Wk 1]:[Wk 52]<TODAY())*((([Wk 1, row below]:[Wk 52, row below]="")+([Wk 1, row below]:[Wk 52, row below]="In Progress"))>0)*(((I8:BH8="")+(I10:BH10=""))>0))

## Monthly
Monthly Deliverables – MPR and companion items
PWS: Mission Partner Environment (MPE) Engineering Services for USPACOM ¦ Contract 47QTCK-18-D-0017 ¦ SOS International LLC ¦ Follow-on to HC1047-18-D-0002 / HC1047-23-F0032
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Fully accepted | Overdue | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01
B01 | Monthly Progress Report (MPR) | 6.1.1 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-12-10 | 2027-01-11 | 2027-02-10 | 2027-03-10 | 2027-04-12 | 2027-05-10 | 2027-06-10 | 2027-07-12 | 2027-08-10 | 2027-09-10 | 2027-10-11 | 2027-11-10
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
B02 | 90-Day Action Plan | 6.1.1 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-12-10 | 2027-01-12 | 2027-02-10 | 2027-03-10 | 2027-04-12 | 2027-05-12 | 2027-06-10 | 2027-07-12 | 2027-08-11 | 2027-09-10 | 2027-10-12 | 2027-11-10
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
B03 | Contractor Performance Report (CPR) | 6.1.1 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-12-22 | 2027-01-22 | 2027-02-22 | 2027-03-22 | 2027-04-22 | 2027-05-21 | 2027-06-22 | 2027-07-22 | 2027-08-20 | 2027-09-22 | 2027-10-22 | 2027-11-22
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
B16 | Technical Library Documentation Report | 6.2.5 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-12-10 | 2027-01-11 | 2027-02-10 | 2027-03-10 | 2027-04-12 | 2027-05-10 | 2027-06-10 | 2027-07-12 | 2027-08-10 | 2027-09-10 | 2027-10-11 | 2027-11-10
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
B26 | Authorization and Accreditation (A&A) Packages | 6.3.1 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-12-10 | 2027-01-11 | 2027-02-10 | 2027-03-10 | 2027-04-12 | 2027-05-10 | 2027-06-10 | 2027-07-12 | 2027-08-10 | 2027-09-10 | 2027-10-11 | 2027-11-10
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
B29 | Network Installation / De-installation Report | 6.3.2 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-12-10 | 2027-01-11 | 2027-02-10 | 2027-03-10 | 2027-04-12 | 2027-05-10 | 2027-06-10 | 2027-07-12 | 2027-08-10 | 2027-09-10 | 2027-10-11 | 2027-11-10
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
B30 | IAVA Compliance Report | 6.3.3 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-12-10 | 2027-01-11 | 2027-02-10 | 2027-03-10 | 2027-04-12 | 2027-05-10 | 2027-06-10 | 2027-07-12 | 2027-08-10 | 2027-09-10 | 2027-10-11 | 2027-11-10
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
B31 | COMSEC Management Procedures Report | 6.3.3 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-12-10 | 2027-01-11 | 2027-02-10 | 2027-03-10 | 2027-04-12 | 2027-05-10 | 2027-06-10 | 2027-07-12 | 2027-08-10 | 2027-09-10 | 2027-10-11 | 2027-11-10
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
B32 | Technical Documentation & Report(s) | 6.4.1 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-12-10 | 2027-01-11 | 2027-02-10 | 2027-03-10 | 2027-04-12 | 2027-05-10 | 2027-06-10 | 2027-07-12 | 2027-08-10 | 2027-09-10 | 2027-10-11 | 2027-11-10
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
B35 | Non-Disclosure Agreement Report | 16.c | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-12-10 | 2027-01-11 | 2027-02-10 | 2027-03-10 | 2027-04-12 | 2027-05-10 | 2027-06-10 | 2027-07-12 | 2027-08-10 | 2027-09-10 | 2027-10-11 | 2027-11-10
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
Set Status, then record who accepted it and when. MPR, Technical Library Report, IAVA and NDA reports are due the 10th (next business day if a weekend or holiday). The 90-Day Action Plan and CPR dates depend on the CPR meeting day in settings (assumed).

## Daily Agenda
Daily Agenda – what is due, in date order
PWS: Mission Partner Environment (MPE) Engineering Services for USPACOM ¦ Contract 47QTCK-18-D-0017 ¦ SOS International LLC ¦ Follow-on to HC1047-18-D-0002 / HC1047-23-F0032
Settings (edit the yellow cells)
Due Date | Day | ID | Deliverable | Source | Status | COR Accepted By | COR Date Accepted | J698 Accepted By | J698 Date Accepted | Result | Days Until Due | Flag | Notes | Clock start (PLACEHOLDER – PoP not stated in this file) | 2026-11-01
2026-11-06 | Fri | B04 | Weekly Activity Report (WAR) – Wk 1 | Weekly | [6 empty] | 24 |  |  | End of 12-month base period | 2027-10-31
2026-11-06 | Fri | B34 | Weekly Activity Report (WAR) – Wk 1 | Weekly | [6 empty] | 24 |  |  | End with 6-month extension (FAR 52.217-8) | 2028-04-30
2026-11-13 | Fri | B04 | Weekly Activity Report (WAR) – Wk 2 | Weekly | [6 empty] | 31 |  |  | CPR meeting day of month (ASSUMED) | 15
2026-11-13 | Fri | B34 | Weekly Activity Report (WAR) – Wk 2 | Weekly | [6 empty] | 31 |  |  | Gov inspection window (business days) | 5
2026-11-20 | Fri | B04 | Weekly Activity Report (WAR) – Wk 3 | Weekly | [6 empty] | 38 |  |  | Resubmission window (business days) | 10
2026-11-20 | Fri | B34 | Weekly Activity Report (WAR) – Wk 3 | Weekly | [6 empty] | 38 |  |  | Today | 2026-10-13
2026-11-27 | Fri | B04 | Weekly Activity Report (WAR) – Wk 4 | Weekly | [6 empty] | 45
2026-11-27 | Fri | B34 | Weekly Activity Report (WAR) – Wk 4 | Weekly | [6 empty] | 45 |  |  | PoP is "completed at TO award" in this PWS: set the real start in cell Q4.
2026-12-04 | Fri | B04 | Weekly Activity Report (WAR) – Wk 5 | Weekly | [6 empty] | 52 |  |  | Inspection and resubmission windows are not stated in this PWS; 5 and 10 business days are placeholders.
2026-12-04 | Fri | B34 | Weekly Activity Report (WAR) – Wk 5 | Weekly | [6 empty] | 52 |  |  | Holidays are not excluded from business-day math.
2026-12-10 | Thu | B01 | Monthly Progress Report (MPR) – Nov 2026 | Monthly | [6 empty] | 58
2026-12-10 | Thu | B02 | 90-Day Action Plan – Nov 2026 | Monthly | [6 empty] | 58
2026-12-10 | Thu | B16 | Technical Library Documentation Report – Nov 2026 | Monthly | [6 empty] | 58
2026-12-10 | Thu | B26 | Authorization and Accreditation (A&A) Packages – Nov 2026 | Monthly | [6 empty] | 58
2026-12-10 | Thu | B29 | Network Installation / De-installation Report – Nov 2026 | Monthly | [6 empty] | 58
2026-12-10 | Thu | B30 | IAVA Compliance Report – Nov 2026 | Monthly | [6 empty] | 58
2026-12-10 | Thu | B31 | COMSEC Management Procedures Report – Nov 2026 | Monthly | [6 empty] | 58
2026-12-10 | Thu | B32 | Technical Documentation & Report(s) – Nov 2026 | Monthly | [6 empty] | 58
2026-12-10 | Thu | B35 | Non-Disclosure Agreement Report – Nov 2026 | Monthly | [6 empty] | 58
2026-12-11 | Fri | B04 | Weekly Activity Report (WAR) – Wk 6 | Weekly | [6 empty] | 59
2026-12-11 | Fri | B34 | Weekly Activity Report (WAR) – Wk 6 | Weekly | [6 empty] | 59
2026-12-18 | Fri | B04 | Weekly Activity Report (WAR) – Wk 7 | Weekly | [6 empty] | 66
2026-12-18 | Fri | B34 | Weekly Activity Report (WAR) – Wk 7 | Weekly | [6 empty] | 66
2026-12-22 | Tue | B03 | Contractor Performance Report (CPR) – Nov 2026 | Monthly | [6 empty] | 70
2026-12-25 | Fri | B04 | Weekly Activity Report (WAR) – Wk 8 | Weekly | [6 empty] | 73
2026-12-25 | Fri | B34 | Weekly Activity Report (WAR) – Wk 8 | Weekly | [6 empty] | 73
2027-01-01 | Fri | B04 | Weekly Activity Report (WAR) – Wk 9 | Weekly | [6 empty] | 80
2027-01-01 | Fri | B34 | Weekly Activity Report (WAR) – Wk 9 | Weekly | [6 empty] | 80
2027-01-08 | Fri | B04 | Weekly Activity Report (WAR) – Wk 10 | Weekly | [6 empty] | 87
2027-01-08 | Fri | B34 | Weekly Activity Report (WAR) – Wk 10 | Weekly | [6 empty] | 87
2027-01-11 | Mon | B01 | Monthly Progress Report (MPR) – Dec 2026 | Monthly | [6 empty] | 90
2027-01-11 | Mon | B16 | Technical Library Documentation Report – Dec 2026 | Monthly | [6 empty] | 90
2027-01-11 | Mon | B26 | Authorization and Accreditation (A&A) Packages – Dec 2026 | Monthly | [6 empty] | 90
2027-01-11 | Mon | B29 | Network Installation / De-installation Report – Dec 2026 | Monthly | [6 empty] | 90
2027-01-11 | Mon | B30 | IAVA Compliance Report – Dec 2026 | Monthly | [6 empty] | 90
2027-01-11 | Mon | B31 | COMSEC Management Procedures Report – Dec 2026 | Monthly | [6 empty] | 90
2027-01-11 | Mon | B32 | Technical Documentation & Report(s) – Dec 2026 | Monthly | [6 empty] | 90
2027-01-11 | Mon | B35 | Non-Disclosure Agreement Report – Dec 2026 | Monthly | [6 empty] | 90
2027-01-12 | Tue | B02 | 90-Day Action Plan – Dec 2026 | Monthly | [6 empty] | 91
2027-01-15 | Fri | B04 | Weekly Activity Report (WAR) – Wk 11 | Weekly | [6 empty] | 94
2027-01-15 | Fri | B34 | Weekly Activity Report (WAR) – Wk 11 | Weekly | [6 empty] | 94
2027-01-22 | Fri | B02 | B02 – Final 90-Day Action Plan | One-time | [6 empty] | 101 |  | Final 90-Day Action Plan: 60 business days after award.
2027-01-22 | Fri | B03 | Contractor Performance Report (CPR) – Dec 2026 | Monthly | [6 empty] | 101
2027-01-22 | Fri | B04 | Weekly Activity Report (WAR) – Wk 12 | Weekly | [6 empty] | 101
2027-01-22 | Fri | B34 | Weekly Activity Report (WAR) – Wk 12 | Weekly | [6 empty] | 101
2027-01-29 | Fri | B04 | Weekly Activity Report (WAR) – Wk 13 | Weekly | [6 empty] | 108
2027-01-29 | Fri | B34 | Weekly Activity Report (WAR) – Wk 13 | Weekly | [6 empty] | 108
2027-02-05 | Fri | B04 | Weekly Activity Report (WAR) – Wk 14 | Weekly | [6 empty] | 115
2027-02-05 | Fri | B34 | Weekly Activity Report (WAR) – Wk 14 | Weekly | [6 empty] | 115
2027-02-10 | Wed | B01 | Monthly Progress Report (MPR) – Jan 2027 | Monthly | [6 empty] | 120
2027-02-10 | Wed | B02 | 90-Day Action Plan – Jan 2027 | Monthly | [6 empty] | 120
2027-02-10 | Wed | B16 | Technical Library Documentation Report – Jan 2027 | Monthly | [6 empty] | 120
2027-02-10 | Wed | B26 | Authorization and Accreditation (A&A) Packages – Jan 2027 | Monthly | [6 empty] | 120
2027-02-10 | Wed | B29 | Network Installation / De-installation Report – Jan 2027 | Monthly | [6 empty] | 120
2027-02-10 | Wed | B30 | IAVA Compliance Report – Jan 2027 | Monthly | [6 empty] | 120
2027-02-10 | Wed | B31 | COMSEC Management Procedures Report – Jan 2027 | Monthly | [6 empty] | 120
2027-02-10 | Wed | B32 | Technical Documentation & Report(s) – Jan 2027 | Monthly | [6 empty] | 120
2027-02-10 | Wed | B35 | Non-Disclosure Agreement Report – Jan 2027 | Monthly | [6 empty] | 120
2027-02-12 | Fri | B04 | Weekly Activity Report (WAR) – Wk 15 | Weekly | [6 empty] | 122
2027-02-12 | Fri | B34 | Weekly Activity Report (WAR) – Wk 15 | Weekly | [6 empty] | 122
2027-02-19 | Fri | B04 | Weekly Activity Report (WAR) – Wk 16 | Weekly | [6 empty] | 129
2027-02-19 | Fri | B34 | Weekly Activity Report (WAR) – Wk 16 | Weekly | [6 empty] | 129
2027-02-22 | Mon | B03 | Contractor Performance Report (CPR) – Jan 2027 | Monthly | [6 empty] | 132
2027-02-26 | Fri | B04 | Weekly Activity Report (WAR) – Wk 17 | Weekly | [6 empty] | 136
2027-02-26 | Fri | B34 | Weekly Activity Report (WAR) – Wk 17 | Weekly | [6 empty] | 136
2027-03-05 | Fri | B04 | Weekly Activity Report (WAR) – Wk 18 | Weekly | [6 empty] | 143
2027-03-05 | Fri | B34 | Weekly Activity Report (WAR) – Wk 18 | Weekly | [6 empty] | 143
2027-03-10 | Wed | B01 | Monthly Progress Report (MPR) – Feb 2027 | Monthly | [6 empty] | 148
2027-03-10 | Wed | B02 | 90-Day Action Plan – Feb 2027 | Monthly | [6 empty] | 148
2027-03-10 | Wed | B16 | Technical Library Documentation Report – Feb 2027 | Monthly | [6 empty] | 148
2027-03-10 | Wed | B26 | Authorization and Accreditation (A&A) Packages – Feb 2027 | Monthly | [6 empty] | 148
2027-03-10 | Wed | B29 | Network Installation / De-installation Report – Feb 2027 | Monthly | [6 empty] | 148
2027-03-10 | Wed | B30 | IAVA Compliance Report – Feb 2027 | Monthly | [6 empty] | 148
2027-03-10 | Wed | B31 | COMSEC Management Procedures Report – Feb 2027 | Monthly | [6 empty] | 148
2027-03-10 | Wed | B32 | Technical Documentation & Report(s) – Feb 2027 | Monthly | [6 empty] | 148
2027-03-10 | Wed | B35 | Non-Disclosure Agreement Report – Feb 2027 | Monthly | [6 empty] | 148
2027-03-12 | Fri | B04 | Weekly Activity Report (WAR) – Wk 19 | Weekly | [6 empty] | 150
2027-03-12 | Fri | B34 | Weekly Activity Report (WAR) – Wk 19 | Weekly | [6 empty] | 150
2027-03-19 | Fri | B04 | Weekly Activity Report (WAR) – Wk 20 | Weekly | [6 empty] | 157
2027-03-19 | Fri | B34 | Weekly Activity Report (WAR) – Wk 20 | Weekly | [6 empty] | 157
2027-03-22 | Mon | B03 | Contractor Performance Report (CPR) – Feb 2027 | Monthly | [6 empty] | 160
2027-03-26 | Fri | B04 | Weekly Activity Report (WAR) – Wk 21 | Weekly | [6 empty] | 164
2027-03-26 | Fri | B34 | Weekly Activity Report (WAR) – Wk 21 | Weekly | [6 empty] | 164
2027-04-02 | Fri | B04 | Weekly Activity Report (WAR) – Wk 22 | Weekly | [6 empty] | 171
2027-04-02 | Fri | B34 | Weekly Activity Report (WAR) – Wk 22 | Weekly | [6 empty] | 171
2027-04-09 | Fri | B04 | Weekly Activity Report (WAR) – Wk 23 | Weekly | [6 empty] | 178
2027-04-09 | Fri | B34 | Weekly Activity Report (WAR) – Wk 23 | Weekly | [6 empty] | 178
2027-04-12 | Mon | B01 | Monthly Progress Report (MPR) – Mar 2027 | Monthly | [6 empty] | 181
2027-04-12 | Mon | B02 | 90-Day Action Plan – Mar 2027 | Monthly | [6 empty] | 181
2027-04-12 | Mon | B16 | Technical Library Documentation Report – Mar 2027 | Monthly | [6 empty] | 181
2027-04-12 | Mon | B26 | Authorization and Accreditation (A&A) Packages – Mar 2027 | Monthly | [6 empty] | 181
2027-04-12 | Mon | B29 | Network Installation / De-installation Report – Mar 2027 | Monthly | [6 empty] | 181
2027-04-12 | Mon | B30 | IAVA Compliance Report – Mar 2027 | Monthly | [6 empty] | 181
2027-04-12 | Mon | B31 | COMSEC Management Procedures Report – Mar 2027 | Monthly | [6 empty] | 181
2027-04-12 | Mon | B32 | Technical Documentation & Report(s) – Mar 2027 | Monthly | [6 empty] | 181
2027-04-12 | Mon | B35 | Non-Disclosure Agreement Report – Mar 2027 | Monthly | [6 empty] | 181
2027-04-16 | Fri | B04 | Weekly Activity Report (WAR) – Wk 24 | Weekly | [6 empty] | 185
2027-04-16 | Fri | B34 | Weekly Activity Report (WAR) – Wk 24 | Weekly | [6 empty] | 185
2027-04-22 | Thu | B03 | Contractor Performance Report (CPR) – Mar 2027 | Monthly | [6 empty] | 191
2027-04-23 | Fri | B04 | Weekly Activity Report (WAR) – Wk 25 | Weekly | [6 empty] | 192
2027-04-23 | Fri | B34 | Weekly Activity Report (WAR) – Wk 25 | Weekly | [6 empty] | 192
2027-04-30 | Fri | B04 | Weekly Activity Report (WAR) – Wk 26 | Weekly | [6 empty] | 199
2027-04-30 | Fri | B34 | Weekly Activity Report (WAR) – Wk 26 | Weekly | [6 empty] | 199
2027-05-07 | Fri | B04 | Weekly Activity Report (WAR) – Wk 27 | Weekly | [6 empty] | 206
2027-05-07 | Fri | B34 | Weekly Activity Report (WAR) – Wk 27 | Weekly | [6 empty] | 206
2027-05-10 | Mon | B01 | Monthly Progress Report (MPR) – Apr 2027 | Monthly | [6 empty] | 209
2027-05-10 | Mon | B16 | Technical Library Documentation Report – Apr 2027 | Monthly | [6 empty] | 209
2027-05-10 | Mon | B26 | Authorization and Accreditation (A&A) Packages – Apr 2027 | Monthly | [6 empty] | 209
2027-05-10 | Mon | B29 | Network Installation / De-installation Report – Apr 2027 | Monthly | [6 empty] | 209
2027-05-10 | Mon | B30 | IAVA Compliance Report – Apr 2027 | Monthly | [6 empty] | 209
2027-05-10 | Mon | B31 | COMSEC Management Procedures Report – Apr 2027 | Monthly | [6 empty] | 209
2027-05-10 | Mon | B32 | Technical Documentation & Report(s) – Apr 2027 | Monthly | [6 empty] | 209
2027-05-10 | Mon | B35 | Non-Disclosure Agreement Report – Apr 2027 | Monthly | [6 empty] | 209
2027-05-12 | Wed | B02 | 90-Day Action Plan – Apr 2027 | Monthly | [6 empty] | 211
2027-05-14 | Fri | B04 | Weekly Activity Report (WAR) – Wk 28 | Weekly | [6 empty] | 213
2027-05-14 | Fri | B34 | Weekly Activity Report (WAR) – Wk 28 | Weekly | [6 empty] | 213
2027-05-21 | Fri | B03 | Contractor Performance Report (CPR) – Apr 2027 | Monthly | [6 empty] | 220
2027-05-21 | Fri | B04 | Weekly Activity Report (WAR) – Wk 29 | Weekly | [6 empty] | 220
2027-05-21 | Fri | B34 | Weekly Activity Report (WAR) – Wk 29 | Weekly | [6 empty] | 220
2027-05-28 | Fri | B04 | Weekly Activity Report (WAR) – Wk 30 | Weekly | [6 empty] | 227
2027-05-28 | Fri | B34 | Weekly Activity Report (WAR) – Wk 30 | Weekly | [6 empty] | 227
2027-06-04 | Fri | B04 | Weekly Activity Report (WAR) – Wk 31 | Weekly | [6 empty] | 234
2027-06-04 | Fri | B34 | Weekly Activity Report (WAR) – Wk 31 | Weekly | [6 empty] | 234
2027-06-10 | Thu | B01 | Monthly Progress Report (MPR) – May 2027 | Monthly | [6 empty] | 240
2027-06-10 | Thu | B02 | 90-Day Action Plan – May 2027 | Monthly | [6 empty] | 240
2027-06-10 | Thu | B16 | Technical Library Documentation Report – May 2027 | Monthly | [6 empty] | 240
2027-06-10 | Thu | B26 | Authorization and Accreditation (A&A) Packages – May 2027 | Monthly | [6 empty] | 240
2027-06-10 | Thu | B29 | Network Installation / De-installation Report – May 2027 | Monthly | [6 empty] | 240
2027-06-10 | Thu | B30 | IAVA Compliance Report – May 2027 | Monthly | [6 empty] | 240
2027-06-10 | Thu | B31 | COMSEC Management Procedures Report – May 2027 | Monthly | [6 empty] | 240
2027-06-10 | Thu | B32 | Technical Documentation & Report(s) – May 2027 | Monthly | [6 empty] | 240
2027-06-10 | Thu | B35 | Non-Disclosure Agreement Report – May 2027 | Monthly | [6 empty] | 240
2027-06-11 | Fri | B04 | Weekly Activity Report (WAR) – Wk 32 | Weekly | [6 empty] | 241
2027-06-11 | Fri | B34 | Weekly Activity Report (WAR) – Wk 32 | Weekly | [6 empty] | 241
2027-06-18 | Fri | B04 | Weekly Activity Report (WAR) – Wk 33 | Weekly | [6 empty] | 248
2027-06-18 | Fri | B34 | Weekly Activity Report (WAR) – Wk 33 | Weekly | [6 empty] | 248
2027-06-22 | Tue | B03 | Contractor Performance Report (CPR) – May 2027 | Monthly | [6 empty] | 252
2027-06-25 | Fri | B04 | Weekly Activity Report (WAR) – Wk 34 | Weekly | [6 empty] | 255
2027-06-25 | Fri | B34 | Weekly Activity Report (WAR) – Wk 34 | Weekly | [6 empty] | 255
2027-07-02 | Fri | B04 | Weekly Activity Report (WAR) – Wk 35 | Weekly | [6 empty] | 262
2027-07-02 | Fri | B34 | Weekly Activity Report (WAR) – Wk 35 | Weekly | [6 empty] | 262
2027-07-03 | Sat | B05 | B05 – Transition-out Plan (base period end) | One-time | [6 empty] | 263 |  | 120 calendar days before end of the 12-month base period.
2027-07-09 | Fri | B04 | Weekly Activity Report (WAR) – Wk 36 | Weekly | [6 empty] | 269
2027-07-09 | Fri | B34 | Weekly Activity Report (WAR) – Wk 36 | Weekly | [6 empty] | 269
2027-07-12 | Mon | B01 | Monthly Progress Report (MPR) – Jun 2027 | Monthly | [6 empty] | 272
2027-07-12 | Mon | B02 | 90-Day Action Plan – Jun 2027 | Monthly | [6 empty] | 272
2027-07-12 | Mon | B16 | Technical Library Documentation Report – Jun 2027 | Monthly | [6 empty] | 272
2027-07-12 | Mon | B26 | Authorization and Accreditation (A&A) Packages – Jun 2027 | Monthly | [6 empty] | 272
2027-07-12 | Mon | B29 | Network Installation / De-installation Report – Jun 2027 | Monthly | [6 empty] | 272
2027-07-12 | Mon | B30 | IAVA Compliance Report – Jun 2027 | Monthly | [6 empty] | 272
2027-07-12 | Mon | B31 | COMSEC Management Procedures Report – Jun 2027 | Monthly | [6 empty] | 272
2027-07-12 | Mon | B32 | Technical Documentation & Report(s) – Jun 2027 | Monthly | [6 empty] | 272
2027-07-12 | Mon | B35 | Non-Disclosure Agreement Report – Jun 2027 | Monthly | [6 empty] | 272
2027-07-16 | Fri | B04 | Weekly Activity Report (WAR) – Wk 37 | Weekly | [6 empty] | 276
2027-07-16 | Fri | B34 | Weekly Activity Report (WAR) – Wk 37 | Weekly | [6 empty] | 276
2027-07-22 | Thu | B03 | Contractor Performance Report (CPR) – Jun 2027 | Monthly | [6 empty] | 282
2027-07-23 | Fri | B04 | Weekly Activity Report (WAR) – Wk 38 | Weekly | [6 empty] | 283
2027-07-23 | Fri | B34 | Weekly Activity Report (WAR) – Wk 38 | Weekly | [6 empty] | 283
2027-07-30 | Fri | B04 | Weekly Activity Report (WAR) – Wk 39 | Weekly | [6 empty] | 290
2027-07-30 | Fri | B34 | Weekly Activity Report (WAR) – Wk 39 | Weekly | [6 empty] | 290
2027-08-06 | Fri | B04 | Weekly Activity Report (WAR) – Wk 40 | Weekly | [6 empty] | 297
2027-08-06 | Fri | B34 | Weekly Activity Report (WAR) – Wk 40 | Weekly | [6 empty] | 297
2027-08-10 | Tue | B01 | Monthly Progress Report (MPR) – Jul 2027 | Monthly | [6 empty] | 301
2027-08-10 | Tue | B16 | Technical Library Documentation Report – Jul 2027 | Monthly | [6 empty] | 301
2027-08-10 | Tue | B26 | Authorization and Accreditation (A&A) Packages – Jul 2027 | Monthly | [6 empty] | 301
2027-08-10 | Tue | B29 | Network Installation / De-installation Report – Jul 2027 | Monthly | [6 empty] | 301
2027-08-10 | Tue | B30 | IAVA Compliance Report – Jul 2027 | Monthly | [6 empty] | 301
2027-08-10 | Tue | B31 | COMSEC Management Procedures Report – Jul 2027 | Monthly | [6 empty] | 301
2027-08-10 | Tue | B32 | Technical Documentation & Report(s) – Jul 2027 | Monthly | [6 empty] | 301
2027-08-10 | Tue | B35 | Non-Disclosure Agreement Report – Jul 2027 | Monthly | [6 empty] | 301
2027-08-11 | Wed | B02 | 90-Day Action Plan – Jul 2027 | Monthly | [6 empty] | 302
2027-08-13 | Fri | B04 | Weekly Activity Report (WAR) – Wk 41 | Weekly | [6 empty] | 304
2027-08-13 | Fri | B34 | Weekly Activity Report (WAR) – Wk 41 | Weekly | [6 empty] | 304
2027-08-20 | Fri | B03 | Contractor Performance Report (CPR) – Jul 2027 | Monthly | [6 empty] | 311
2027-08-20 | Fri | B04 | Weekly Activity Report (WAR) – Wk 42 | Weekly | [6 empty] | 311
2027-08-20 | Fri | B34 | Weekly Activity Report (WAR) – Wk 42 | Weekly | [6 empty] | 311
2027-08-27 | Fri | B04 | Weekly Activity Report (WAR) – Wk 43 | Weekly | [6 empty] | 318
2027-08-27 | Fri | B34 | Weekly Activity Report (WAR) – Wk 43 | Weekly | [6 empty] | 318
2027-09-03 | Fri | B04 | Weekly Activity Report (WAR) – Wk 44 | Weekly | [6 empty] | 325
2027-09-03 | Fri | B34 | Weekly Activity Report (WAR) – Wk 44 | Weekly | [6 empty] | 325
2027-09-10 | Fri | B01 | Monthly Progress Report (MPR) – Aug 2027 | Monthly | [6 empty] | 332
2027-09-10 | Fri | B02 | 90-Day Action Plan – Aug 2027 | Monthly | [6 empty] | 332
2027-09-10 | Fri | B04 | Weekly Activity Report (WAR) – Wk 45 | Weekly | [6 empty] | 332
2027-09-10 | Fri | B16 | Technical Library Documentation Report – Aug 2027 | Monthly | [6 empty] | 332
2027-09-10 | Fri | B26 | Authorization and Accreditation (A&A) Packages – Aug 2027 | Monthly | [6 empty] | 332
2027-09-10 | Fri | B29 | Network Installation / De-installation Report – Aug 2027 | Monthly | [6 empty] | 332
2027-09-10 | Fri | B30 | IAVA Compliance Report – Aug 2027 | Monthly | [6 empty] | 332
2027-09-10 | Fri | B31 | COMSEC Management Procedures Report – Aug 2027 | Monthly | [6 empty] | 332
2027-09-10 | Fri | B32 | Technical Documentation & Report(s) – Aug 2027 | Monthly | [6 empty] | 332
2027-09-10 | Fri | B34 | Weekly Activity Report (WAR) – Wk 45 | Weekly | [6 empty] | 332
2027-09-10 | Fri | B35 | Non-Disclosure Agreement Report – Aug 2027 | Monthly | [6 empty] | 332
2027-09-17 | Fri | B04 | Weekly Activity Report (WAR) – Wk 46 | Weekly | [6 empty] | 339
2027-09-17 | Fri | B34 | Weekly Activity Report (WAR) – Wk 46 | Weekly | [6 empty] | 339
2027-09-22 | Wed | B03 | Contractor Performance Report (CPR) – Aug 2027 | Monthly | [6 empty] | 344
2027-09-24 | Fri | B04 | Weekly Activity Report (WAR) – Wk 47 | Weekly | [6 empty] | 346
2027-09-24 | Fri | B34 | Weekly Activity Report (WAR) – Wk 47 | Weekly | [6 empty] | 346
2027-10-01 | Fri | B04 | Weekly Activity Report (WAR) – Wk 48 | Weekly | [6 empty] | 353
2027-10-01 | Fri | B34 | Weekly Activity Report (WAR) – Wk 48 | Weekly | [6 empty] | 353
2027-10-08 | Fri | B04 | Weekly Activity Report (WAR) – Wk 49 | Weekly | [6 empty] | 360
2027-10-08 | Fri | B34 | Weekly Activity Report (WAR) – Wk 49 | Weekly | [6 empty] | 360
2027-10-11 | Mon | B01 | Monthly Progress Report (MPR) – Sep 2027 | Monthly | [6 empty] | 363
2027-10-11 | Mon | B16 | Technical Library Documentation Report – Sep 2027 | Monthly | [6 empty] | 363
2027-10-11 | Mon | B26 | Authorization and Accreditation (A&A) Packages – Sep 2027 | Monthly | [6 empty] | 363
2027-10-11 | Mon | B29 | Network Installation / De-installation Report – Sep 2027 | Monthly | [6 empty] | 363
2027-10-11 | Mon | B30 | IAVA Compliance Report – Sep 2027 | Monthly | [6 empty] | 363
2027-10-11 | Mon | B31 | COMSEC Management Procedures Report – Sep 2027 | Monthly | [6 empty] | 363
2027-10-11 | Mon | B32 | Technical Documentation & Report(s) – Sep 2027 | Monthly | [6 empty] | 363
2027-10-11 | Mon | B35 | Non-Disclosure Agreement Report – Sep 2027 | Monthly | [6 empty] | 363
2027-10-12 | Tue | B02 | 90-Day Action Plan – Sep 2027 | Monthly | [6 empty] | 364
2027-10-15 | Fri | B04 | Weekly Activity Report (WAR) – Wk 50 | Weekly | [6 empty] | 367
2027-10-15 | Fri | B34 | Weekly Activity Report (WAR) – Wk 50 | Weekly | [6 empty] | 367
2027-10-22 | Fri | B03 | Contractor Performance Report (CPR) – Sep 2027 | Monthly | [6 empty] | 374
2027-10-22 | Fri | B04 | Weekly Activity Report (WAR) – Wk 51 | Weekly | [6 empty] | 374
2027-10-22 | Fri | B34 | Weekly Activity Report (WAR) – Wk 51 | Weekly | [6 empty] | 374
2027-10-29 | Fri | B04 | Weekly Activity Report (WAR) – Wk 52 | Weekly | [6 empty] | 381
2027-10-29 | Fri | B34 | Weekly Activity Report (WAR) – Wk 52 | Weekly | [6 empty] | 381
2027-11-10 | Wed | B01 | Monthly Progress Report (MPR) – Oct 2027 | Monthly | [6 empty] | 393
2027-11-10 | Wed | B02 | 90-Day Action Plan – Oct 2027 | Monthly | [6 empty] | 393
2027-11-10 | Wed | B16 | Technical Library Documentation Report – Oct 2027 | Monthly | [6 empty] | 393
2027-11-10 | Wed | B26 | Authorization and Accreditation (A&A) Packages – Oct 2027 | Monthly | [6 empty] | 393
2027-11-10 | Wed | B29 | Network Installation / De-installation Report – Oct 2027 | Monthly | [6 empty] | 393
2027-11-10 | Wed | B30 | IAVA Compliance Report – Oct 2027 | Monthly | [6 empty] | 393
2027-11-10 | Wed | B31 | COMSEC Management Procedures Report – Oct 2027 | Monthly | [6 empty] | 393
2027-11-10 | Wed | B32 | Technical Documentation & Report(s) – Oct 2027 | Monthly | [6 empty] | 393
2027-11-10 | Wed | B35 | Non-Disclosure Agreement Report – Oct 2027 | Monthly | [6 empty] | 393
2027-11-22 | Mon | B03 | Contractor Performance Report (CPR) – Oct 2027 | Monthly | [6 empty] | 405
2028-01-01 | Sat | B05 | B05 – Transition-out Plan (with 6-month extension) | One-time | [6 empty] | 445 |  | 120 calendar days before end if the 6-month FAR 52.217-8 extension is exercised.