## Tracker
ITS2 (IT Service Support) – Deliverable Tracker
PWS as of 29 Sep 2023 ¦ USINDOPACOM J6 ¦ Tracking No. 712367735 ¦ Follow-on to CS2 (GS00Q17GWD2133 / HC1019-19-F-0015) ¦ Transition-in Jan 2024; Base Feb 2024 – Jan 2025; Option Years 1–4 to Jan 2029
Government POCs |  | Primary COR and Alternate COR are blank in the PWS. Acceptors below are carried over from the Thunderdome tracker – edit the lists on the Tracker tab.
At a glance |  | Overdue | Due within 7 days | Awaiting COR / J698 | Fully accepted | Returned: resubmit | PWS paragraphs with no deliverable
|  | 24 | 8 | 0 | 0 | 0 | 0
Lists (dropdown sources). Names you type into an Accepted By cell do not have to be on a list.
Month | Sub Task Number | Paragraph / Section | Frequency | Category | Primary POC | Secondary POC | Format of Deliverable | Deliverable 1 | Deliverable 2 | Deliverable 3 | Deliverable 4 | Deliverable 5 | Status Flow 1 | Status Flow 2 | Status Flow 3 | COR Accepted By | COR Date Accepted | J698 Accepted By | J698 Date Accepted | Category | Status Flow 1 | Status Flow 2 | Status Flow 3 | Frequency | Month | COR Acceptors | J698 Acceptors
Oct | 6.1.1 | Enterprise Architecture Support | Mixed (see due row) | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.1.1-01 Architecture Recommendations | 6.1.1-02 Architecture Implementation Plans | 6.1.1-03 MSR |  |  | Not Received | Not Reviewed | [5 empty] | Cybersecurity | Received | Reviewed | Accepted | Weekly | Jan | Christine Y. Shigeta | J698
[7 empty] | Due / Frequency (per document) | Due: NLT 5 business days from assignment Freq: As Required | Due: NLT 15 business days from assignment Freq: As Required | Due: NLT 5th business day of the succeeding month Freq: Monthly | [9 empty] | Engineering | Not Received | Not Reviewed | Returned | Monthly | Feb | Brian Abrigo
Oct | 6.1.2 | Project Management Support | Not required (suspended) | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.1.2-01 Project POAM | 6.1.2-02 Project Risk Plan | 6.1.2-03 Decision Brief {POAM Deviation} | 6.1.2-04 MSR | [8 empty] | Operations |  | Demonstrated | Returned, but Fixed | Quarterly | Mar
[7 empty] | Due / Frequency (per document) | Due: Initial: NLT 3 weeks of project assignment Updates: NLT the last duty day of the week Freq: As Required Flag: Subtask not required effective 1 Jun 2022, until further notice (PWS Section 11). | Due: Initial: NLT 3 weeks of project assignment Maintenance: NLT 3 weeks of identified change Freq: As Required Flag: Subtask not required effective 1 Jun 2022, until further notice (PWS Section 11). | Due: NLT 3 weeks of identified requirement Freq: As Required Flag: Subtask not required effective 1 Jun 2022, until further notice (PWS Section 11). | Due: NLT 5th business day of the succeeding month Freq: Monthly Flag: Subtask not required effective 1 Jun 2022, until further notice (PWS Section 11). | [8 empty] | Program Mgmt |  | Not Demonstrated |  | Annual | Apr
Oct | 6.1.3 | Business Process Analyst Support | Mixed (see due row) | Program Mgmt | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.1.3-01 Story Board Recommendations and Plans | 6.1.3-02 Story Board Implementations | 6.1.3-03 MSR |  |  | Not Received | Not Reviewed | [9 empty] | Daily (standing) | May
[7 empty] | Due / Frequency (per document) | Due: Initial: NLT 3 weeks of assignment Maintenance: NLT 3 weeks of identified change Freq: As Required | Due: Initial: NLT 3 weeks of assignment Maintenance: NLT 3 weeks of identified change Freq: As Required | Due: NLT 5th business day of the succeeding month Freq: Monthly | [13 empty] | One-Time | Jun
Oct | 6.2.1 | Audio Visual Systems Engineering Support | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.2.1-01 AV Recommendations | 6.2.1-02 AV Documentation | 6.2.1-03 AV Audits | 6.2.1-04 AV POAM | 6.2.1-05 MSR | Not Received | Not Reviewed | [9 empty] | One-Time + Updates | Jul
[7 empty] | Due / Frequency (per document) | Due: NLT 5th business day of the 1st month of the quarter Freq: Quarterly | Due: NLT 5 business days after the activity completion Freq: As Required | Due: NLT 5th business day of the 1st month of the quarter Freq: Quarterly | Due: NLT 3 weeks of project assignment Freq: As Required | Due: NLT 5th business day of the succeeding month Freq: Monthly | [11 empty] | As Needed | Aug
Oct | 6.2.2 | Video Teleconferencing (VTC) Scheduling Support | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.2.2-01 Technology Evaluation & Recommendations | 6.2.2-02 Standard Operating Procedures (SOP) & Training | 6.2.2-03 VTC Scheduling & Operations | 6.2.2-04 MSR |  | Not Received | Not Reviewed | [9 empty] | Not required (suspended) | Sep
[7 empty] | Due / Frequency (per document) | Due: NLT 15 days from assignment Freq: As Required | Due: NLT 15 days from assignment Freq: As Required | Due: Short Notice / Emergent: NLT 1 hour of notification Standard: NLT 1 day of notification Freq: As Required | Due: NLT 5th business day of the succeeding month Freq: Monthly | [12 empty] | Mixed (see due row) | Oct
Oct | 6.2.3 | Video Teleconferencing (VTC) Network Engineering Support | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.2.3-01 VTC Recommendations | 6.2.3-02 MSR |  |  |  | Not Received | Not Reviewed | [9 empty] | None named | Nov
[7 empty] | Due / Frequency (per document) | Due: NLT 5th business day of the 1st month of the quarter Freq: Quarterly | Due: NLT 5th business day of the succeeding month Freq: Monthly | [15 empty] | Dec
Oct | 6.2.4 | Senior Cisco Networking Engineering Support (1 of 2) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.2.4-01 Network Engineering Design & Implementation | 6.2.4-02 Network Engineering Troubleshooting and Operations | 6.2.4-03 Network ASIs | 6.2.4-04 STIG Implementation & Reporting | 6.2.4-05 Security Scans | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 15 business days after assignment of task Freq: As Required | Due: On-going Freq: Daily | Due: NLT 5 business days after assignment Freq: As Required | Due: Monthly: NLT 5th business day of the succeeding month Quarterly: NLT 5th business day of the 1st month of the quarter Freq: Monthly & Quarterly Flag: Also reported quarterly (5th business day of the quarter's first month). | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Daily
Oct | 6.2.4 | Senior Cisco Networking Engineering Support (2 of 2) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.2.4-06 Network Cabling | 6.2.4-07 Architecture & Rack Diagrams | 6.2.4-08 Standard Operating Procedures (SOP) | 6.2.4-09 MSR |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: Maintenance complete NLT 5 business days assigned Freq: As Required | Due: NLT 15 business days after assignment of task Freq: As Required | Due: NLT 15 business days after assignment of task Freq: As Required | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.2.5 | Cisco Network Engineering Support (1 of 2) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.2.5-01 Network Engineering Design & Implementation | 6.2.5-02 Network Engineering Troubleshooting and Operations | 6.2.5-03 Network ASIs | 6.2.5-04 STIG Implementation & Reporting | 6.2.5-05 Security Scans | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 15 business days after assignment of task Freq: As Required | Due: On-going Freq: Daily | Due: NLT 5 business days after assignment Freq: As Required | Due: Monthly: NLT 5th business day of the succeeding month Quarterly: NLT 5th business day of the 1st month of the quarter Freq: Monthly & Quarterly Flag: Also reported quarterly (5th business day of the quarter's first month). | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Daily
Oct | 6.2.5 | Cisco Network Engineering Support (2 of 2) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.2.5-06 Network Cabling | 6.2.5-07 Architecture & Rack Diagrams | 6.2.5-08 Standard Operating Procedures (SOP) | 6.2.5-09 MSR |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: Maintenance complete NLT 5 business days assigned Freq: As Required | Due: NLT 15 business days after assignment of task Freq: As Required | Due: NLT 15 business days after assignment of task Freq: As Required | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.3.1 | Linux System Administration Support (1 of 2) | Daily (standing) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.1-01 System Administration {Operating Systems & Applications} | 6.3.1-02 Patching | 6.3.1-03 STIG Compliance | 6.3.1-04 PKI Compliance | 6.3.1-05 ESS Compliance | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: On-going Freq: Daily | Due: a) NLT the patch IAVA compliance date b) All deficiencies documented with a POAM within 1 business day Freq: Daily | Due: a) NLT 4 weeks of STIGS release b) NLT 5 business days of CAT I STIG release c) (STIG Status Report) NLT 5 business days after the start of the new quarter Freq: Daily | Due: On-going Freq: Daily | Due: On-going Freq: Daily
Oct | 6.3.1 | Linux System Administration Support (2 of 2) | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.1-06 Security Scans | 6.3.1-07 Backup / Restore | 6.3.1-08 Standard Operating Procedures (SOP) | 6.3.1-09 MSR |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution: NLT 5 business days after issue identification Freq: Daily | Due: a) NLT COB every workday for backups b) NLT last workday of month for restore validation Freq: Daily for backups Monthly for restores Flag: Daily backups; monthly restore test (last workday of month). | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution: NLT 5 business days after issue identification Freq: Quarterly Flag: Due text repeats the Security Scans wording; quarterly review assumed due the 5th business day of the quarter's first month. | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.3.2 | Virtual Desktop Infrastructure (VDI) System Administration Support (1 of 2) | Daily (standing) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.2-01 System Administration {Operating Systems & Applications} | 6.3.2-02 STIG Compliance | 6.3.2-03 PKI Compliance | 6.3.2-04 HBSS Compliance | 6.3.2-05 Security Scans | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: On-going Freq: Daily | Due: a) NLT 4 weeks of STIGS release b) NLT 5 business days of CAT I STIG release c) (STIG Status Report) NLT 5 business days after the start of the new quarter Freq: Daily | Due: On-going Freq: Daily | Due: On-going Freq: Daily | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Daily
Oct | 6.3.2 | Virtual Desktop Infrastructure (VDI) System Administration Support (2 of 2) | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.2-06 Backup / Restore | 6.3.2-07 Standard Operating Procedures (SOP) | 6.3.2-08 MSR |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: a) NLT COB every workday for backups b) NLT last workday of month for restore validation Freq: Daily for backups Monthly for restores Flag: Daily backups; monthly restore test (last workday of month). | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Quarterly Flag: Due text repeats the Security Scans wording; quarterly review assumed due the 5th business day of the quarter's first month. | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.3.3 | Virtual Infrastructure (VI) System Administration Support (1 of 2) | Daily (standing) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.3-01 System Administration {Operating Systems & Applications} | 6.3.3-02 Patching | 6.3.3-03 STIG Compliance | 6.3.3-04 PKI Compliance | 6.3.3-05 ESS Compliance | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: On-going Freq: Daily | Due: On-going Freq: Daily | Due: a) NLT 4 weeks of STIGS release b) NLT 5 business days of CAT I STIG release c) (STIG Status Report) NLT 5 business days after the start of the new quarter Freq: Daily | Due: On-going Freq: Daily | Due: On-going Freq: Daily
Oct | 6.3.3 | Virtual Infrastructure (VI) System Administration Support (2 of 2) | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.3-06 Security Scans | 6.3.3-07 Backup / Restore | 6.3.3-08 Continuity of Operations (COOP) | 6.3.3-09 Standard Operating Procedures (SOP) | 6.3.3-10 MSR | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Daily | Due: a) NLT COB every workday for backups b) NLT last workday of month for restore validation Freq: Daily for backups Monthly for restores Flag: Daily backups; monthly restore test (last workday of month). | Due: a) On-going b) bi-annual test/exercise based on USINDOPACOM operational schedule Freq: Daily & bi-annual Flag: Includes a bi-annual COOP test/exercise (no date anchor in the PWS). | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Quarterly Flag: Due text repeats the Security Scans wording; quarterly review assumed due the 5th business day of the quarter's first month. | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.3.4 | Senior Windows System Administration Support (1 of 3) | Daily (standing) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.4-01 System Administration {Operating Systems & Applications} | 6.3.4-02 Patching | 6.3.4-03 STIG Compliance | 6.3.4-04 PKI Compliance | 6.3.4-05 ESS Compliance | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: On-going Freq: Daily | Due: On-going Freq: Daily | Due: a) NLT 4 weeks of STIGS release b) NLT 5 business days of CAT I STIG release c) (STIG Status Report) NLT 5 business days after the start of the new quarter Freq: Daily | Due: On-going Freq: Daily | Due: On-going Freq: Daily
Oct | 6.3.4 | Senior Windows System Administration Support (2 of 3) | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.4-06 Security Scans | 6.3.4-07 Backup / Restore | 6.3.4-08 Active Directory Management | 6.3.4-09 Continuity of Operations (COOP) | 6.3.4-10 Standard Operating Procedures (SOP) | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Daily | Due: a) NLT COB every workday for backups b) NLT last workday of month for restore validation Freq: Daily for backups Monthly for restores Flag: Daily backups; monthly restore test (last workday of month). | Due: a) On-going b) Reporting: NLT the last duty day of the week Freq: Daily & Weekly | Due: a) On-going b) bi-annual test/exercise based on USINDOPACOM operational schedule Freq: Daily & bi-annual Flag: Includes a bi-annual COOP test/exercise (no date anchor in the PWS). | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Quarterly Flag: Due text repeats the Security Scans wording; quarterly review assumed due the 5th business day of the quarter's first month.
Oct | 6.3.4 | Senior Windows System Administration Support (3 of 3) | Monthly | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.4-11 MSR |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.3.5 | Windows System Administration Support (1 of 3) | Daily (standing) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.5-01 System Administration {Operating Systems & Applications} | 6.3.5-02 Patching | 6.3.5-03 STIG Compliance | 6.3.5-04 PKI Compliance | 6.3.5-05 HBSS Compliance | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: On-going Freq: Daily | Due: On-going Freq: Daily | Due: a) NLT 4 weeks of STIGS release b) NLT 5 business days of CAT I STIG release c) (STIG Status Report) NLT 5 business days after the start of the new quarter Freq: Daily | Due: On-going Freq: Daily | Due: On-going Freq: Daily
Oct | 6.3.5 | Windows System Administration Support (2 of 3) | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.5-06 Security Scans | 6.3.5-07 Backup / Restore | 6.3.5-08 Active Directory Management | 6.3.5-09 Continuity of Operations (COOP) | 6.3.5-10 Standard Operating Procedures (SOP) | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Daily | Due: a) NLT COB every workday for backups b) NLT last workday of month for restore validation Freq: Daily for backups Monthly for restores Flag: Daily backups; monthly restore test (last workday of month). | Due: a) On-going b) Reporting: NLT the last duty day of the week Freq: Daily & Weekly | Due: a) On-going b) bi-annual test/exercise based on USINDOPACOM operational schedule Freq: Daily & bi-annual Flag: Includes a bi-annual COOP test/exercise (no date anchor in the PWS). | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Quarterly Flag: Due text repeats the Security Scans wording; quarterly review assumed due the 5th business day of the quarter's first month.
Oct | 6.3.5 | Windows System Administration Support (3 of 3) | Monthly | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.5-11 MSR |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.3.6 | Global Command & Control System (GCCS) System Administration Support (1 of 3) | Daily (standing) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.6-01 System Administration {Operating Systems & Applications} | 6.3.6-02 Patching | 6.3.6-03 STIG Compliance | 6.3.6-04 PKI Compliance | 6.3.6-05 ESS Compliance | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: On-going Freq: Daily | Due: On-going Freq: Daily | Due: a) NLT 4 weeks of STIGS release b) NLT 5 business days of CAT I STIG release c) (STIG Status Report) NLT 5 business days after the start of the new quarter Freq: Daily | Due: On-going Freq: Daily | Due: On-going Freq: Daily
Oct | 6.3.6 | Global Command & Control System (GCCS) System Administration Support (2 of 3) | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.6-06 Security Scans | 6.3.6-07 Backup / Restore | 6.3.6-08 Continuity of Operations (COOP) | 6.3.6-09 Standard Operating Procedures (SOP) | 6.3.6-10 Deployment Files & Virtual Images | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Daily | Due: a) NLT COB every workday for backups b) NLT last workday of month for restore validation Freq: Daily for backups Monthly for restores Flag: Daily backups; monthly restore test (last workday of month). | Due: a) On-going b) bi-annual test/exercise based on USINDOPACOM operational schedule Freq: Daily & bi-annual Flag: Includes a bi-annual COOP test/exercise (no date anchor in the PWS). | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Quarterly Flag: Due text repeats the Security Scans wording; quarterly review assumed due the 5th business day of the quarter's first month. | Due: NLT 1 business day after GCCS-J update received Freq: As Required
Oct | 6.3.6 | Global Command & Control System (GCCS) System Administration Support (3 of 3) | Monthly | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.6-11 MSR |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.3.7 | SCCM/MECH Administration Support (1 of 4) | Daily (standing) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.7-01 System Administration {Operating Systems & Applications} | 6.3.7-02 Patching | 6.3.7-03 STIG Compliance | 6.3.7-04 PKI Compliance | 6.3.7-05 ESS Compliance | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: On-going Freq: Daily | Due: On-going Freq: Daily | Due: a) NLT 4 weeks of STIGS release b) NLT 5 business days of CAT I STIG release c) (STIG Status Report) NLT 5 business days after the start of the new quarter Freq: Daily | Due: On-going Freq: Daily | Due: On-going Freq: Daily
Oct | 6.3.7 | SCCM/MECH Administration Support (2 of 4) | Daily (standing) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.7-06 Monitor the performance of SCCM/MECM and identify and troubleshoot issues as they arise. | 6.3.7-07 Configures synchronization with software and patch update servers and Comply to Connect (C2C). | 6.3.7-08 Create/Edit/Delete/Deploy Collections (both user and device) | 6.3.7-09 Create/Edit/Delete/Deploy Reports | 6.3.7-10 Create/Edit/Delete/Deploy Task Sequences | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: On-going Freq: Daily | Due: On-going Freq: Daily | Due: On-going Freq: Daily | Due: On-going Freq: Daily | Due: On-going Freq: Daily
Oct | 6.3.7 | SCCM/MECH Administration Support (3 of 4) | Daily (standing) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.7-11 Create/Edit/Delete/Deploy Compliance Rules | 6.3.7-12 Create/Edit/Delete/Deploy Software Applications | 6.3.7-13 Create/Edit/Delete/Deploy Software Updates | 6.3.7-14 Create/Edit/Delete/Deploy Desktop SCCM Policies | 6.3.7-15 Create/Edit/Delete/Deploy Anti-malware Policies | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: On-going Freq: Daily | Due: On-going Freq: Daily | Due: On-going Freq: Daily | Due: On-going Freq: Daily | Due: On-going Freq: Daily
Oct | 6.3.7 | SCCM/MECH Administration Support (4 of 4) | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.3.7-16 Create/Edit/Delete/Deploy Operating System Images | 6.3.7-17 Standard Operating Procedures (SOP) | 6.3.7-18 MSR |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: On-going Freq: Daily | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Quarterly Flag: Due text repeats the Security Scans wording; quarterly review assumed due the 5th business day of the quarter's first month. | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.4.1 | Senior Web Application Development Support (1 of 2) | As Needed | Engineering | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.4.1-01 Application Coding | 6.4.1-02 Incident Handling | 6.4.1-03 Project Plan | 6.4.1-04 Feasibility Study Report | 6.4.1-05 Testing and Evaluation Report | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW Project Plan Freq: As Required | Due: IAW Service Desk CONOPS {NLT 1 business day of the incident} Freq: As Required | Due: NLT 5 business days after project assignment Freq: As Required | Due: NLT 5 business days of assignment Freq: As Required | Due: NLT 5 business days after testing concludes Freq: As Required
Oct | 6.4.1 | Senior Web Application Development Support (2 of 2) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.4.1-06 Product Acceptance Documentation | 6.4.1-07 Application Documentation | 6.4.1-08 Application Training Guide | 6.4.1-09 MSR |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 1 business day after customer acceptance Freq: As Required | Due: NLT 30 business days after project completion Freq: As Required | Due: IAW Project Plan Freq: As Required | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.4.2 | Web Application Development Support (1 of 2) | As Needed | Engineering | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.4.2-01 Application Coding | 6.4.2-02 Incident Handling | 6.4.2-03 Feasibility Study Report | 6.4.2-04 Testing and Evaluation Report | 6.4.2-05 Application documentation | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW Project Plan Freq: As Required | Due: IAW Service Desk CONOPS {NLT 1 business day of the incident} Freq: As Required | Due: NLT 5 business days of assignment Freq: As Required | Due: NLT 5 business days after testing concludes Freq: As Required | Due: NLT 30 business days after project completion Freq: As Required
Oct | 6.4.2 | Web Application Development Support (2 of 2) | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.4.2-06 Application Training Guide | 6.4.2-07 MSR |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW Project Plan Freq: As Required | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.4.3 | Senior Web Portal Development Support (1 of 2) | As Needed | Engineering | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.4.3-01 O&M Action Documentation | 6.4.3-02 Script & Portal Coding | 6.4.3-03 Level of Effort Estimates | 6.4.3-04 Project Plan | 6.4.3-05 Portal Training & Training Aids | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW Service Desk CONOPS Freq: As Required | Due: IAW Service Desk CONOPS and Project Plan Freq: As Required | Due: NLT 5 business days after O&M request Freq: As Required | Due: NLT 5 business days after receipt of project requirements Freq: As Required | Due: IAW Project Plan Freq: As Required
Oct | 6.4.3 | Senior Web Portal Development Support (2 of 2) | Monthly | Engineering | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.4.3-06 MSR |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.4.4 | Web Portal Development Support | Mixed (see due row) | Engineering | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.4.4-01 O&M Action Documentation | 6.4.4-02 Script & Portal Coding | 6.4.4-03 Level of Effort Estimates | 6.4.4-04 Portal Training & Training Aids | 6.4.4-05 MSR | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW Service Desk CONOPS Freq: As Required | Due: IAW Service Desk CONOPS and Project Plan Freq: As Required | Due: NLT 5 business days after O&M request Freq: As Required | Due: IAW Project Plan Freq: As Required | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.5.1 | Assessment and Authorization Support | Mixed (see due row) | Cybersecurity | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.5.1-01 System Expiration Notification | 6.5.1-02 Security Authorization Package Generation | 6.5.1-03 Portfolio Management System Updates | 6.5.1-04 Performance Objective Reporting | 6.5.1-05 MSR | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: 30, 60, 90, and 120 days prior to authorization expiration of system Freq: As Required | Due: NLT one week prior to expiration of system Freq: As Required | Due: NLT 5 business days of the SAP acceptance Freq: As Required | Due: NLT one business day of Performance Objective completed Freq: As Required | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.5.2 | Cybersecurity Compliance Support (1 of 2) | Mixed (see due row) | Cybersecurity | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.5.2-01 Compliance Tracking & Reporting | 6.5.2-02 Risk Analysis | 6.5.2-03 Vulnerability Tracking & Reporting | 6.5.2-04 Vulnerability Analysis | 6.5.2-05 Cybersecurity Recommendations | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT the last day of the business week Freq: Weekly | Due: NLT the last day of the business week Freq: Weekly | Due: NLT 5 business days of task assignment Freq: As Required | Due: NLT 5 business days of task assignment Freq: As Required | Due: NLT 5 business days of task assignment Freq: As Required
Oct | 6.5.2 | Cybersecurity Compliance Support (2 of 2) | Mixed (see due row) | Cybersecurity | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.5.2-06 System Technical & Procedural Audits | 6.5.2-07 Cyber Scorecard & Defense CyberScope Web Tool | 6.5.2-08 MSR |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 5 business days of task assignment Freq: Annually | Due: NLT 25th business day of the month Freq: Monthly Flag: PWS says "25th business day of the month", but a month has at most 23 business days; the 25th calendar day is assumed. | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.5.3 | Cybersecurity Governance Support | Mixed (see due row) | Cybersecurity | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.5.3-01 Update Service Logs with Performed LRA Duties | 6.5.3-02 Information System Security Manager Duties | 6.5.3-03 Policy development review and updates | 6.5.3-04 Risk Management Framework (RMF) Common Controls Management | 6.5.3-05 MSR | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 30 mins of request submission Freq: As Required | Due: NLT 5 business days of assignment Freq: As Required | Due: NLT 15 business day of policy review date. For new policy NLT 30 business days of assignment Freq: As Required | Due: IAW Common Controls Management Lifecycle Plan Freq: As Required | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.5.4 | Network Defense Administrator Support (1 of 2) | Mixed (see due row) | Cybersecurity | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.5.4-01 Recommendations & Suggestions | 6.5.4-02 Detection Signatures & ACLs | 6.5.4-03 Incident Response | 6.5.4-04 Configuration Management Summary of Changes | 6.5.4-05 Cyber Threat Summaries | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 5 business days of analyzing new requirements Freq: As Required | Due: NLT 1 day after assignment Freq: As Required | Due: Immediately upon discovery of anomalous traffic Freq: As Required | Due: NLT the 3rd business day of the following week Freq: Weekly | Due: NLT the 3rd business day of the following week Freq: Weekly
Oct | 6.5.4 | Network Defense Administrator Support (2 of 2) | Mixed (see due row) | Cybersecurity | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.5.4-06 STIG Compliance | 6.5.4-07 Security Scans | 6.5.4-08 PKI Compliance | 6.5.4-09 MSR |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: a) NLT 4 weeks of STIGS release b) NLT 5 business days of CAT I STIG release c) (STIG Status Report) NLT 5 business days after the start of the new quarter Freq: Daily | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Daily | Due: On-going Freq: Daily | Due: NLT 5th business day of the succeeding month Freq: Monthly Flag: PWS reference "6.5.4.ll" looks like a typo.
Oct | 6.5.5 | Endpoint Security Solutions (ESS) Support (1 of 2) | Mixed (see due row) | Cybersecurity | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.5.5-01 Recommendations & Suggestions | 6.5.5-02 Host Based Firewall Rule Sets & HIPS | 6.5.5-03 Incident Response | 6.5.5-04 ESS O&M | 6.5.5-05 Configuration management summary of changes | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 5 business days of analyzing new requirements Freq: As Required | Due: NLT 5 business days of assignment Freq: As Required | Due: Immediately upon discovery of anomalous traffic Freq: As Required | Due: NLT the close of work day business Freq: Daily | Due: NLT the 3rd business day of the following week Freq: Weekly
Oct | 6.5.5 | Endpoint Security Solutions (ESS) Support (2 of 2) | Mixed (see due row) | Cybersecurity | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.5.5-06 ESS Baseline Report | 6.5.5-07 STIG Compliance | 6.5.5-08 Security Scans | 6.5.5-09 PKI Compliance | 6.5.5-10 MSR | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT the 3rd business day of the following week Freq: Weekly | Due: a) NLT 4 weeks of STIGS release b) NLT 5 business days of CAT I STIG release c) (STIG Status Report) NLT 5 business days after the start of the new quarter Freq: Daily | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Daily | Due: On-going Freq: Daily | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.5.6 | Electronic Key Management Support | Mixed (see due row) | Cybersecurity | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.5.6-01 USINDOPACOM COMSEC Program | 6.5.6-02 In-Country Distribution Plans | 6.5.6-03 Standard Operating Procedures (SOPs) | 6.5.6-04 MSR |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT the close of work day business Freq: Daily | Due: NLT 15 business days of assignment Freq: As Required | Due: NLT 15 business days of assignment Freq: As Required | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.5.7 | Security Information Event Manager (SIEM) Administrator Support (1 of 3) | Daily (standing) | Cybersecurity | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.5.7-01 System Administration {Operating Systems & Applications} | 6.5.7-02 Patching | 6.5.7-03 STIG Compliance | 6.5.7-04 PKI Compliance | 6.5.7-05 ESS Compliance | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: On-going Freq: Daily | Due: On-going Freq: Daily | Due: a) NLT 4 weeks of STIGS release b) NLT 5 business days of CAT I STIG release c) (STIG Status Report) NLT 5 business days after the start of the new quarter Freq: Daily | Due: On-going Freq: Daily | Due: On-going Freq: Daily
Oct | 6.5.7 | Security Information Event Manager (SIEM) Administrator Support (2 of 3) | Mixed (see due row) | Cybersecurity | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.5.7-06 Security Scans | 6.5.7-07 Backup/Restore | 6.5.7-08 ServiceNow Tickets | 6.5.7-09 Continuity of Operations (COOP) | 6.5.7-10 Standard Operating Procedures (SOP) | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Daily | Due: a) NLT COB every workday for backups b) NLT last workday of month for restore validation Freq: Daily for backups Monthly for restores Flag: Daily backups; monthly restore test (last workday of month). | Due: On-going Freq: Daily | Due: a) On-going b) bi-annual test/exercise based on USINDOPACOM operational schedule Freq: Daily & bi-annual Flag: Includes a bi-annual COOP test/exercise (no date anchor in the PWS). | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Quarterly Flag: Due text repeats the Security Scans wording; quarterly review assumed due the 5th business day of the quarter's first month.
Oct | 6.5.7 | Security Information Event Manager (SIEM) Administrator Support (3 of 3) | Monthly | Cybersecurity | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.5.7-11 MSR |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.5.8 | Compliance Administrator Support (1 of 3) | Daily (standing) | Cybersecurity | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.5.8-01 System Administration {Operating Systems & Applications} | 6.5.8-02 Patching | 6.5.8-03 STIG Compliance | 6.5.8-04 PKI Compliance | 6.5.8-05 ESS Compliance | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: On-going Freq: Daily | Due: On-going Freq: Daily | Due: a) NLT 4 weeks of STIGS release b) NLT 5 business days of CAT I STIG release c) (STIG Status Report) NLT 5 business days after the start of the new quarter Freq: Daily | Due: On-going Freq: Daily | Due: On-going Freq: Daily
Oct | 6.5.8 | Compliance Administrator Support (2 of 3) | Mixed (see due row) | Cybersecurity | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.5.8-06 Security Scans | 6.5.8-07 Backup/Restore | 6.5.8-08 ServiceNow Tickets | 6.5.8-09 Continuity of Operations (COOP) | 6.5.8-10 Standard Operating Procedures (SOP) | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 busi- ness days after issue iden- tification Freq: Daily (inferred: blank in PWS) Flag: Frequency is blank in the PWS; Daily inferred from the other subtasks. | Due: a) NLT COB every workday for backups b) NLT last workday of month for restore validation Freq: Daily for backups Monthly for restores Flag: Daily backups; monthly restore test (last workday of month). | Due: On-going Freq: Daily | Due: a) On-going b) bi-annual test/exercise based on USINDO- PACOM operational schedule Freq: Daily & bi-annual Flag: Includes a bi-annual COOP test/exercise (no date anchor in the PWS). | Due: a) Documentation: NLT 1 business days after issue identification b) Resolution NLT 5 business days after issue identification Freq: Quarterly Flag: Due text repeats the Security Scans wording; quarterly review assumed due the 5th business day of the quarter's first month.
Oct | 6.5.8 | Compliance Administrator Support (3 of 3) | Monthly | Cybersecurity | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.5.8-11 MSR |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.6.1 | Assistant Contract Technical Representative (ACTR) Support | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.6.1-01 IT Request Market Research | 6.6.1-02 Move Add Change | 6.6.1-03 Data Collection & Reporting | 6.6.1-04 MSR |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 48 business hours of submission Freq: As Required | Due: NLT 6 business hours of initial submission & NLT 24 business hours of change in project status Freq: As Required | Due: NLT 4 business hours of request for information Freq: As Required | Due: NLT 5th business day of the succeeding month Freq: Monthly
Oct | 6.6.2 | Communications Focal Point (CFP) Support | Mixed (see due row) | Operations | Christine Y. Shigeta | Brian Abrigo | Distribute to TA | 6.6.2-01 Trouble Ticket | 6.6.2-02 Trend Analysis | 6.6.2-03 MSR |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 4 business hours of submission Freq: As Required | Due: NLT 1 business day of receiving request Freq: As Required | Due: NLT 5th business day of the succeeding month Freq: Monthly
Task rows record the two Government acceptances once per row. Recurring deliverables record them per period on the Weekly, Monthly, Quarterly and Daily Duties tabs. "TA" in the PWS distribution column = Technical Authority. Fully accepted = both dates filled in.

## Weekly
Weekly Deliverables – last duty day / 3rd business day of the following week
PWS as of 29 Sep 2023 ¦ USINDOPACOM J6 ¦ Tracking No. 712367735 ¦ Follow-on to CS2 (GS00Q17GWD2133 / HC1019-19-F-0015) ¦ Transition-in Jan 2024; Base Feb 2024 – Jan 2025; Option Years 1–4 to Jan 2029
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Fully accepted | Overdue | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26
6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support | 6.3.4.p | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 2 | 2026-10-02 | 2026-10-09 | 2026-10-16 | 2026-10-23 | 2026-10-30 | 2026-11-06 | 2026-11-13 | 2026-11-20 | 2026-11-27 | 2026-12-04 | 2026-12-11 | 2026-12-18 | 2026-12-25 | 2027-01-01 | 2027-01-08 | 2027-01-15 | 2027-01-22 | 2027-01-29 | 2027-02-05 | 2027-02-12 | 2027-02-19 | 2027-02-26 | 2027-03-05 | 2027-03-12 | 2027-03-19 | 2027-03-26
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support | 6.3.5.p | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 2 | 2026-10-02 | 2026-10-09 | 2026-10-16 | 2026-10-23 | 2026-10-30 | 2026-11-06 | 2026-11-13 | 2026-11-20 | 2026-11-27 | 2026-12-04 | 2026-12-11 | 2026-12-18 | 2026-12-25 | 2027-01-01 | 2027-01-08 | 2027-01-15 | 2027-01-22 | 2027-01-29 | 2027-02-05 | 2027-02-12 | 2027-02-19 | 2027-02-26 | 2027-03-05 | 2027-03-12 | 2027-03-19 | 2027-03-26
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support | 6.5.2.a | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 2 | 2026-10-02 | 2026-10-09 | 2026-10-16 | 2026-10-23 | 2026-10-30 | 2026-11-06 | 2026-11-13 | 2026-11-20 | 2026-11-27 | 2026-12-04 | 2026-12-11 | 2026-12-18 | 2026-12-25 | 2027-01-01 | 2027-01-08 | 2027-01-15 | 2027-01-22 | 2027-01-29 | 2027-02-05 | 2027-02-12 | 2027-02-19 | 2027-02-26 | 2027-03-05 | 2027-03-12 | 2027-03-19 | 2027-03-26
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support | 6.5.2.b | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 2 | 2026-10-02 | 2026-10-09 | 2026-10-16 | 2026-10-23 | 2026-10-30 | 2026-11-06 | 2026-11-13 | 2026-11-20 | 2026-11-27 | 2026-12-04 | 2026-12-11 | 2026-12-18 | 2026-12-25 | 2027-01-01 | 2027-01-08 | 2027-01-15 | 2027-01-22 | 2027-01-29 | 2027-02-05 | 2027-02-12 | 2027-02-19 | 2027-02-26 | 2027-03-05 | 2027-03-12 | 2027-03-19 | 2027-03-26
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support | 6.5.4.d | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2026-10-14 | 2026-10-21 | 2026-10-28 | 2026-11-04 | 2026-11-11 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-09 | 2026-12-16 | 2026-12-23 | 2026-12-30 | 2027-01-06 | 2027-01-13 | 2027-01-20 | 2027-01-27 | 2027-02-03 | 2027-02-10 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-10 | 2027-03-17 | 2027-03-24 | 2027-03-31
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support | 6.5.4.e | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2026-10-14 | 2026-10-21 | 2026-10-28 | 2026-11-04 | 2026-11-11 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-09 | 2026-12-16 | 2026-12-23 | 2026-12-30 | 2027-01-06 | 2027-01-13 | 2027-01-20 | 2027-01-27 | 2027-02-03 | 2027-02-10 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-10 | 2027-03-17 | 2027-03-24 | 2027-03-31
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support | 6.5.5.d | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2026-10-14 | 2026-10-21 | 2026-10-28 | 2026-11-04 | 2026-11-11 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-09 | 2026-12-16 | 2026-12-23 | 2026-12-30 | 2027-01-06 | 2027-01-13 | 2027-01-20 | 2027-01-27 | 2027-02-03 | 2027-02-10 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-10 | 2027-03-17 | 2027-03-24 | 2027-03-31
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support | 6.5.5.e | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2026-10-14 | 2026-10-21 | 2026-10-28 | 2026-11-04 | 2026-11-11 | 2026-11-18 | 2026-11-25 | 2026-12-02 | 2026-12-09 | 2026-12-16 | 2026-12-23 | 2026-12-30 | 2027-01-06 | 2027-01-13 | 2027-01-20 | 2027-01-27 | 2027-02-03 | 2027-02-10 | 2027-02-17 | 2027-02-24 | 2027-03-03 | 2027-03-10 | 2027-03-17 | 2027-03-24 | 2027-03-31
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
Set Status, then record who accepted it and when. Weekly reports are due the last duty day of the week (Fri) or the 3rd business day of the following week (Wed), per Section 11.
Formulas:
Overdue = SUMPRODUCT(([Wk 1]:[Wk 26]<TODAY())*((([Wk 1, row below]:[Wk 26, row below]="")+([Wk 1, row below]:[Wk 26, row below]="In Progress"))>0)*(((I8:AH8="")+(I10:AH10=""))>0))

## Monthly
Monthly Deliverables – MSRs and monthly reports (5th business day of the succeeding month)
PWS as of 29 Sep 2023 ¦ USINDOPACOM J6 ¦ Tracking No. 712367735 ¦ Follow-on to CS2 (GS00Q17GWD2133 / HC1019-19-F-0015) ¦ Transition-in Jan 2024; Base Feb 2024 – Jan 2025; Option Years 1–4 to Jan 2029
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Fully accepted | Overdue | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01
6.1.1-03 | MSR – 6.1.1 Enterprise Architecture Support | 6.1.1.c | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.1.3-03 | MSR – 6.1.3 Business Process Analyst Support | 6.1.3.f | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.2.1-05 | MSR – 6.2.1 Audio Visual Systems Engineering Support | 6.2.1.o | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.2.2-04 | MSR – 6.2.2 Video Teleconferencing (VTC) Scheduling Support | 6.2.2.e | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.2.3-02 | MSR – 6.2.3 Video Teleconferencing (VTC) Network Engineering Support | 6.2.3.p | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.2.4-04 | STIG Implementation & Reporting – 6.2.4 Senior Cisco Networking Engineering Support | 6.2.4.e | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.2.4-09 | MSR – 6.2.4 Senior Cisco Networking Engineering Support | 6.2.4.r | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.2.5-04 | STIG Implementation & Reporting – 6.2.5 Cisco Network Engineering Support | 6.2.5.e | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.2.5-09 | MSR – 6.2.5 Cisco Network Engineering Support | 6.2.5.n | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.1-09 | MSR – 6.3.1 Linux System Administration Support | 6.3.1.r | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.2-08 | MSR – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support | 6.3.2.o | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.3-10 | MSR – 6.3.3 Virtual Infrastructure (VI) System Administration Support | 6.3.3.p | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.4-11 | MSR – 6.3.4 Senior Windows System Administration Support | 6.3.4.u | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.5-11 | MSR – 6.3.5 Windows System Administration Support | 6.3.5.u | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.6-11 | MSR – 6.3.6 Global Command & Control System (GCCS) System Administration Support | 6.3.6.u | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-18 | MSR – 6.3.7 SCCM/MECH Administration Support | 6.3.7.z | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.4.1-09 | MSR – 6.4.1 Senior Web Application Development Support | 6.4.1.k | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.4.2-07 | MSR – 6.4.2 Web Application Development Support | 6.4.2.i | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.4.3-06 | MSR – 6.4.3 Senior Web Portal Development Support | 6.4.3.j | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.4.4-05 | MSR – 6.4.4 Web Portal Development Support | 6.4.4.i | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.1-05 | MSR – 6.5.1 Assessment and Authorization Support | 6.5.1.h | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.2-07 | Cyber Scorecard & Defense CyberScope Web Tool – 6.5.2 Cybersecurity Compliance Support | 6.5.2.h & 6.5.2.i | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-10-26 | 2026-11-25 | 2026-12-25 | 2027-01-25 | 2027-02-25 | 2027-03-25
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.2-08 | MSR – 6.5.2 Cybersecurity Compliance Support | 6.5.2.j | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.3-05 | MSR – 6.5.3 Cybersecurity Governance Support | 6.5.3.c | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.4-09 | MSR – 6.5.4 Network Defense Administrator Support | 6.5.4.ll | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.5-10 | MSR – 6.5.5 Endpoint Security Solutions (ESS) Support | 6.5.5.l | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.6-04 | MSR – 6.5.6 Electronic Key Management Support | 6.5.6.f | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.7-11 | MSR – 6.5.7 Security Information Event Manager (SIEM) Administrator Support | 6.5.7.l | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.8-11 | MSR – 6.5.8 Compliance Administrator Support | 6.5.8.g | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.6.1-04 | MSR – 6.6.1 Assistant Contract Technical Representative (ACTR) Support | 6.6.1.g | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.6.2-03 | MSR – 6.6.2 Communications Focal Point (CFP) Support | 6.6.2.e | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
Set Status, then record who accepted it and when. MSR is due the 5th business day of the succeeding month; the Cyber Scorecard is due the 25th business day of the month.

## Quarterly
Quarterly Deliverables – 5th business day of the quarter's first month
PWS as of 29 Sep 2023 ¦ USINDOPACOM J6 ¦ Tracking No. 712367735 ¦ Follow-on to CS2 (GS00Q17GWD2133 / HC1019-19-F-0015) ¦ Transition-in Jan 2024; Base Feb 2024 – Jan 2025; Option Years 1–4 to Jan 2029
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Fully accepted | Overdue | 2026-10-01 | 2027-01-01 | 2027-04-01
6.2.1-01 | AV Recommendations – 6.2.1 Audio Visual Systems Engineering Support | 6.2.1.d & 6.2.1.l | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2027-01-07 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.2.1-03 | AV Audits – 6.2.1 Audio Visual Systems Engineering Support | 6.2.1.k | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2027-01-07 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.2.3-01 | VTC Recommendations – 6.2.3 Video Teleconferencing (VTC) Network Engineering Support | 6.2.3.d & 6.2.3.g & 6.2.3.m | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2027-01-07 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.1-08 | Standard Operating Procedures (SOP) – 6.3.1 Linux System Administration Support | 6.3.1.p | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2027-01-07 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.2-07 | Standard Operating Procedures (SOP) – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support | 6.3.2.m | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2027-01-07 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.3-09 | Standard Operating Procedures (SOP) – 6.3.3 Virtual Infrastructure (VI) System Administration Support | 6.3.3.n | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2027-01-07 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.4-10 | Standard Operating Procedures (SOP) – 6.3.4 Senior Windows System Administration Support | 6.3.4.s | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2027-01-07 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.5-10 | Standard Operating Procedures (SOP) – 6.3.5 Windows System Administration Support | 6.3.5.s | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2027-01-07 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.6-09 | Standard Operating Procedures (SOP) – 6.3.6 Global Command & Control System (GCCS) System Administration Suppo | 6.3.6.r | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2027-01-07 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-17 | Standard Operating Procedures (SOP) – 6.3.7 SCCM/MECH Administration Support | 6.3.7.x | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2027-01-07 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.7-10 | Standard Operating Procedures (SOP) – 6.5.7 Security Information Event Manager (SIEM) Administrator Support | 6.5.7 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2027-01-07 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.8-10 | Standard Operating Procedures (SOP) – 6.5.8 Compliance Administrator Support | 6.5.8 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 1 | 2026-10-07 | 2027-01-07 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
Set Status, then record who accepted it and when. Quarters are calendar quarters (Jan, Apr, Jul, Oct), which are also the federal fiscal quarter starts.

## Daily Duties
Daily Duties – standing requirements, confirmed monthly
PWS as of 29 Sep 2023 ¦ USINDOPACOM J6 ¦ Tracking No. 712367735 ¦ Follow-on to CS2 (GS00Q17GWD2133 / HC1019-19-F-0015) ¦ Transition-in Jan 2024; Base Feb 2024 – Jan 2025; Option Years 1–4 to Jan 2029
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Fully accepted | Overdue | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01
6.2.4-02 | Network Engineering Troubleshooting and Operations – 6.2.4 Senior Cisco Networking Engineering Support | 6.2.4.a 6.2.4.g 6.2.4.h 6.2.4.i 6.2.4.j 6.2.4.k 6.2.4.l 6.2.4.m | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.2.4-05 | Security Scans – 6.2.4 Senior Cisco Networking Engineering Support | 6.2.4.h | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.2.5-02 | Network Engineering Troubleshooting and Operations – 6.2.5 Cisco Network Engineering Support | 6.2.5.a 6.2.5.g 6.2.5.h 6.2.5.i 6.2.5.j 6.2.5.k 6.2.5.l 6.2.5.m | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.2.5-05 | Security Scans – 6.2.5 Cisco Network Engineering Support | 6.2.5.h | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.1-01 | System Administration {Operating Systems & Applications} – 6.3.1 Linux System Administration Support | 6.3.1.a 6.3.1.e 6.3.1.f 6.3.1.h 6.3.1.i 6.3.1.j 6.3.1.k 6.3.1.n 6.3.1.o | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.1-02 | Patching – 6.3.1 Linux System Administration Support | 6.3.1.b | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.1-03 | STIG Compliance – 6.3.1 Linux System Administration Support | 6.3.1.c | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.1-04 | PKI Compliance – 6.3.1 Linux System Administration Support | 6.3.1.d | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.1-05 | ESS Compliance – 6.3.1 Linux System Administration Support | 6.3.1.g | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.1-06 | Security Scans – 6.3.1 Linux System Administration Support | 6.3.1.h 6.3.1.l | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.1-07 | Backup / Restore – 6.3.1 Linux System Administration Support | 6.3.1.m | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.2-01 | System Administration {Operating Systems & Applications} – 6.3.2 Virtual Desktop Infrastructure (VDI) System A | 6.3.2.a 6.3.2.f 6.3.2.g 6.3.2.h 6.3.2.k 6.3.2.l | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.2-02 | STIG Compliance – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support | 6.3.2.b | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.2-03 | PKI Compliance – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support | 6.3.2.c | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.2-04 | HBSS Compliance – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support | 6.3.2.d | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.2-05 | Security Scans – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support | 6.3.2.e 6.3.2.i | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.2-06 | Backup / Restore – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support | 6.3.2.j | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.3-01 | System Administration {Operating Systems & Applications} – 6.3.3 Virtual Infrastructure (VI) System Administra | 6.3.3.a 6.3.3.g 6.3.3.h 6.3.3.i 6.3.3.l | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.3-02 | Patching – 6.3.3 Virtual Infrastructure (VI) System Administration Support | 6.3.3.b | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.3-03 | STIG Compliance – 6.3.3 Virtual Infrastructure (VI) System Administration Support | 6.3.3.c | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.3-04 | PKI Compliance – 6.3.3 Virtual Infrastructure (VI) System Administration Support | 6.3.3.d | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.3-05 | ESS Compliance – 6.3.3 Virtual Infrastructure (VI) System Administration Support | 6.3.3.e | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.3-06 | Security Scans – 6.3.3 Virtual Infrastructure (VI) System Administration Support | 6.3.3.f 6.3.3.j | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.3-07 | Backup / Restore – 6.3.3 Virtual Infrastructure (VI) System Administration Support | 6.3.3.k | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.3-08 | Continuity of Operations (COOP) – 6.3.3 Virtual Infrastructure (VI) System Administration Support | 6.3.3.m | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.4-01 | System Administration {Operating Systems & Applications} – 6.3.4 Senior Windows System Administration Support | 6.3.4.a 6.3.4.d 6.3.4.e 6.3.4.f 6.3.4.h 6.3.4.k 6.3.4.l 6.3.4.m 6.3.4.q | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.4-02 | Patching – 6.3.4 Senior Windows System Administration Support | 6.3.4.b | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.4-03 | STIG Compliance – 6.3.4 Senior Windows System Administration Support | 6.3.4.c | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.4-04 | PKI Compliance – 6.3.4 Senior Windows System Administration Support | 6.3.4.g | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.4-05 | ESS Compliance – 6.3.4 Senior Windows System Administration Support | 6.3.4.i | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.4-06 | Security Scans – 6.3.4 Senior Windows System Administration Support | 6.3.4.j 6.3.4.n | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.4-07 | Backup / Restore – 6.3.4 Senior Windows System Administration Support | 6.3.4.o | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.4-09 | Continuity of Operations (COOP) – 6.3.4 Senior Windows System Administration Support | 6.3.4.r | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.5-01 | System Administration {Operating Systems & Applications} – 6.3.5 Windows System Administration Support | 6.3.5.a 6.3.5.d 6.3.5.e 6.3.5.i 6.3.5.j 6.3.5.k 6.3.5.l 6.3.5.m 6.3.5.q | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.5-02 | Patching – 6.3.5 Windows System Administration Support | 6.3.5.b | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.5-03 | STIG Compliance – 6.3.5 Windows System Administration Support | 6.3.5.c | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.5-04 | PKI Compliance – 6.3.5 Windows System Administration Support | 6.3.5.f | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.5-05 | HBSS Compliance – 6.3.5 Windows System Administration Support | 6.3.5.g | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.5-06 | Security Scans – 6.3.5 Windows System Administration Support | 6.3.5.h 6.3.5.n | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.5-07 | Backup / Restore – 6.3.5 Windows System Administration Support | 6.3.5.o | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.5-09 | Continuity of Operations (COOP) – 6.3.5 Windows System Administration Support | 6.3.5.r | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.6-01 | System Administration {Operating Systems & Applications} – 6.3.6 Global Command & Control System (GCCS) System | 6.3.6.a 6.3.6.e 6.3.6.h 6.3.6.i 6.3.6.j 6.3.6.m 6.3.6.n 6.3.6.o 6.3.6.p | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.6-02 | Patching – 6.3.6 Global Command & Control System (GCCS) System Administration Support | 6.3.6.b | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.6-03 | STIG Compliance – 6.3.6 Global Command & Control System (GCCS) System Administration Support | 6.3.6.c | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.6-04 | PKI Compliance – 6.3.6 Global Command & Control System (GCCS) System Administration Support | 6.3.6.d | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.6-05 | ESS Compliance – 6.3.6 Global Command & Control System (GCCS) System Administration Support | 6.3.6.f | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.6-06 | Security Scans – 6.3.6 Global Command & Control System (GCCS) System Administration Support | 6.3.6.g 6.3.6.k | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.6-07 | Backup / Restore – 6.3.6 Global Command & Control System (GCCS) System Administration Support | 6.3.6.l | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.6-08 | Continuity of Operations (COOP) – 6.3.6 Global Command & Control System (GCCS) System Administration Support | 6.3.6.q | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-01 | System Administration {Operating Systems & Applications} – 6.3.7 SCCM/MECH Administration Support | 6.3.7.a 6.3.7.f 6.3.7.g 6.3.7.h 6.3.7.j 6.3.7.k 6.3.7.m 6.3.7.w | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-02 | Patching – 6.3.7 SCCM/MECH Administration Support | 6.3.7.b | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-03 | STIG Compliance – 6.3.7 SCCM/MECH Administration Support | 6.3.7.c | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-04 | PKI Compliance – 6.3.7 SCCM/MECH Administration Support | 6.3.7.d | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-05 | ESS Compliance – 6.3.7 SCCM/MECH Administration Support | 6.3.7.e | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-06 | Monitor the performance of SCCM/MECM and identify and troubleshoot issues as they arise. – 6.3.7 SCCM/MECH Adm | 6.3.7.i | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-07 | Configures synchronization with software and patch update servers and Comply to Connect (C2C). – 6.3.7 SCCM/ME | 6.3.7.l | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-08 | Create/Edit/Delete/Deploy Collections (both user and device) – 6.3.7 SCCM/MECH Administration Support | 6.3.7.n | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-09 | Create/Edit/Delete/Deploy Reports – 6.3.7 SCCM/MECH Administration Support | 6.3.7.o | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-10 | Create/Edit/Delete/Deploy Task Sequences – 6.3.7 SCCM/MECH Administration Support | 6.3.7.p | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-11 | Create/Edit/Delete/Deploy Compliance Rules – 6.3.7 SCCM/MECH Administration Support | 6.3.7.q | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-12 | Create/Edit/Delete/Deploy Software Applications – 6.3.7 SCCM/MECH Administration Support | 6.3.7.r | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-13 | Create/Edit/Delete/Deploy Software Updates – 6.3.7 SCCM/MECH Administration Support | 6.3.7.s | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-14 | Create/Edit/Delete/Deploy Desktop SCCM Policies – 6.3.7 SCCM/MECH Administration Support | 6.3.7.t | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-15 | Create/Edit/Delete/Deploy Anti-malware Policies – 6.3.7 SCCM/MECH Administration Support | 6.3.7.u | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.3.7-16 | Create/Edit/Delete/Deploy Operating System Images – 6.3.7 SCCM/MECH Administration Support | 6.3.7.v | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.4-06 | STIG Compliance – 6.5.4 Network Defense Administrator Support | 6.5.4.e | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.4-07 | Security Scans – 6.5.4 Network Defense Administrator Support | 6.5.4.h | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.4-08 | PKI Compliance – 6.5.4 Network Defense Administrator Support | 6.5.4.i | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.5-04 | ESS O&M – 6.5.5 Endpoint Security Solutions (ESS) Support | 6.5.5.c 6.5.5.g 6.5.5.h | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.5-07 | STIG Compliance – 6.5.5 Endpoint Security Solutions (ESS) Support | 6.5.5.f | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.5-08 | Security Scans – 6.5.5 Endpoint Security Solutions (ESS) Support | 6.5.5.i | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.5-09 | PKI Compliance – 6.5.5 Endpoint Security Solutions (ESS) Support | 6.5.5.j | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.6-01 | USINDOPACOM COMSEC Program – 6.5.6 Electronic Key Management Support | 6.5.6.a & 6.5.6.c 6.5.6.d | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.7-01 | System Administration {Operating Systems & Applications} – 6.5.7 Security Information Event Manager (SIEM) Adm | 6.5.7.a 6.5.7.b 6.5.7.c | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.7-02 | Patching – 6.5.7 Security Information Event Manager (SIEM) Administrator Support | 6.5.7 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.7-03 | STIG Compliance – 6.5.7 Security Information Event Manager (SIEM) Administrator Support | 6.5.7.f | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.7-04 | PKI Compliance – 6.5.7 Security Information Event Manager (SIEM) Administrator Support | 6.5.7.j | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.7-05 | ESS Compliance – 6.5.7 Security Information Event Manager (SIEM) Administrator Support | 6.5.7 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.7-06 | Security Scans – 6.5.7 Security Information Event Manager (SIEM) Administrator Support | 6.5.7.i | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.7-07 | Backup/Restore – 6.5.7 Security Information Event Manager (SIEM) Administrator Support | 6.5.7 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.7-08 | ServiceNow Tickets – 6.5.7 Security Information Event Manager (SIEM) Administrator Support | 6.5.7.g | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.7-09 | Continuity of Operations (COOP) – 6.5.7 Security Information Event Manager (SIEM) Administrator Support | 6.5.7 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.8-01 | System Administration {Operating Systems & Applications} – 6.5.8 Compliance Administrator Support | 6.5.8 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.8-02 | Patching – 6.5.8 Compliance Administrator Support | 6.5.8 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.8-03 | STIG Compliance – 6.5.8 Compliance Administrator Support | 6.5.8a | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.8-04 | PKI Compliance – 6.5.8 Compliance Administrator Support | 6.5.8.e | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.8-05 | ESS Compliance – 6.5.8 Compliance Administrator Support | 6.5.8 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.8-06 | Security Scans – 6.5.8 Compliance Administrator Support | 6.5.8.d | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.8-07 | Backup/Restore – 6.5.8 Compliance Administrator Support | 6.5.8 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.8-08 | ServiceNow Tickets – 6.5.8 Compliance Administrator Support | 6.5.8.b | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
6.5.8-09 | Continuity of Operations (COOP) – 6.5.8 Compliance Administrator Support | 6.5.8 | Christine Y. Shigeta | Brian Abrigo | Due date | 0 | 0 | 2026-11-06 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07
Status
COR accepted by
COR date accepted
J698 accepted by
J698 date accepted
Result
These duties run every workday (patching, STIG compliance, scans, backups and the like). Tracking each day is impractical, so record the Government's monthly confirmation here: Status, who confirmed, and the date. Due date = 5th business day after month end, with the MSR.

## Daily Agenda
Daily Agenda – what is due, in date order
PWS as of 29 Sep 2023 ¦ USINDOPACOM J6 ¦ Tracking No. 712367735 ¦ Follow-on to CS2 (GS00Q17GWD2133 / HC1019-19-F-0015) ¦ Transition-in Jan 2024; Base Feb 2024 – Jan 2025; Option Years 1–4 to Jan 2029
Settings (edit the yellow cells)
Due Date | Day | ID | Deliverable | Source | Status | COR Accepted By | COR Date Accepted | J698 Accepted By | J698 Date Accepted | Result | Days Until Due | Flag | Notes | Clock start (tracking window; current option year is OY2) | 2026-10-01
2026-10-02 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 1 | Weekly | [6 empty] | -11 | OVERDUE |  | End of current option year (OY2) | 2027-01-31
2026-10-02 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 1 | Weekly | [6 empty] | -11 | OVERDUE |  | End of final option year (OY4) | 2029-01-31
2026-10-02 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 1 | Weekly | [6 empty] | -11 | OVERDUE |  | Gov inspection window (business days) | 5
2026-10-02 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 1 | Weekly | [6 empty] | -11 | OVERDUE |  | Resubmission window (business days) | 10
2026-10-07 | Wed | 6.2.1-01 | AV Recommendations – 6.2.1 Audio Visual Systems Engineering Support – Qtr from 01 Oct 2026 | Quarterly | [6 empty] | -6 | OVERDUE |  | Today | 2026-10-13
2026-10-07 | Wed | 6.2.1-03 | AV Audits – 6.2.1 Audio Visual Systems Engineering Support – Qtr from 01 Oct 2026 | Quarterly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | 6.2.3-01 | VTC Recommendations – 6.2.3 Video Teleconferencing (VTC) Network Engineering Support – Qtr from 01 Oct 2026 | Quarterly | [6 empty] | -6 | OVERDUE |  | Option year dates (PWS Section 10): OY1 Feb 2025–Jan 2026, OY2 Feb 2026–Jan 2027, OY3 Feb 2027–Jan 2028, OY4 Feb 2028–Jan 2029.
2026-10-07 | Wed | 6.3.1-08 | Standard Operating Procedures (SOP) – 6.3.1 Linux System Administration Support – Qtr from 01 Oct 2026 | Quarterly | [6 empty] | -6 | OVERDUE |  | The PWS does not state an inspection or resubmission window; 5 and 10 business days are placeholders.
2026-10-07 | Wed | 6.3.2-07 | Standard Operating Procedures (SOP) – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support – Qtr from 01 Oct 2026 | Quarterly | [6 empty] | -6 | OVERDUE |  | Daily Duties are not listed here; they are confirmed monthly on the Daily Duties tab.
2026-10-07 | Wed | 6.3.3-09 | Standard Operating Procedures (SOP) – 6.3.3 Virtual Infrastructure (VI) System Administration Support – Qtr from 01 Oct 2026 | Quarterly | [6 empty] | -6 | OVERDUE |  | Holidays are not excluded from business-day math.
2026-10-07 | Wed | 6.3.4-10 | Standard Operating Procedures (SOP) – 6.3.4 Senior Windows System Administration Support – Qtr from 01 Oct 2026 | Quarterly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | 6.3.5-10 | Standard Operating Procedures (SOP) – 6.3.5 Windows System Administration Support – Qtr from 01 Oct 2026 | Quarterly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | 6.3.6-09 | Standard Operating Procedures (SOP) – 6.3.6 Global Command & Control System (GCCS) System Administration Suppo – Qtr from 01 Oct 2026 | Quarterly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | 6.3.7-17 | Standard Operating Procedures (SOP) – 6.3.7 SCCM/MECH Administration Support – Qtr from 01 Oct 2026 | Quarterly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 1 | Weekly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 1 | Weekly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 1 | Weekly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 1 | Weekly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | 6.5.7-10 | Standard Operating Procedures (SOP) – 6.5.7 Security Information Event Manager (SIEM) Administrator Support – Qtr from 01 Oct 2026 | Quarterly | [6 empty] | -6 | OVERDUE
2026-10-07 | Wed | 6.5.8-10 | Standard Operating Procedures (SOP) – 6.5.8 Compliance Administrator Support – Qtr from 01 Oct 2026 | Quarterly | [6 empty] | -6 | OVERDUE
2026-10-09 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 2 | Weekly | [6 empty] | -4 | OVERDUE
2026-10-09 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 2 | Weekly | [6 empty] | -4 | OVERDUE
2026-10-09 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 2 | Weekly | [6 empty] | -4 | OVERDUE
2026-10-09 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 2 | Weekly | [6 empty] | -4 | OVERDUE
2026-10-14 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 2 | Weekly | [6 empty] | 1 | Due within 7 days
2026-10-14 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 2 | Weekly | [6 empty] | 1 | Due within 7 days
2026-10-14 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 2 | Weekly | [6 empty] | 1 | Due within 7 days
2026-10-14 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 2 | Weekly | [6 empty] | 1 | Due within 7 days
2026-10-16 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 3 | Weekly | [6 empty] | 3 | Due within 7 days
2026-10-16 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 3 | Weekly | [6 empty] | 3 | Due within 7 days
2026-10-16 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 3 | Weekly | [6 empty] | 3 | Due within 7 days
2026-10-16 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 3 | Weekly | [6 empty] | 3 | Due within 7 days
2026-10-21 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 3 | Weekly | [6 empty] | 8
2026-10-21 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 3 | Weekly | [6 empty] | 8
2026-10-21 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 3 | Weekly | [6 empty] | 8
2026-10-21 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 3 | Weekly | [6 empty] | 8
2026-10-23 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 4 | Weekly | [6 empty] | 10
2026-10-23 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 4 | Weekly | [6 empty] | 10
2026-10-23 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 4 | Weekly | [6 empty] | 10
2026-10-23 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 4 | Weekly | [6 empty] | 10
2026-10-26 | Mon | 6.5.2-07 | Cyber Scorecard & Defense CyberScope Web Tool – 6.5.2 Cybersecurity Compliance Support – Oct 2026 | Monthly | [6 empty] | 13
2026-10-28 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 4 | Weekly | [6 empty] | 15
2026-10-28 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 4 | Weekly | [6 empty] | 15
2026-10-28 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 4 | Weekly | [6 empty] | 15
2026-10-28 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 4 | Weekly | [6 empty] | 15
2026-10-30 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 5 | Weekly | [6 empty] | 17
2026-10-30 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 5 | Weekly | [6 empty] | 17
2026-10-30 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 5 | Weekly | [6 empty] | 17
2026-10-30 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 5 | Weekly | [6 empty] | 17
2026-11-04 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 5 | Weekly | [6 empty] | 22
2026-11-04 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 5 | Weekly | [6 empty] | 22
2026-11-04 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 5 | Weekly | [6 empty] | 22
2026-11-04 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 5 | Weekly | [6 empty] | 22
2026-11-06 | Fri | 6.1.1-03 | MSR – 6.1.1 Enterprise Architecture Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.1.3-03 | MSR – 6.1.3 Business Process Analyst Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.2.1-05 | MSR – 6.2.1 Audio Visual Systems Engineering Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.2.2-04 | MSR – 6.2.2 Video Teleconferencing (VTC) Scheduling Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.2.3-02 | MSR – 6.2.3 Video Teleconferencing (VTC) Network Engineering Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.2.4-04 | STIG Implementation & Reporting – 6.2.4 Senior Cisco Networking Engineering Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.2.4-09 | MSR – 6.2.4 Senior Cisco Networking Engineering Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.2.5-04 | STIG Implementation & Reporting – 6.2.5 Cisco Network Engineering Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.2.5-09 | MSR – 6.2.5 Cisco Network Engineering Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.3.1-09 | MSR – 6.3.1 Linux System Administration Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.3.2-08 | MSR – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.3.3-10 | MSR – 6.3.3 Virtual Infrastructure (VI) System Administration Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 6 | Weekly | [6 empty] | 24
2026-11-06 | Fri | 6.3.4-11 | MSR – 6.3.4 Senior Windows System Administration Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 6 | Weekly | [6 empty] | 24
2026-11-06 | Fri | 6.3.5-11 | MSR – 6.3.5 Windows System Administration Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.3.6-11 | MSR – 6.3.6 Global Command & Control System (GCCS) System Administration Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.3.7-18 | MSR – 6.3.7 SCCM/MECH Administration Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.4.1-09 | MSR – 6.4.1 Senior Web Application Development Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.4.2-07 | MSR – 6.4.2 Web Application Development Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.4.3-06 | MSR – 6.4.3 Senior Web Portal Development Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.4.4-05 | MSR – 6.4.4 Web Portal Development Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.5.1-05 | MSR – 6.5.1 Assessment and Authorization Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 6 | Weekly | [6 empty] | 24
2026-11-06 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 6 | Weekly | [6 empty] | 24
2026-11-06 | Fri | 6.5.2-08 | MSR – 6.5.2 Cybersecurity Compliance Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.5.3-05 | MSR – 6.5.3 Cybersecurity Governance Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.5.4-09 | MSR – 6.5.4 Network Defense Administrator Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.5.5-10 | MSR – 6.5.5 Endpoint Security Solutions (ESS) Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.5.6-04 | MSR – 6.5.6 Electronic Key Management Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.5.7-11 | MSR – 6.5.7 Security Information Event Manager (SIEM) Administrator Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.5.8-11 | MSR – 6.5.8 Compliance Administrator Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.6.1-04 | MSR – 6.6.1 Assistant Contract Technical Representative (ACTR) Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-06 | Fri | 6.6.2-03 | MSR – 6.6.2 Communications Focal Point (CFP) Support – Oct 2026 | Monthly | [6 empty] | 24
2026-11-11 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 6 | Weekly | [6 empty] | 29
2026-11-11 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 6 | Weekly | [6 empty] | 29
2026-11-11 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 6 | Weekly | [6 empty] | 29
2026-11-11 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 6 | Weekly | [6 empty] | 29
2026-11-13 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 7 | Weekly | [6 empty] | 31
2026-11-13 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 7 | Weekly | [6 empty] | 31
2026-11-13 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 7 | Weekly | [6 empty] | 31
2026-11-13 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 7 | Weekly | [6 empty] | 31
2026-11-18 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 7 | Weekly | [6 empty] | 36
2026-11-18 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 7 | Weekly | [6 empty] | 36
2026-11-18 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 7 | Weekly | [6 empty] | 36
2026-11-18 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 7 | Weekly | [6 empty] | 36
2026-11-20 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 8 | Weekly | [6 empty] | 38
2026-11-20 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 8 | Weekly | [6 empty] | 38
2026-11-20 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 8 | Weekly | [6 empty] | 38
2026-11-20 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 8 | Weekly | [6 empty] | 38
2026-11-25 | Wed | 6.5.2-07 | Cyber Scorecard & Defense CyberScope Web Tool – 6.5.2 Cybersecurity Compliance Support – Nov 2026 | Monthly | [6 empty] | 43
2026-11-25 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 8 | Weekly | [6 empty] | 43
2026-11-25 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 8 | Weekly | [6 empty] | 43
2026-11-25 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 8 | Weekly | [6 empty] | 43
2026-11-25 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 8 | Weekly | [6 empty] | 43
2026-11-27 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 9 | Weekly | [6 empty] | 45
2026-11-27 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 9 | Weekly | [6 empty] | 45
2026-11-27 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 9 | Weekly | [6 empty] | 45
2026-11-27 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 9 | Weekly | [6 empty] | 45
2026-12-02 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 9 | Weekly | [6 empty] | 50
2026-12-02 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 9 | Weekly | [6 empty] | 50
2026-12-02 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 9 | Weekly | [6 empty] | 50
2026-12-02 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 9 | Weekly | [6 empty] | 50
2026-12-04 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 10 | Weekly | [6 empty] | 52
2026-12-04 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 10 | Weekly | [6 empty] | 52
2026-12-04 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 10 | Weekly | [6 empty] | 52
2026-12-04 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 10 | Weekly | [6 empty] | 52
2026-12-07 | Mon | 6.1.1-03 | MSR – 6.1.1 Enterprise Architecture Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.1.3-03 | MSR – 6.1.3 Business Process Analyst Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.2.1-05 | MSR – 6.2.1 Audio Visual Systems Engineering Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.2.2-04 | MSR – 6.2.2 Video Teleconferencing (VTC) Scheduling Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.2.3-02 | MSR – 6.2.3 Video Teleconferencing (VTC) Network Engineering Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.2.4-04 | STIG Implementation & Reporting – 6.2.4 Senior Cisco Networking Engineering Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.2.4-09 | MSR – 6.2.4 Senior Cisco Networking Engineering Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.2.5-04 | STIG Implementation & Reporting – 6.2.5 Cisco Network Engineering Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.2.5-09 | MSR – 6.2.5 Cisco Network Engineering Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.3.1-09 | MSR – 6.3.1 Linux System Administration Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.3.2-08 | MSR – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.3.3-10 | MSR – 6.3.3 Virtual Infrastructure (VI) System Administration Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.3.4-11 | MSR – 6.3.4 Senior Windows System Administration Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.3.5-11 | MSR – 6.3.5 Windows System Administration Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.3.6-11 | MSR – 6.3.6 Global Command & Control System (GCCS) System Administration Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.3.7-18 | MSR – 6.3.7 SCCM/MECH Administration Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.4.1-09 | MSR – 6.4.1 Senior Web Application Development Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.4.2-07 | MSR – 6.4.2 Web Application Development Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.4.3-06 | MSR – 6.4.3 Senior Web Portal Development Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.4.4-05 | MSR – 6.4.4 Web Portal Development Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.5.1-05 | MSR – 6.5.1 Assessment and Authorization Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.5.2-08 | MSR – 6.5.2 Cybersecurity Compliance Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.5.3-05 | MSR – 6.5.3 Cybersecurity Governance Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.5.4-09 | MSR – 6.5.4 Network Defense Administrator Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.5.5-10 | MSR – 6.5.5 Endpoint Security Solutions (ESS) Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.5.6-04 | MSR – 6.5.6 Electronic Key Management Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.5.7-11 | MSR – 6.5.7 Security Information Event Manager (SIEM) Administrator Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.5.8-11 | MSR – 6.5.8 Compliance Administrator Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.6.1-04 | MSR – 6.6.1 Assistant Contract Technical Representative (ACTR) Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | 6.6.2-03 | MSR – 6.6.2 Communications Focal Point (CFP) Support – Nov 2026 | Monthly | [6 empty] | 55
2026-12-09 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 10 | Weekly | [6 empty] | 57
2026-12-09 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 10 | Weekly | [6 empty] | 57
2026-12-09 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 10 | Weekly | [6 empty] | 57
2026-12-09 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 10 | Weekly | [6 empty] | 57
2026-12-11 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 11 | Weekly | [6 empty] | 59
2026-12-11 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 11 | Weekly | [6 empty] | 59
2026-12-11 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 11 | Weekly | [6 empty] | 59
2026-12-11 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 11 | Weekly | [6 empty] | 59
2026-12-16 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 11 | Weekly | [6 empty] | 64
2026-12-16 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 11 | Weekly | [6 empty] | 64
2026-12-16 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 11 | Weekly | [6 empty] | 64
2026-12-16 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 11 | Weekly | [6 empty] | 64
2026-12-18 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 12 | Weekly | [6 empty] | 66
2026-12-18 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 12 | Weekly | [6 empty] | 66
2026-12-18 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 12 | Weekly | [6 empty] | 66
2026-12-18 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 12 | Weekly | [6 empty] | 66
2026-12-23 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 12 | Weekly | [6 empty] | 71
2026-12-23 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 12 | Weekly | [6 empty] | 71
2026-12-23 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 12 | Weekly | [6 empty] | 71
2026-12-23 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 12 | Weekly | [6 empty] | 71
2026-12-25 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 13 | Weekly | [6 empty] | 73
2026-12-25 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 13 | Weekly | [6 empty] | 73
2026-12-25 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 13 | Weekly | [6 empty] | 73
2026-12-25 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 13 | Weekly | [6 empty] | 73
2026-12-25 | Fri | 6.5.2-07 | Cyber Scorecard & Defense CyberScope Web Tool – 6.5.2 Cybersecurity Compliance Support – Dec 2026 | Monthly | [6 empty] | 73
2026-12-30 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 13 | Weekly | [6 empty] | 78
2026-12-30 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 13 | Weekly | [6 empty] | 78
2026-12-30 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 13 | Weekly | [6 empty] | 78
2026-12-30 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 13 | Weekly | [6 empty] | 78
2027-01-01 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 14 | Weekly | [6 empty] | 80
2027-01-01 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 14 | Weekly | [6 empty] | 80
2027-01-01 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 14 | Weekly | [6 empty] | 80
2027-01-01 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 14 | Weekly | [6 empty] | 80
2027-01-06 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 14 | Weekly | [6 empty] | 85
2027-01-06 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 14 | Weekly | [6 empty] | 85
2027-01-06 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 14 | Weekly | [6 empty] | 85
2027-01-06 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 14 | Weekly | [6 empty] | 85
2027-01-07 | Thu | 6.1.1-03 | MSR – 6.1.1 Enterprise Architecture Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.1.3-03 | MSR – 6.1.3 Business Process Analyst Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.2.1-01 | AV Recommendations – 6.2.1 Audio Visual Systems Engineering Support – Qtr from 01 Jan 2027 | Quarterly | [6 empty] | 86
2027-01-07 | Thu | 6.2.1-03 | AV Audits – 6.2.1 Audio Visual Systems Engineering Support – Qtr from 01 Jan 2027 | Quarterly | [6 empty] | 86
2027-01-07 | Thu | 6.2.1-05 | MSR – 6.2.1 Audio Visual Systems Engineering Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.2.2-04 | MSR – 6.2.2 Video Teleconferencing (VTC) Scheduling Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.2.3-01 | VTC Recommendations – 6.2.3 Video Teleconferencing (VTC) Network Engineering Support – Qtr from 01 Jan 2027 | Quarterly | [6 empty] | 86
2027-01-07 | Thu | 6.2.3-02 | MSR – 6.2.3 Video Teleconferencing (VTC) Network Engineering Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.2.4-04 | STIG Implementation & Reporting – 6.2.4 Senior Cisco Networking Engineering Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.2.4-09 | MSR – 6.2.4 Senior Cisco Networking Engineering Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.2.5-04 | STIG Implementation & Reporting – 6.2.5 Cisco Network Engineering Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.2.5-09 | MSR – 6.2.5 Cisco Network Engineering Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.3.1-08 | Standard Operating Procedures (SOP) – 6.3.1 Linux System Administration Support – Qtr from 01 Jan 2027 | Quarterly | [6 empty] | 86
2027-01-07 | Thu | 6.3.1-09 | MSR – 6.3.1 Linux System Administration Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.3.2-07 | Standard Operating Procedures (SOP) – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support – Qtr from 01 Jan 2027 | Quarterly | [6 empty] | 86
2027-01-07 | Thu | 6.3.2-08 | MSR – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.3.3-09 | Standard Operating Procedures (SOP) – 6.3.3 Virtual Infrastructure (VI) System Administration Support – Qtr from 01 Jan 2027 | Quarterly | [6 empty] | 86
2027-01-07 | Thu | 6.3.3-10 | MSR – 6.3.3 Virtual Infrastructure (VI) System Administration Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.3.4-10 | Standard Operating Procedures (SOP) – 6.3.4 Senior Windows System Administration Support – Qtr from 01 Jan 2027 | Quarterly | [6 empty] | 86
2027-01-07 | Thu | 6.3.4-11 | MSR – 6.3.4 Senior Windows System Administration Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.3.5-10 | Standard Operating Procedures (SOP) – 6.3.5 Windows System Administration Support – Qtr from 01 Jan 2027 | Quarterly | [6 empty] | 86
2027-01-07 | Thu | 6.3.5-11 | MSR – 6.3.5 Windows System Administration Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.3.6-09 | Standard Operating Procedures (SOP) – 6.3.6 Global Command & Control System (GCCS) System Administration Suppo – Qtr from 01 Jan 2027 | Quarterly | [6 empty] | 86
2027-01-07 | Thu | 6.3.6-11 | MSR – 6.3.6 Global Command & Control System (GCCS) System Administration Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.3.7-17 | Standard Operating Procedures (SOP) – 6.3.7 SCCM/MECH Administration Support – Qtr from 01 Jan 2027 | Quarterly | [6 empty] | 86
2027-01-07 | Thu | 6.3.7-18 | MSR – 6.3.7 SCCM/MECH Administration Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.4.1-09 | MSR – 6.4.1 Senior Web Application Development Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.4.2-07 | MSR – 6.4.2 Web Application Development Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.4.3-06 | MSR – 6.4.3 Senior Web Portal Development Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.4.4-05 | MSR – 6.4.4 Web Portal Development Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.5.1-05 | MSR – 6.5.1 Assessment and Authorization Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.5.2-08 | MSR – 6.5.2 Cybersecurity Compliance Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.5.3-05 | MSR – 6.5.3 Cybersecurity Governance Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.5.4-09 | MSR – 6.5.4 Network Defense Administrator Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.5.5-10 | MSR – 6.5.5 Endpoint Security Solutions (ESS) Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.5.6-04 | MSR – 6.5.6 Electronic Key Management Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.5.7-10 | Standard Operating Procedures (SOP) – 6.5.7 Security Information Event Manager (SIEM) Administrator Support – Qtr from 01 Jan 2027 | Quarterly | [6 empty] | 86
2027-01-07 | Thu | 6.5.7-11 | MSR – 6.5.7 Security Information Event Manager (SIEM) Administrator Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.5.8-10 | Standard Operating Procedures (SOP) – 6.5.8 Compliance Administrator Support – Qtr from 01 Jan 2027 | Quarterly | [6 empty] | 86
2027-01-07 | Thu | 6.5.8-11 | MSR – 6.5.8 Compliance Administrator Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.6.1-04 | MSR – 6.6.1 Assistant Contract Technical Representative (ACTR) Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | 6.6.2-03 | MSR – 6.6.2 Communications Focal Point (CFP) Support – Dec 2026 | Monthly | [6 empty] | 86
2027-01-08 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 15 | Weekly | [6 empty] | 87
2027-01-08 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 15 | Weekly | [6 empty] | 87
2027-01-08 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 15 | Weekly | [6 empty] | 87
2027-01-08 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 15 | Weekly | [6 empty] | 87
2027-01-13 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 15 | Weekly | [6 empty] | 92
2027-01-13 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 15 | Weekly | [6 empty] | 92
2027-01-13 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 15 | Weekly | [6 empty] | 92
2027-01-13 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 15 | Weekly | [6 empty] | 92
2027-01-15 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 16 | Weekly | [6 empty] | 94
2027-01-15 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 16 | Weekly | [6 empty] | 94
2027-01-15 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 16 | Weekly | [6 empty] | 94
2027-01-15 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 16 | Weekly | [6 empty] | 94
2027-01-20 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 16 | Weekly | [6 empty] | 99
2027-01-20 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 16 | Weekly | [6 empty] | 99
2027-01-20 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 16 | Weekly | [6 empty] | 99
2027-01-20 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 16 | Weekly | [6 empty] | 99
2027-01-22 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 17 | Weekly | [6 empty] | 101
2027-01-22 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 17 | Weekly | [6 empty] | 101
2027-01-22 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 17 | Weekly | [6 empty] | 101
2027-01-22 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 17 | Weekly | [6 empty] | 101
2027-01-25 | Mon | 6.5.2-07 | Cyber Scorecard & Defense CyberScope Web Tool – 6.5.2 Cybersecurity Compliance Support – Jan 2027 | Monthly | [6 empty] | 104
2027-01-27 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 17 | Weekly | [6 empty] | 106
2027-01-27 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 17 | Weekly | [6 empty] | 106
2027-01-27 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 17 | Weekly | [6 empty] | 106
2027-01-27 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 17 | Weekly | [6 empty] | 106
2027-01-29 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 18 | Weekly | [6 empty] | 108
2027-01-29 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 18 | Weekly | [6 empty] | 108
2027-01-29 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 18 | Weekly | [6 empty] | 108
2027-01-29 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 18 | Weekly | [6 empty] | 108
2027-02-03 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 18 | Weekly | [6 empty] | 113
2027-02-03 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 18 | Weekly | [6 empty] | 113
2027-02-03 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 18 | Weekly | [6 empty] | 113
2027-02-03 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 18 | Weekly | [6 empty] | 113
2027-02-05 | Fri | 6.1.1-03 | MSR – 6.1.1 Enterprise Architecture Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.1.3-03 | MSR – 6.1.3 Business Process Analyst Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.2.1-05 | MSR – 6.2.1 Audio Visual Systems Engineering Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.2.2-04 | MSR – 6.2.2 Video Teleconferencing (VTC) Scheduling Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.2.3-02 | MSR – 6.2.3 Video Teleconferencing (VTC) Network Engineering Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.2.4-04 | STIG Implementation & Reporting – 6.2.4 Senior Cisco Networking Engineering Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.2.4-09 | MSR – 6.2.4 Senior Cisco Networking Engineering Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.2.5-04 | STIG Implementation & Reporting – 6.2.5 Cisco Network Engineering Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.2.5-09 | MSR – 6.2.5 Cisco Network Engineering Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.3.1-09 | MSR – 6.3.1 Linux System Administration Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.3.2-08 | MSR – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.3.3-10 | MSR – 6.3.3 Virtual Infrastructure (VI) System Administration Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 19 | Weekly | [6 empty] | 115
2027-02-05 | Fri | 6.3.4-11 | MSR – 6.3.4 Senior Windows System Administration Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 19 | Weekly | [6 empty] | 115
2027-02-05 | Fri | 6.3.5-11 | MSR – 6.3.5 Windows System Administration Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.3.6-11 | MSR – 6.3.6 Global Command & Control System (GCCS) System Administration Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.3.7-18 | MSR – 6.3.7 SCCM/MECH Administration Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.4.1-09 | MSR – 6.4.1 Senior Web Application Development Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.4.2-07 | MSR – 6.4.2 Web Application Development Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.4.3-06 | MSR – 6.4.3 Senior Web Portal Development Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.4.4-05 | MSR – 6.4.4 Web Portal Development Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.5.1-05 | MSR – 6.5.1 Assessment and Authorization Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 19 | Weekly | [6 empty] | 115
2027-02-05 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 19 | Weekly | [6 empty] | 115
2027-02-05 | Fri | 6.5.2-08 | MSR – 6.5.2 Cybersecurity Compliance Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.5.3-05 | MSR – 6.5.3 Cybersecurity Governance Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.5.4-09 | MSR – 6.5.4 Network Defense Administrator Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.5.5-10 | MSR – 6.5.5 Endpoint Security Solutions (ESS) Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.5.6-04 | MSR – 6.5.6 Electronic Key Management Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.5.7-11 | MSR – 6.5.7 Security Information Event Manager (SIEM) Administrator Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.5.8-11 | MSR – 6.5.8 Compliance Administrator Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.6.1-04 | MSR – 6.6.1 Assistant Contract Technical Representative (ACTR) Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | 6.6.2-03 | MSR – 6.6.2 Communications Focal Point (CFP) Support – Jan 2027 | Monthly | [6 empty] | 115
2027-02-10 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 19 | Weekly | [6 empty] | 120
2027-02-10 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 19 | Weekly | [6 empty] | 120
2027-02-10 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 19 | Weekly | [6 empty] | 120
2027-02-10 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 19 | Weekly | [6 empty] | 120
2027-02-12 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 20 | Weekly | [6 empty] | 122
2027-02-12 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 20 | Weekly | [6 empty] | 122
2027-02-12 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 20 | Weekly | [6 empty] | 122
2027-02-12 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 20 | Weekly | [6 empty] | 122
2027-02-17 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 20 | Weekly | [6 empty] | 127
2027-02-17 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 20 | Weekly | [6 empty] | 127
2027-02-17 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 20 | Weekly | [6 empty] | 127
2027-02-17 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 20 | Weekly | [6 empty] | 127
2027-02-19 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 21 | Weekly | [6 empty] | 129
2027-02-19 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 21 | Weekly | [6 empty] | 129
2027-02-19 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 21 | Weekly | [6 empty] | 129
2027-02-19 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 21 | Weekly | [6 empty] | 129
2027-02-24 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 21 | Weekly | [6 empty] | 134
2027-02-24 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 21 | Weekly | [6 empty] | 134
2027-02-24 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 21 | Weekly | [6 empty] | 134
2027-02-24 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 21 | Weekly | [6 empty] | 134
2027-02-25 | Thu | 6.5.2-07 | Cyber Scorecard & Defense CyberScope Web Tool – 6.5.2 Cybersecurity Compliance Support – Feb 2027 | Monthly | [6 empty] | 135
2027-02-26 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 22 | Weekly | [6 empty] | 136
2027-02-26 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 22 | Weekly | [6 empty] | 136
2027-02-26 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 22 | Weekly | [6 empty] | 136
2027-02-26 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 22 | Weekly | [6 empty] | 136
2027-03-03 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 22 | Weekly | [6 empty] | 141
2027-03-03 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 22 | Weekly | [6 empty] | 141
2027-03-03 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 22 | Weekly | [6 empty] | 141
2027-03-03 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 22 | Weekly | [6 empty] | 141
2027-03-05 | Fri | 6.1.1-03 | MSR – 6.1.1 Enterprise Architecture Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.1.3-03 | MSR – 6.1.3 Business Process Analyst Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.2.1-05 | MSR – 6.2.1 Audio Visual Systems Engineering Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.2.2-04 | MSR – 6.2.2 Video Teleconferencing (VTC) Scheduling Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.2.3-02 | MSR – 6.2.3 Video Teleconferencing (VTC) Network Engineering Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.2.4-04 | STIG Implementation & Reporting – 6.2.4 Senior Cisco Networking Engineering Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.2.4-09 | MSR – 6.2.4 Senior Cisco Networking Engineering Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.2.5-04 | STIG Implementation & Reporting – 6.2.5 Cisco Network Engineering Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.2.5-09 | MSR – 6.2.5 Cisco Network Engineering Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.3.1-09 | MSR – 6.3.1 Linux System Administration Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.3.2-08 | MSR – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.3.3-10 | MSR – 6.3.3 Virtual Infrastructure (VI) System Administration Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 23 | Weekly | [6 empty] | 143
2027-03-05 | Fri | 6.3.4-11 | MSR – 6.3.4 Senior Windows System Administration Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 23 | Weekly | [6 empty] | 143
2027-03-05 | Fri | 6.3.5-11 | MSR – 6.3.5 Windows System Administration Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.3.6-11 | MSR – 6.3.6 Global Command & Control System (GCCS) System Administration Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.3.7-18 | MSR – 6.3.7 SCCM/MECH Administration Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.4.1-09 | MSR – 6.4.1 Senior Web Application Development Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.4.2-07 | MSR – 6.4.2 Web Application Development Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.4.3-06 | MSR – 6.4.3 Senior Web Portal Development Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.4.4-05 | MSR – 6.4.4 Web Portal Development Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.5.1-05 | MSR – 6.5.1 Assessment and Authorization Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 23 | Weekly | [6 empty] | 143
2027-03-05 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 23 | Weekly | [6 empty] | 143
2027-03-05 | Fri | 6.5.2-08 | MSR – 6.5.2 Cybersecurity Compliance Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.5.3-05 | MSR – 6.5.3 Cybersecurity Governance Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.5.4-09 | MSR – 6.5.4 Network Defense Administrator Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.5.5-10 | MSR – 6.5.5 Endpoint Security Solutions (ESS) Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.5.6-04 | MSR – 6.5.6 Electronic Key Management Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.5.7-11 | MSR – 6.5.7 Security Information Event Manager (SIEM) Administrator Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.5.8-11 | MSR – 6.5.8 Compliance Administrator Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.6.1-04 | MSR – 6.6.1 Assistant Contract Technical Representative (ACTR) Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | 6.6.2-03 | MSR – 6.6.2 Communications Focal Point (CFP) Support – Feb 2027 | Monthly | [6 empty] | 143
2027-03-10 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 23 | Weekly | [6 empty] | 148
2027-03-10 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 23 | Weekly | [6 empty] | 148
2027-03-10 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 23 | Weekly | [6 empty] | 148
2027-03-10 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 23 | Weekly | [6 empty] | 148
2027-03-12 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 24 | Weekly | [6 empty] | 150
2027-03-12 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 24 | Weekly | [6 empty] | 150
2027-03-12 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 24 | Weekly | [6 empty] | 150
2027-03-12 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 24 | Weekly | [6 empty] | 150
2027-03-17 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 24 | Weekly | [6 empty] | 155
2027-03-17 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 24 | Weekly | [6 empty] | 155
2027-03-17 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 24 | Weekly | [6 empty] | 155
2027-03-17 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 24 | Weekly | [6 empty] | 155
2027-03-19 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 25 | Weekly | [6 empty] | 157
2027-03-19 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 25 | Weekly | [6 empty] | 157
2027-03-19 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 25 | Weekly | [6 empty] | 157
2027-03-19 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 25 | Weekly | [6 empty] | 157
2027-03-24 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 25 | Weekly | [6 empty] | 162
2027-03-24 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 25 | Weekly | [6 empty] | 162
2027-03-24 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 25 | Weekly | [6 empty] | 162
2027-03-24 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 25 | Weekly | [6 empty] | 162
2027-03-25 | Thu | 6.5.2-07 | Cyber Scorecard & Defense CyberScope Web Tool – 6.5.2 Cybersecurity Compliance Support – Mar 2027 | Monthly | [6 empty] | 163
2027-03-26 | Fri | 6.3.4-08 | Active Directory Management – 6.3.4 Senior Windows System Administration Support – Wk 26 | Weekly | [6 empty] | 164
2027-03-26 | Fri | 6.3.5-08 | Active Directory Management – 6.3.5 Windows System Administration Support – Wk 26 | Weekly | [6 empty] | 164
2027-03-26 | Fri | 6.5.2-01 | Compliance Tracking & Reporting – 6.5.2 Cybersecurity Compliance Support – Wk 26 | Weekly | [6 empty] | 164
2027-03-26 | Fri | 6.5.2-02 | Risk Analysis – 6.5.2 Cybersecurity Compliance Support – Wk 26 | Weekly | [6 empty] | 164
2027-03-31 | Wed | 6.5.4-04 | Configuration Management Summary of Changes – 6.5.4 Network Defense Administrator Support – Wk 26 | Weekly | [6 empty] | 169
2027-03-31 | Wed | 6.5.4-05 | Cyber Threat Summaries – 6.5.4 Network Defense Administrator Support – Wk 26 | Weekly | [6 empty] | 169
2027-03-31 | Wed | 6.5.5-05 | Configuration management summary of changes – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 26 | Weekly | [6 empty] | 169
2027-03-31 | Wed | 6.5.5-06 | ESS Baseline Report – 6.5.5 Endpoint Security Solutions (ESS) Support – Wk 26 | Weekly | [6 empty] | 169
2027-04-07 | Wed | 6.1.1-03 | MSR – 6.1.1 Enterprise Architecture Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.1.3-03 | MSR – 6.1.3 Business Process Analyst Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.2.1-01 | AV Recommendations – 6.2.1 Audio Visual Systems Engineering Support – Qtr from 01 Apr 2027 | Quarterly | [6 empty] | 176
2027-04-07 | Wed | 6.2.1-03 | AV Audits – 6.2.1 Audio Visual Systems Engineering Support – Qtr from 01 Apr 2027 | Quarterly | [6 empty] | 176
2027-04-07 | Wed | 6.2.1-05 | MSR – 6.2.1 Audio Visual Systems Engineering Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.2.2-04 | MSR – 6.2.2 Video Teleconferencing (VTC) Scheduling Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.2.3-01 | VTC Recommendations – 6.2.3 Video Teleconferencing (VTC) Network Engineering Support – Qtr from 01 Apr 2027 | Quarterly | [6 empty] | 176
2027-04-07 | Wed | 6.2.3-02 | MSR – 6.2.3 Video Teleconferencing (VTC) Network Engineering Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.2.4-04 | STIG Implementation & Reporting – 6.2.4 Senior Cisco Networking Engineering Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.2.4-09 | MSR – 6.2.4 Senior Cisco Networking Engineering Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.2.5-04 | STIG Implementation & Reporting – 6.2.5 Cisco Network Engineering Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.2.5-09 | MSR – 6.2.5 Cisco Network Engineering Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.3.1-08 | Standard Operating Procedures (SOP) – 6.3.1 Linux System Administration Support – Qtr from 01 Apr 2027 | Quarterly | [6 empty] | 176
2027-04-07 | Wed | 6.3.1-09 | MSR – 6.3.1 Linux System Administration Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.3.2-07 | Standard Operating Procedures (SOP) – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support – Qtr from 01 Apr 2027 | Quarterly | [6 empty] | 176
2027-04-07 | Wed | 6.3.2-08 | MSR – 6.3.2 Virtual Desktop Infrastructure (VDI) System Administration Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.3.3-09 | Standard Operating Procedures (SOP) – 6.3.3 Virtual Infrastructure (VI) System Administration Support – Qtr from 01 Apr 2027 | Quarterly | [6 empty] | 176
2027-04-07 | Wed | 6.3.3-10 | MSR – 6.3.3 Virtual Infrastructure (VI) System Administration Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.3.4-10 | Standard Operating Procedures (SOP) – 6.3.4 Senior Windows System Administration Support – Qtr from 01 Apr 2027 | Quarterly | [6 empty] | 176
2027-04-07 | Wed | 6.3.4-11 | MSR – 6.3.4 Senior Windows System Administration Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.3.5-10 | Standard Operating Procedures (SOP) – 6.3.5 Windows System Administration Support – Qtr from 01 Apr 2027 | Quarterly | [6 empty] | 176
2027-04-07 | Wed | 6.3.5-11 | MSR – 6.3.5 Windows System Administration Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.3.6-09 | Standard Operating Procedures (SOP) – 6.3.6 Global Command & Control System (GCCS) System Administration Suppo – Qtr from 01 Apr 2027 | Quarterly | [6 empty] | 176
2027-04-07 | Wed | 6.3.6-11 | MSR – 6.3.6 Global Command & Control System (GCCS) System Administration Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.3.7-17 | Standard Operating Procedures (SOP) – 6.3.7 SCCM/MECH Administration Support – Qtr from 01 Apr 2027 | Quarterly | [6 empty] | 176
2027-04-07 | Wed | 6.3.7-18 | MSR – 6.3.7 SCCM/MECH Administration Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.4.1-09 | MSR – 6.4.1 Senior Web Application Development Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.4.2-07 | MSR – 6.4.2 Web Application Development Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.4.3-06 | MSR – 6.4.3 Senior Web Portal Development Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.4.4-05 | MSR – 6.4.4 Web Portal Development Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.5.1-05 | MSR – 6.5.1 Assessment and Authorization Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.5.2-08 | MSR – 6.5.2 Cybersecurity Compliance Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.5.3-05 | MSR – 6.5.3 Cybersecurity Governance Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.5.4-09 | MSR – 6.5.4 Network Defense Administrator Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.5.5-10 | MSR – 6.5.5 Endpoint Security Solutions (ESS) Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.5.6-04 | MSR – 6.5.6 Electronic Key Management Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.5.7-10 | Standard Operating Procedures (SOP) – 6.5.7 Security Information Event Manager (SIEM) Administrator Support – Qtr from 01 Apr 2027 | Quarterly | [6 empty] | 176
2027-04-07 | Wed | 6.5.7-11 | MSR – 6.5.7 Security Information Event Manager (SIEM) Administrator Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.5.8-10 | Standard Operating Procedures (SOP) – 6.5.8 Compliance Administrator Support – Qtr from 01 Apr 2027 | Quarterly | [6 empty] | 176
2027-04-07 | Wed | 6.5.8-11 | MSR – 6.5.8 Compliance Administrator Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.6.1-04 | MSR – 6.6.1 Assistant Contract Technical Representative (ACTR) Support – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | 6.6.2-03 | MSR – 6.6.2 Communications Focal Point (CFP) Support – Mar 2027 | Monthly | [6 empty] | 176