## Tracker
LEIA Task Order – Deliverable Tracker
TO 47QFCA24F0049 ¦ Contract 47QFCA22D0032 ¦ Smartronix, LLC ¦ GSA AAS-Defense ¦ for SOCPAC ¦ Awarded 25 Sep 2024, Mod P00008 (29 May 2025) ¦ Base + 7 options to 24 Sep 2031
Government POCs |  | AAS CO: Steve Madsen ¦ AAS COR: Alexandria Williams ¦ ACORs: Donald Shevlin, Crystal Miller ¦ TO TPOC: Keith Stilwell (per Project Plan P018) ¦ Acceptance by AAS COR and designated TPOC (E.1)
At a glance |  | Overdue | Due within 7 days | Awaiting AAS COR / TPOC | Fully accepted | Returned: resubmit | PWS paragraphs with no deliverable
|  | 8 | 0 | 0 | 0 | 0 | 0
Lists (dropdown sources). Names you type into an Accepted By cell do not have to be on a list.
Month | Sub Task Number | Paragraph / Section | Frequency | Category | Primary POC | Secondary POC | Format of Deliverable | Deliverable 1 | Deliverable 2 | Deliverable 3 | Deliverable 4 | Deliverable 5 | Status Flow 1 | Status Flow 2 | Status Flow 3 | AAS COR Accepted By | AAS COR Date Accepted | TPOC Accepted By | TPOC Date Accepted | Category | Status Flow 1 | Status Flow 2 | Status Flow 3 | Frequency | Month | AAS COR Acceptors | TPOC Acceptors
Oct | C.5.1 | Task 1 – Program Management | Mixed (see due row) | Program Mgmt | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D01 Monthly Status of GFP and CAP | D02 Program Management Deliverables |  |  |  | Not Received | Not Reviewed | [5 empty] | Cybersecurity | Received | Reviewed | Accepted | Weekly | Jan | Alexandria Williams (AAS COR) | Keith Stilwell (TO TPOC)
[7 empty] | Due / Frequency (per document) | Due: Monthly Freq: Monthly (C.5.1) Flag: F.3 gives no day. The 1st calendar day (per Project Plan P018 F01) is assumed; due the next workday if it falls on a weekend or holiday. | Due: IAW Project Plan (PP) Freq: As needed | [10 empty] | Intelligence | Not Received | Not Reviewed | Returned | Monthly | Feb | Foster Folger (AAS PM / COR per P018) | Dr. Marvina Harring (Requirement Owner)
Oct | C.5.1.1 | Subtask 1.1 – Service Contract Reporting | Annual | Program Mgmt | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | C1.1 SAM.gov Service Contract Reporting (labor hours) |  |  |  |  | Not Received | Not Reviewed | [5 empty] | Logistics |  | Demonstrated | Returned, but Fixed | Quarterly | Mar | Donald Shevlin (AAS ACOR)
[7 empty] | Due / Frequency (per document) | Due: NLT 31 Oct each year Freq: Annual Date: Sat 31 Oct 2026 (NLT) | [11 empty] | Operations |  | Not Demonstrated |  | Annual | Apr | Crystal Miller (AAS ACOR)
Oct | C.5.1.2 | Subtask 1.2 – TO Kick-Off Meeting | One-Time | Program Mgmt | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | C1.2a TO Kick-Off Meeting Agenda | C1.2b TO Kick-Off Meeting Minutes Report |  |  |  | Not Received | Not Reviewed | [5 empty] | Program Mgmt |  |  |  | Daily (standing) | May
[7 empty] | Due / Frequency (per document) | Due: Before the kick-off (kick-off NLT 5 workdays after TO start) Freq: One-time Historical (TO start 25 Sep 2024) | Due: After the kick-off Freq: One-time Historical (TO start 25 Sep 2024) | [10 empty] | Solutions |  |  |  | One-Time | Jun
Oct | C.5.1.3 | Subtask 1.3 – Monthly Status Report (MSR) | Monthly | Program Mgmt | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | C1.3 Monthly Status Report (MSR) |  |  |  |  | Not Received | Not Reviewed | [5 empty] | Training |  |  |  | One-Time + Updates | Jul
[7 empty] | Due / Frequency (per document) | Due: Monthly (no day in the TO) Freq: Monthly Also: 60 days before each option period ends, identify recurring requirements that could transition to another contract type. Flag: The TO gives no due day. Project Plan P018 sets the 1st calendar day of each month; used here. | [15 empty] | As Needed | Aug
Oct | C.5.1.4 | Subtask 1.4 – Technical Status Meetings | Monthly | Program Mgmt | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | C1.4 Technical Status Meeting Minutes |  |  |  |  | Not Received | Not Reviewed | [9 empty] | Not required (suspended) | Sep
[7 empty] | Due / Frequency (per document) | Due: Monthly meeting; minutes to the AAS COR (no day stated) Freq: Monthly Flag: No due day stated; due with the MSR (assumed). | [15 empty] | Mixed (see due row) | Oct
Oct | C.5.1.5 | Subtask 1.5 – Program Management Plan (PMP) | Quarterly | Program Mgmt | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D03 Program Management Plan (PMP) |  |  |  |  | Not Received | Not Reviewed | [9 empty] | None named | Nov
[7 empty] | Due / Frequency (per document) | Due: At Kick-Off Meeting; quarterly updates unless there is a significant project change Freq: Quarterly updates Flag: C.5.1.5 says update annually at minimum; F.3 says quarterly. Quarterly assumed, due 5 business days after quarter end. | [16 empty] | Dec
Oct | C.5.1.6 | Subtask 1.6 – Project Plan (PP) | As Needed | Program Mgmt | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D04 Project Plan (PP) |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 5 workdays following the technical exchange meeting with the Government Freq: Each project
Oct | C.5.1.7 | Subtask 1.7 – Project Trip Reports | As Needed | Program Mgmt | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D05 Trip Report(s) |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: Within 10 workdays following completion of each trip Freq: Each trip Flag: F.3 cites C.5.1.6; the trip-report paragraph is C.5.1.7.
Oct | C.5.1.8 | Subtask 1.8 – Transition-In | One-Time | Program Mgmt | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D06 Transition-In Plan |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: At Kick-Off Meeting start Freq: One-time Historical (TO start 25 Sep 2024)
Oct | C.5.1.9 | Subtask 1.9 – Transition-Out | One-Time + Updates | Program Mgmt | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D07 Transition-Out Plan |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: Within six months of TO start; update annually, then quarterly in the final option period Freq: One-time + updates Annual update: Fri 25 Sep 2026. Implement NLT 6 months before TO expiry: Mon 24 Mar 2031. Flag: Annual updates run each 25 Sep (TO start anniversary); quarterly updates start in the final option period.
Oct | C.5.1.10 | Subtask 1.10 – TO Management Portal | One-Time | Program Mgmt | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D08 Task Order (TO) Management Portal Strategy |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: At Kick-Off Meeting start; portal operational within 90 days of approval Freq: One-time Historical (TO start 25 Sep 2024)
Oct | C.5.2 | Task 2 – C6ISR Operations (Subtasks 2.1–2.4) | As Needed | Operations | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D09 Operations Deliverables (C6ISR Operations, Subtasks 2.1–2.4) |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW Project Plan (PP) Freq: Each project
Oct | C.5.3 | Task 3 – C6ISR Solutions | As Needed | Solutions | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D10 C6ISR Deliverables (Solutions) |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW Project Plan (PP) Freq: Each project
Oct | C.5.4 | Task 4 – Intelligence Operations (Subtasks 4.1–4.2) | As Needed | Intelligence | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D11 Intelligence Analysis and Assessment Deliverables |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW Project Plan (PP) Freq: Each project Flag: F.3 cites C.5.4.1 only; Subtask 4.2 (PED) also lists no separate deliverable.
Oct | C.5.5 | Task 5 – C6ISR Training | As Needed | Training | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D12 Training Deliverables |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW Project Plan (PP) Freq: Each project
Oct | C.5.6 | Task 6 – Cybersecurity and IA | As Needed | Cybersecurity | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D13 Cyber and IA Deliverables |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW Project Plan (PP) Freq: Each project
Oct | C.5.7 | Task 7 – Logistics | As Needed | Logistics | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D14 Logistics Deliverables |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW Project Plan (PP) Freq: Each project
Oct | H.8.2 | Security Badges and CAC Cards | One-Time | Program Mgmt | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | n/a | D15 Security Badges and CAC Cards |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: At contract closeout Freq: One-time Date: Wed 24 Sep 2031 (end of TO)
Oct | H.9.5 | Personnel list (deployment) | As Needed | Program Mgmt | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D16 Personnel list |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW Project Plan (PP) Freq: Each project
Oct | H.14.1 | LQA Annual Reconciliation | As Needed | Program Mgmt | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D17 LQA Annual reconciliation |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW Project Plan (PP) Freq: Annual
Oct | H.17 / H.18 | AWR / Interim Flight Clearance | As Needed | Operations | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D18 AWR / Interim Flight Clearance |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW Project Plan (PP) Freq: Each project
Oct | H.31 | Mission Essential Contractor Services Plan | As Needed | Program Mgmt | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Contractor format | D19 Mission Essential Contractor Services Plan |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: At Project Kick-Off; update per DFARS 252.237-7023(c)(2) Freq: Each project + updates
Task rows record the two Government acceptances once per row (AAS COR, then TPOC; E.1). Recurring deliverables record them per period on the Monthly and Quarterly tabs. After acceptance, upload to ASSIST PAC within 5 workdays (E.5). Fully accepted = both dates filled in.

## Monthly
Monthly Deliverables – GFP/CAP status, MSR, Technical Status Meeting minutes
TO 47QFCA24F0049 ¦ Contract 47QFCA22D0032 ¦ Smartronix, LLC ¦ GSA AAS-Defense ¦ for SOCPAC ¦ Awarded 25 Sep 2024, Mod P00008 (29 May 2025) ¦ Base + 7 options to 24 Sep 2031
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Fully accepted | Overdue | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01
D01 | Monthly Status of GFP and CAP | C.5.1 | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Due date | 0 | 2 | 2026-09-01 | 2026-10-01 | 2026-11-02 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-03 | 2027-06-01 | 2027-07-01 | 2027-08-02
Status
AAS COR accepted by
AAS COR date accepted
TPOC accepted by
TPOC date accepted
Result
C1.3 | Monthly Status Report (MSR) | C.5.1.3 | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Due date | 0 | 2 | 2026-09-01 | 2026-10-01 | 2026-11-02 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-03 | 2027-06-01 | 2027-07-01 | 2027-08-02
Status
AAS COR accepted by
AAS COR date accepted
TPOC accepted by
TPOC date accepted
Result
C1.4 | Technical Status Meeting Minutes | C.5.1.4 | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Due date | 0 | 2 | 2026-09-01 | 2026-10-01 | 2026-11-02 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-03 | 2027-06-01 | 2027-07-01 | 2027-08-02
Status
AAS COR accepted by
AAS COR date accepted
TPOC accepted by
TPOC date accepted
Result
Set Status, then record who accepted it and when. The TO does not give a monthly due day; the 1st calendar day (Project Plan P018 F01), rolled to the next workday per F.3, is assumed.

## Quarterly
Quarterly Deliverables – Program Management Plan updates
TO 47QFCA24F0049 ¦ Contract 47QFCA22D0032 ¦ Smartronix, LLC ¦ GSA AAS-Defense ¦ for SOCPAC ¦ Awarded 25 Sep 2024, Mod P00008 (29 May 2025) ¦ Base + 7 options to 24 Sep 2031
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Fully accepted | Overdue | 2026-07-01 | 2026-10-01 | 2027-01-01 | 2027-04-01
D03 | Program Management Plan (PMP) | C.5.1.5; H.13 | Alexandria Williams (AAS COR) | Keith Stilwell (TPOC) | Due date | 0 | 1 | 2026-10-07 | 2027-01-07 | 2027-04-07 | 2027-07-07
Status
AAS COR accepted by
AAS COR date accepted
TPOC accepted by
TPOC date accepted
Result
Set Status, then record who accepted it and when. F.3 calls for quarterly PMP updates; C.5.1.5 says annual. 5 business days after quarter end is assumed.

## Daily Agenda
Daily Agenda – what is due, in date order
TO 47QFCA24F0049 ¦ Contract 47QFCA22D0032 ¦ Smartronix, LLC ¦ GSA AAS-Defense ¦ for SOCPAC ¦ Awarded 25 Sep 2024, Mod P00008 (29 May 2025) ¦ Base + 7 options to 24 Sep 2031
Settings (edit the yellow cells)
Due Date | Day | ID | Deliverable | Source | Status | AAS COR Accepted By | AAS COR Date Accepted | TPOC Accepted By | TPOC Date Accepted | Result | Days Until Due | Flag | Notes | Clock start (tracking window = Option Period 2 start) | 2026-08-01
2026-09-01 | Tue | C1.3 | Monthly Status Report (MSR) – Aug 2026 | Monthly | [6 empty] | -42 | OVERDUE |  | TO start (award period start) | 2024-09-25
2026-09-01 | Tue | C1.4 | Technical Status Meeting Minutes – Aug 2026 | Monthly | [6 empty] | -42 | OVERDUE |  | End of current option period (Option 2) | 2027-07-31
2026-09-01 | Tue | D01 | Monthly Status of GFP and CAP – Aug 2026 | Monthly | [6 empty] | -42 | OVERDUE |  | End of final option (Option 7) | 2031-09-24
2026-09-25 | Fri | D07 | D07 – Transition-Out Plan, annual update (TO start anniversary) | One-time | [6 empty] | -18 | OVERDUE | Updates annually; quarterly in the final option period. | Gov inspection window (workdays, E.2) | 15
2026-10-01 | Thu | C1.3 | Monthly Status Report (MSR) – Sep 2026 | Monthly | [6 empty] | -12 | OVERDUE |  | Resubmission window (workdays, E.4) | 10
2026-10-01 | Thu | C1.4 | Technical Status Meeting Minutes – Sep 2026 | Monthly | [6 empty] | -12 | OVERDUE |  | Today | 2026-10-13
2026-10-01 | Thu | D01 | Monthly Status of GFP and CAP – Sep 2026 | Monthly | [6 empty] | -12 | OVERDUE
2026-10-07 | Wed | D03 | Program Management Plan (PMP) – Qtr from 01 Jul 2026 | Quarterly | [6 empty] | -6 | OVERDUE |  | Per F.3, deliverables are due the next Government workday if the date falls on a weekend or holiday.
2026-10-31 | Sat | C1.1 | C1.1 – SAM.gov Service Contract Reporting (NLT 31 Oct) | One-time | [6 empty] | 18 |  | All labor hours for the government fiscal year. | Late delivery: file a Problem Notification Report (F.6).
2026-11-02 | Mon | C1.3 | Monthly Status Report (MSR) – Oct 2026 | Monthly | [6 empty] | 20 |  |  | Holidays are not excluded from business-day math here.
2026-11-02 | Mon | C1.4 | Technical Status Meeting Minutes – Oct 2026 | Monthly | [6 empty] | 20
2026-11-02 | Mon | D01 | Monthly Status of GFP and CAP – Oct 2026 | Monthly | [6 empty] | 20
2026-12-01 | Tue | C1.3 | Monthly Status Report (MSR) – Nov 2026 | Monthly | [6 empty] | 49
2026-12-01 | Tue | C1.4 | Technical Status Meeting Minutes – Nov 2026 | Monthly | [6 empty] | 49
2026-12-01 | Tue | D01 | Monthly Status of GFP and CAP – Nov 2026 | Monthly | [6 empty] | 49
2027-01-01 | Fri | C1.3 | Monthly Status Report (MSR) – Dec 2026 | Monthly | [6 empty] | 80
2027-01-01 | Fri | C1.4 | Technical Status Meeting Minutes – Dec 2026 | Monthly | [6 empty] | 80
2027-01-01 | Fri | D01 | Monthly Status of GFP and CAP – Dec 2026 | Monthly | [6 empty] | 80
2027-01-07 | Thu | D03 | Program Management Plan (PMP) – Qtr from 01 Oct 2026 | Quarterly | [6 empty] | 86
2027-02-01 | Mon | C1.3 | Monthly Status Report (MSR) – Jan 2027 | Monthly | [6 empty] | 111
2027-02-01 | Mon | C1.4 | Technical Status Meeting Minutes – Jan 2027 | Monthly | [6 empty] | 111
2027-02-01 | Mon | D01 | Monthly Status of GFP and CAP – Jan 2027 | Monthly | [6 empty] | 111
2027-03-01 | Mon | C1.3 | Monthly Status Report (MSR) – Feb 2027 | Monthly | [6 empty] | 139
2027-03-01 | Mon | C1.4 | Technical Status Meeting Minutes – Feb 2027 | Monthly | [6 empty] | 139
2027-03-01 | Mon | D01 | Monthly Status of GFP and CAP – Feb 2027 | Monthly | [6 empty] | 139
2027-04-01 | Thu | C1.3 | Monthly Status Report (MSR) – Mar 2027 | Monthly | [6 empty] | 170
2027-04-01 | Thu | C1.4 | Technical Status Meeting Minutes – Mar 2027 | Monthly | [6 empty] | 170
2027-04-01 | Thu | D01 | Monthly Status of GFP and CAP – Mar 2027 | Monthly | [6 empty] | 170
2027-04-07 | Wed | D03 | Program Management Plan (PMP) – Qtr from 01 Jan 2027 | Quarterly | [6 empty] | 176
2027-05-03 | Mon | C1.3 | Monthly Status Report (MSR) – Apr 2027 | Monthly | [6 empty] | 202
2027-05-03 | Mon | C1.4 | Technical Status Meeting Minutes – Apr 2027 | Monthly | [6 empty] | 202
2027-05-03 | Mon | D01 | Monthly Status of GFP and CAP – Apr 2027 | Monthly | [6 empty] | 202
2027-06-01 | Tue | C1.3 | Monthly Status Report (MSR) – May 2027 | Monthly | [6 empty] | 231
2027-06-01 | Tue | C1.3 | C1.3 – MSR content: identify recurring requirements eligible to transition (60 days before option period ends) | One-time | [6 empty] | 231 |  | C.5.1.3.
2027-06-01 | Tue | C1.4 | Technical Status Meeting Minutes – May 2027 | Monthly | [6 empty] | 231
2027-06-01 | Tue | D01 | Monthly Status of GFP and CAP – May 2027 | Monthly | [6 empty] | 231
2027-07-01 | Thu | C1.3 | Monthly Status Report (MSR) – Jun 2027 | Monthly | [6 empty] | 261
2027-07-01 | Thu | C1.4 | Technical Status Meeting Minutes – Jun 2027 | Monthly | [6 empty] | 261
2027-07-01 | Thu | D01 | Monthly Status of GFP and CAP – Jun 2027 | Monthly | [6 empty] | 261
2027-07-07 | Wed | D03 | Program Management Plan (PMP) – Qtr from 01 Apr 2027 | Quarterly | [6 empty] | 267
2027-08-02 | Mon | C1.3 | Monthly Status Report (MSR) – Jul 2027 | Monthly | [6 empty] | 293
2027-08-02 | Mon | C1.4 | Technical Status Meeting Minutes – Jul 2027 | Monthly | [6 empty] | 293
2027-08-02 | Mon | D01 | Monthly Status of GFP and CAP – Jul 2027 | Monthly | [6 empty] | 293
2031-03-24 | Mon | D07 | D07 – Transition-Out Plan: implement NLT 6 months before TO expiry | One-time | [6 empty] | 1623 |  | C.5.1.9.
2031-09-24 | Wed | D15 | D15 – Security Badges and CAC Cards (contract closeout) | One-time | [6 empty] | 1807 |  | H.8.2.