## Tracker
Morpheus (NSIN) – Deliverable Tracker
Statement of Work 47QFCA22K0053 ¦ National Security Innovation Network (NSIN) ¦ GSA FEDSIM ¦ OASIS Pool 1 ¦ Anticipated award June 2022 ¦ Base + 4 options (dates TBD at award)
Government POCs |  | FEDSIM CO / COR and NSIN Morpheus TPOC: names are not in the SOW. Replace the placeholder acceptors in the lists on the Tracker tab.
At a glance |  | Overdue | Due within 7 days | Awaiting FEDSIM COR / TPOC | Fully accepted | Returned: resubmit | PWS paragraphs with no deliverable
|  | 0 | 0 | 0 | 0 | 0 | 0
Lists (dropdown sources). Names you type into an Accepted By cell do not have to be on a list.
Month | Sub Task Number | Paragraph / Section | Frequency | Category | Primary POC | Secondary POC | Format of Deliverable | Deliverable 1 | Deliverable 2 | Deliverable 3 | Deliverable 4 | Deliverable 5 | Status Flow 1 | Status Flow 2 | Status Flow 3 | FEDSIM COR Accepted By | FEDSIM COR Date Accepted | TPOC Accepted By | TPOC Date Accepted | Category | Status Flow 1 | Status Flow 2 | Status Flow 3 | Frequency | Month | FEDSIM COR Acceptors | TPOC Acceptors
Nov | C.5.1.1 | Subtask 1 – Project Kick-Off Meeting | One-Time | Program Mgmt | FEDSIM COR | NSIN Morpheus TPOC | Contractor format | D01 Project Kick-Off Meeting | D02 Project Kick-Off Meeting Agenda | D03 Project Kick-Off Meeting Minutes Report |  |  | Not Received | Not Reviewed | [5 empty] | Design | Received | Reviewed | Accepted | Weekly | Jan | FEDSIM COR (enter name) | NSIN Morpheus TPOC (enter name)
[7 empty] | Due / Frequency (per document) | Due: At the location approved by the Government Freq: One-time | Due: At least 3 days before the Kick-Off Meeting Freq: One-time | Due: After the Kick-Off Meeting (no day stated) Freq: One-time | [9 empty] | Development | Not Received | Not Reviewed | Returned | Monthly | Feb
Nov | C.5.1.2 | Subtask 2 – Monthly Status Report | Monthly | Program Mgmt | FEDSIM COR | NSIN Morpheus TPOC | Contractor format | D04 Monthly Status Report (MSR) – Attachment E |  |  |  |  | Not Received | Not Reviewed | [5 empty] | Engineering |  | Demonstrated | Returned, but Fixed | Quarterly | Mar
[7 empty] | Due / Frequency (per document) | Due: Monthly (due day not in this file) Freq: Monthly Flag: Section F (delivery schedule) is not in this file. 5 business days after month end is assumed. | [11 empty] | Operations |  | Not Demonstrated |  | Annual | Apr
Nov | C.5.1.3 | Subtask 3 – Technical Status Meetings | Monthly | Program Mgmt | FEDSIM COR | NSIN Morpheus TPOC | Contractor format | D05 Technical Status Meeting (monthly) | D06 Technical Status Meeting Minutes |  |  |  | Not Received | Not Reviewed | [5 empty] | Program Mgmt |  |  |  | Daily (standing) | May
[7 empty] | Due / Frequency (per document) | Due: Monthly Freq: Monthly Flag: No due day stated; tracked with the MSR (assumed). | Due: After each monthly meeting (no day stated) Freq: Monthly Flag: No due day stated; tracked with the MSR (assumed). | [14 empty] | One-Time | Jun
Nov | C.5.1.4 | Subtask 4 – Project Management Plan | One-Time + Updates | Program Mgmt | FEDSIM COR | NSIN Morpheus TPOC | Contractor format | D07 Project Management Plan (PMP) |  |  |  |  | Not Received | Not Reviewed | [9 empty] | One-Time + Updates | Jul
[7 empty] | Due / Frequency (per document) | Due: Provided at kick-off; update annually at minimum and as project changes occur Freq: One-time + updates | [15 empty] | As Needed | Aug
Nov | C.5.1.5 | Subtask 5 – Trip Reports | As Needed | Program Mgmt | FEDSIM COR | NSIN Morpheus TPOC | Contractor format | D08 Trip Reports |  |  |  |  | Not Received | Not Reviewed | [9 empty] | Not required (suspended) | Sep
[7 empty] | Due / Frequency (per document) | Due: Need identified when the travel request is submitted Freq: Each trip | [15 empty] | Mixed (see due row) | Oct
Nov | C.5.1.6 | Subtask 6 – Quality Management | One-Time + Updates | Program Mgmt | FEDSIM COR | NSIN Morpheus TPOC | Contractor format | D09 Quality Management Plan (QMP) |  |  |  |  | Not Received | Not Reviewed | [9 empty] | None named | Nov
[7 empty] | Due / Frequency (per document) | Due: Provided with the PMP; update as processes change Freq: One-time + updates | [16 empty] | Dec
Nov | C.5.1.7 | Subtask 7 – Transition-In | One-Time | Program Mgmt | FEDSIM COR | NSIN Morpheus TPOC | Contractor format | D10 Transition-In Plan |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: Implement NLT 15 calendar days after award; FOC 45 days after project start Freq: One-time
Nov | C.5.1.8 | Subtask 8 – Transition-Out | One-Time + Updates | Program Mgmt | FEDSIM COR | NSIN Morpheus TPOC | Contractor format | D11 Transition-Out Plan |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: Within six months of project start; implement NLT six months before TO expiry Freq: One-time + updates
Nov | C.5.1.9 | Subtask 9 – TO Management Portal | One-Time | Program Mgmt | FEDSIM COR | NSIN Morpheus TPOC | Contractor format | D12 Task Order Management Portal solution |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: Proposed at Kick-Off; fully operational 90 days after base year start Freq: One-time
Nov | C.5.1.10 | Subtask 10 – Technical Direction Plans | As Needed | Program Mgmt | FEDSIM COR | NSIN Morpheus TPOC | Contractor format | D13 Technical Direction Plan(s) (TDP) |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: Per FEDSIM CO-approved TDL; schedule updated monthly Freq: Each TDL
Nov | C.5.1.11 | Subtask 11 – Service Contract Reporting | Annual | Program Mgmt | FEDSIM COR | NSIN Morpheus TPOC | Contractor format | C11 SAM.gov Service Contract Reporting (labor hours) |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: NLT 31 Oct each year Freq: Annual
Nov | C.5.2 | Task 2 – Project Design | As Needed | Design | FEDSIM COR | NSIN Morpheus TPOC | Contractor format | D14 Project Design Deliverables |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW TDL / project plan Freq: Each TDL
Nov | C.5.3 | Task 3 – Project Development | As Needed | Development | FEDSIM COR | NSIN Morpheus TPOC | Contractor format | D15 Project Development Deliverables |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW TDL / project plan Freq: Each TDL
Nov | C.5.4 | Task 4 – Project Engineering and Integration | As Needed | Engineering | FEDSIM COR | NSIN Morpheus TPOC | Contractor format | D16 Project Engineering and Integration Deliverables |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW TDL / project plan Freq: Each TDL
Nov | C.5.5 | Task 5 – Project Operations and Sustainment | As Needed | Operations | FEDSIM COR | NSIN Morpheus TPOC | Contractor format | D17 Project Operations and Sustainment Deliverables |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: IAW TDL / project plan Freq: Each TDL
Section E (inspection and acceptance) and Section F (delivery schedule) are not in this file, so deliverable numbering follows the "Section F, Deliverable nn" references in Section C. Tasks 2–5 deliverables follow each TDL. Fully accepted = both dates filled in.

## Monthly
Monthly Deliverables – MSR and Technical Status Meeting
Statement of Work 47QFCA22K0053 ¦ National Security Innovation Network (NSIN) ¦ GSA FEDSIM ¦ OASIS Pool 1 ¦ Anticipated award June 2022 ¦ Base + 4 options (dates TBD at award)
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Fully accepted | Overdue | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01
D04 | Monthly Status Report (MSR) – Attachment E | C.5.1.2 | FEDSIM COR | NSIN Morpheus TPOC | Due date | 0 | 0 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07 | 2027-05-07 | 2027-06-07 | 2027-07-07 | 2027-08-06 | 2027-09-07 | 2027-10-07 | 2027-11-05
Status
FEDSIM COR accepted by
FEDSIM COR date accepted
TPOC accepted by
TPOC date accepted
Result
D05 | Technical Status Meeting (monthly) | C.5.1.3 | FEDSIM COR | NSIN Morpheus TPOC | Due date | 0 | 0 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07 | 2027-05-07 | 2027-06-07 | 2027-07-07 | 2027-08-06 | 2027-09-07 | 2027-10-07 | 2027-11-05
Status
FEDSIM COR accepted by
FEDSIM COR date accepted
TPOC accepted by
TPOC date accepted
Result
D06 | Technical Status Meeting Minutes | C.5.1.3 | FEDSIM COR | NSIN Morpheus TPOC | Due date | 0 | 0 | 2026-12-07 | 2027-01-07 | 2027-02-05 | 2027-03-05 | 2027-04-07 | 2027-05-07 | 2027-06-07 | 2027-07-07 | 2027-08-06 | 2027-09-07 | 2027-10-07 | 2027-11-05
Status
FEDSIM COR accepted by
FEDSIM COR date accepted
TPOC accepted by
TPOC date accepted
Result
Set Status, then record who accepted it and when. Section F (the delivery schedule) is not in this file, so due days are assumed: 5 business days after month end.

## Daily Agenda
Daily Agenda – what is due, in date order
Statement of Work 47QFCA22K0053 ¦ National Security Innovation Network (NSIN) ¦ GSA FEDSIM ¦ OASIS Pool 1 ¦ Anticipated award June 2022 ¦ Base + 4 options (dates TBD at award)
Settings (edit the yellow cells)
Due Date | Day | ID | Deliverable | Source | Status | FEDSIM COR Accepted By | FEDSIM COR Date Accepted | TPOC Accepted By | TPOC Date Accepted | Result | Days Until Due | Flag | Notes | Clock start (PLACEHOLDER – PoP is TBD at award) | 2026-11-01
2026-11-12 | Thu | D02 | D02 – Kick-Off Meeting Agenda (3 days before kick-off) | One-time | [6 empty] | 30 |  | At least three days prior. | Kick-off date (ASSUMED = start + 14 days) | 2026-11-15
2026-11-15 | Sun | D01 | D01 – Project Kick-Off Meeting (date assumed) | One-time | [6 empty] | 33 |  | Kick-off date is not set in the SOW; ClockStart + 14 days assumed. | End of base year | 2027-10-31
2026-11-15 | Sun | D07 | D07 – PMP and D09 QMP at kick-off | One-time | [6 empty] | 33 |  | Agenda topics include QMP and PMP. | End of option year 4 | 2031-10-31
2026-11-15 | Sun | D12 | D12 – TO management portal solution proposed at kick-off | One-time | [6 empty] | 33 |  |  | Gov inspection window (business days, ASSUMED) | 5
2026-11-16 | Mon | D10 | D10 – Transition-In Plan: implement NLT 15 days after award | One-time | [6 empty] | 34 |  | C.5.1.7. | Resubmission window (business days, ASSUMED) | 10
2026-12-07 | Mon | D04 | Monthly Status Report (MSR) – Attachment E – Nov 2026 | Monthly | [6 empty] | 55 |  |  | Today | 2026-10-13
2026-12-07 | Mon | D05 | Technical Status Meeting (monthly) – Nov 2026 | Monthly | [6 empty] | 55
2026-12-07 | Mon | D06 | Technical Status Meeting Minutes – Nov 2026 | Monthly | [6 empty] | 55 |  |  | The SOW says the PoP is "TBD at award" and the award was anticipated for June 2022. Enter the real start in cell Q4.
2026-12-16 | Wed | D10 | D10 – Full Operational Capability (45 days after project start) | One-time | [6 empty] | 64 |  | C.5.1.7. | Inspection and acceptance terms (Section E) are not in this file.
2027-01-07 | Thu | D04 | Monthly Status Report (MSR) – Attachment E – Dec 2026 | Monthly | [6 empty] | 86 |  |  | Holidays are not excluded from business-day math.
2027-01-07 | Thu | D05 | Technical Status Meeting (monthly) – Dec 2026 | Monthly | [6 empty] | 86
2027-01-07 | Thu | D06 | Technical Status Meeting Minutes – Dec 2026 | Monthly | [6 empty] | 86
2027-01-30 | Sat | D12 | D12 – Portal fully operational (90 days after base year start) | One-time | [6 empty] | 109 |  | C.5.1.9.
2027-02-05 | Fri | D04 | Monthly Status Report (MSR) – Attachment E – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | D05 | Technical Status Meeting (monthly) – Jan 2027 | Monthly | [6 empty] | 115
2027-02-05 | Fri | D06 | Technical Status Meeting Minutes – Jan 2027 | Monthly | [6 empty] | 115
2027-03-05 | Fri | D04 | Monthly Status Report (MSR) – Attachment E – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | D05 | Technical Status Meeting (monthly) – Feb 2027 | Monthly | [6 empty] | 143
2027-03-05 | Fri | D06 | Technical Status Meeting Minutes – Feb 2027 | Monthly | [6 empty] | 143
2027-04-07 | Wed | D04 | Monthly Status Report (MSR) – Attachment E – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | D05 | Technical Status Meeting (monthly) – Mar 2027 | Monthly | [6 empty] | 176
2027-04-07 | Wed | D06 | Technical Status Meeting Minutes – Mar 2027 | Monthly | [6 empty] | 176
2027-05-01 | Sat | D11 | D11 – Transition-Out Plan (within six months of project start) | One-time | [6 empty] | 200 |  | C.5.1.8.
2027-05-07 | Fri | D04 | Monthly Status Report (MSR) – Attachment E – Apr 2027 | Monthly | [6 empty] | 206
2027-05-07 | Fri | D05 | Technical Status Meeting (monthly) – Apr 2027 | Monthly | [6 empty] | 206
2027-05-07 | Fri | D06 | Technical Status Meeting Minutes – Apr 2027 | Monthly | [6 empty] | 206
2027-06-07 | Mon | D04 | Monthly Status Report (MSR) – Attachment E – May 2027 | Monthly | [6 empty] | 237
2027-06-07 | Mon | D05 | Technical Status Meeting (monthly) – May 2027 | Monthly | [6 empty] | 237
2027-06-07 | Mon | D06 | Technical Status Meeting Minutes – May 2027 | Monthly | [6 empty] | 237
2027-07-07 | Wed | D04 | Monthly Status Report (MSR) – Attachment E – Jun 2027 | Monthly | [6 empty] | 267
2027-07-07 | Wed | D05 | Technical Status Meeting (monthly) – Jun 2027 | Monthly | [6 empty] | 267
2027-07-07 | Wed | D06 | Technical Status Meeting Minutes – Jun 2027 | Monthly | [6 empty] | 267
2027-08-06 | Fri | D04 | Monthly Status Report (MSR) – Attachment E – Jul 2027 | Monthly | [6 empty] | 297
2027-08-06 | Fri | D05 | Technical Status Meeting (monthly) – Jul 2027 | Monthly | [6 empty] | 297
2027-08-06 | Fri | D06 | Technical Status Meeting Minutes – Jul 2027 | Monthly | [6 empty] | 297
2027-09-07 | Tue | D04 | Monthly Status Report (MSR) – Attachment E – Aug 2027 | Monthly | [6 empty] | 329
2027-09-07 | Tue | D05 | Technical Status Meeting (monthly) – Aug 2027 | Monthly | [6 empty] | 329
2027-09-07 | Tue | D06 | Technical Status Meeting Minutes – Aug 2027 | Monthly | [6 empty] | 329
2027-10-07 | Thu | D04 | Monthly Status Report (MSR) – Attachment E – Sep 2027 | Monthly | [6 empty] | 359
2027-10-07 | Thu | D05 | Technical Status Meeting (monthly) – Sep 2027 | Monthly | [6 empty] | 359
2027-10-07 | Thu | D06 | Technical Status Meeting Minutes – Sep 2027 | Monthly | [6 empty] | 359
2027-10-31 | Sun | C11 | C11 – SAM.gov Service Contract Reporting (NLT 31 Oct) | One-time | [6 empty] | 383 |  | C.5.1.11.
2027-11-01 | Mon | D07 | D07 – PMP annual update | One-time | [6 empty] | 384 |  | Updated annually at minimum.
2027-11-05 | Fri | D04 | Monthly Status Report (MSR) – Attachment E – Oct 2027 | Monthly | [6 empty] | 388
2027-11-05 | Fri | D05 | Technical Status Meeting (monthly) – Oct 2027 | Monthly | [6 empty] | 388
2027-11-05 | Fri | D06 | Technical Status Meeting Minutes – Oct 2027 | Monthly | [6 empty] | 388
2031-04-30 | Wed | D11 | D11 – Implement Transition-Out Plan NLT six months before TO expiry | One-time | [6 empty] | 1660 |  | Uses end of option year 4.