## Tracker
Project Plan P018 (J6 Comm Support) – Deliverable Tracker
Project Plan # P018 (Deliverable 04) ¦ TO 47QFCA24F0049 LEIA ¦ Contract 47QFCA22D0032 ¦ INDOPACOM J6 ¦ 7600A 47QFCA24S0224 ¦ Signed 31 Mar 2025 ¦ PoP stated as 20MAR24 [sic] – 31JUL25
Government POCs |  | Req. Owner: Dr. Marvina Harring ¦ AAS COR/PM: Foster Folger ¦ AAS ACOR: Donald Shevlin ¦ TO TPOC: Keith Stilwell ¦ SMX Project Lead: Darren Conrad
At a glance |  | Overdue | Due within 7 days | Awaiting AAS COR / TPOC / Req Owner | Fully accepted | Returned: resubmit | PWS paragraphs with no deliverable
|  | 40 | 0 | 0 | 0 | 0 | 0
Lists (dropdown sources). Names you type into an Accepted By cell do not have to be on a list.
Month | Sub Task Number | Paragraph / Section | Frequency | Category | Primary POC | Secondary POC | Format of Deliverable | Deliverable 1 | Deliverable 2 | Deliverable 3 | Deliverable 4 | Deliverable 5 | Status Flow 1 | Status Flow 2 | Status Flow 3 | AAS COR Accepted By | AAS COR Date Accepted | TPOC / Req Owner Accepted By | TPOC / Req Owner Date Accepted | Category | Status Flow 1 | Status Flow 2 | Status Flow 3 | Frequency | Month | AAS COR Acceptors | TPOC / Req Owner Acceptors
Apr | C.5.1.3 | Monthly Status Report | Monthly | Program Mgmt | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Contractor format | F01 Monthly Status Report |  |  |  |  | Not Received | Not Reviewed | [5 empty] | Cybersecurity | Received | Reviewed | Accepted | Weekly | Jan | Foster Folger (AAS COR / PM) | Keith Stilwell (TO TPOC)
[7 empty] | Due / Frequency (per document) | Due: 1st calendar day of each month Freq: 5 copies (monthly) Flag: LEIA TO Deliverable 01 is the monthly GFP/CAP status; P018 labels F01 the Monthly Status Report. | [11 empty] | Intelligence | Not Received | Not Reviewed | Returned | Monthly | Feb | Donald Shevlin (AAS ACOR) | Dr. Marvina Harring (Requirement Owner)
Apr | C.5.1.5 | Project Plan (this document) | One-Time | Program Mgmt | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Contractor format | F04 Project Plan (this document) |  |  |  |  | Not Received | Not Reviewed | [5 empty] | Logistics |  | Demonstrated | Returned, but Fixed | Quarterly | Mar
[7 empty] | Due / Frequency (per document) | Due: At Project Kick-Off Meeting Freq: 1 Date: 20 Mar 2025 (signed 31 Mar 2025) Flag: P018 cites C.5.1.5 (the PMP paragraph); the Project Plan paragraph in the TO is C.5.1.6. | [11 empty] | Operations |  | Not Demonstrated |  | Annual | Apr
Apr | C.5.2 | Task 2 – C6ISR Operations | Monthly | Operations | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Contractor format | F09 C6ISR Operations Deliverables |  |  |  |  | Not Received | Not Reviewed | [5 empty] | Program Mgmt |  |  |  | Daily (standing) | May
[7 empty] | Due / Frequency (per document) | Due: ICW MSR (in concert with the Monthly Status Report) Freq: Number 02 Flag: "Number" column values are not explained in the Project Plan. | [11 empty] | Solutions |  |  |  | One-Time | Jun
Apr | C.5.3 | Task 3 – C6ISR Solutions | Monthly | Solutions | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Contractor format | F10 C6ISR Solutions Deliverables |  |  |  |  | Not Received | Not Reviewed | [5 empty] | Training |  |  |  | One-Time + Updates | Jul
[7 empty] | Due / Frequency (per document) | Due: ICW MSR (in concert with the Monthly Status Report) Freq: Number 03 | [15 empty] | As Needed | Aug
Apr | C.5.4 | Task 4 – Intelligence Operations | Monthly | Intelligence | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Contractor format | F11 Intelligence Operations Deliverables |  |  |  |  | Not Received | Not Reviewed | [9 empty] | Not required (suspended) | Sep
[7 empty] | Due / Frequency (per document) | Due: ICW MSR (in concert with the Monthly Status Report) Freq: Number 04 | [15 empty] | Mixed (see due row) | Oct
Apr | C.5.5 | Task 5 – Training | Monthly | Training | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Contractor format | F12 Training Deliverables |  |  |  |  | Not Received | Not Reviewed | [9 empty] | None named | Nov
[7 empty] | Due / Frequency (per document) | Due: ICW MSR (in concert with the Monthly Status Report) Freq: Number 05 | [16 empty] | Dec
Apr | C.5.6 | Task 6 – Cybersecurity and IA | Monthly | Cybersecurity | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Contractor format | F13 Cybersecurity and Information Assurance Deliverables |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: ICW MSR (in concert with the Monthly Status Report) Freq: Number 06
Apr | C.5.7 | Task 7 – Logistics | Monthly | Logistics | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Contractor format | F14 Logistics Deliverables |  |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: ICW MSR (in concert with the Monthly Status Report) Freq: Number 07
Apr | Section 3 | Project Milestones (1 of 2) | One-Time | Program Mgmt | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | n/a | M01 Project Kick-Off Meeting Briefing | M02 Project Plan | M03 Project Initiation | M04 Program Management Services initiation | M05 C6ISR Operations Services initiation | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: O/A 20 Mar 2025 Freq: Milestone | Due: O/A 20 Mar 2025 Freq: Milestone | Due: O/A 01 Apr 2025 Freq: Milestone | Due: O/A 01 Apr 2025 Freq: Milestone | Due: O/A 01 Apr 2025 Freq: Milestone
Apr | Section 3 | Project Milestones (2 of 2) | One-Time | Program Mgmt | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | n/a | M06 C6ISR Solutions Services initiation | M07 Training and Equipment Services initiation | M08 Cybersecurity and IA Services initiation | M09 Logistics Services initiation |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: O/A 01 Apr 2025 Freq: Milestone | Due: O/A 01 Apr 2025 Freq: Milestone | Due: O/A 01 Apr 2025 Freq: Milestone | Due: O/A 01 Apr 2025 Freq: Milestone
Apr | Section 7 | Project Management Plan and self-assessment | As Needed | Program Mgmt | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Contractor format | P71 PMP update (Project Plan 7.1) | P72 Project Lead self-assessment (7.2) |  |  |  | Not Received | Not Reviewed
[7 empty] | Due / Frequency (per document) | Due: Not stated Freq: As needed | Due: Every six months Freq: Every 6 months Flag: Every six months from 20 Mar 2025 is 20 Sep 2025, after the 31 Jul 2025 end of Activity 1.
Activity 1 ended 31 Jul 2025 unless extended by modification. Every date is in the past as of today, so items show OVERDUE until you back-fill who accepted them and when (or mark them N/A). Fully accepted = both dates filled in.

## Monthly
Monthly Deliverables – MSR and companion deliverables (due the 1st calendar day of each month)
Project Plan # P018 (Deliverable 04) ¦ TO 47QFCA24F0049 LEIA ¦ Contract 47QFCA22D0032 ¦ INDOPACOM J6 ¦ 7600A 47QFCA24S0224 ¦ Signed 31 Mar 2025 ¦ PoP stated as 20MAR24 [sic] – 31JUL25
ID | Deliverable | PWS ¶ | Primary POC | Secondary POC | Record | Fully accepted | Overdue | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01
F01 | Monthly Status Report | C.5.1.3 | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Due date | 0 | 5 | 2025-04-01 | 2025-05-01 | 2025-06-02 | 2025-07-01 | 2025-08-01
Status
AAS COR accepted by
AAS COR date accepted
TPOC / Req Owner accepted by
TPOC / Req Owner date accepted
Result
F09 | C6ISR Operations Deliverables | C.5.2 | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Due date | 0 | 5 | 2025-04-01 | 2025-05-01 | 2025-06-02 | 2025-07-01 | 2025-08-01
Status
AAS COR accepted by
AAS COR date accepted
TPOC / Req Owner accepted by
TPOC / Req Owner date accepted
Result
F10 | C6ISR Solutions Deliverables | C.5.3 | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Due date | 0 | 5 | 2025-04-01 | 2025-05-01 | 2025-06-02 | 2025-07-01 | 2025-08-01
Status
AAS COR accepted by
AAS COR date accepted
TPOC / Req Owner accepted by
TPOC / Req Owner date accepted
Result
F11 | Intelligence Operations Deliverables | C.5.4 | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Due date | 0 | 5 | 2025-04-01 | 2025-05-01 | 2025-06-02 | 2025-07-01 | 2025-08-01
Status
AAS COR accepted by
AAS COR date accepted
TPOC / Req Owner accepted by
TPOC / Req Owner date accepted
Result
F12 | Training Deliverables | C.5.5 | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Due date | 0 | 5 | 2025-04-01 | 2025-05-01 | 2025-06-02 | 2025-07-01 | 2025-08-01
Status
AAS COR accepted by
AAS COR date accepted
TPOC / Req Owner accepted by
TPOC / Req Owner date accepted
Result
F13 | Cybersecurity and Information Assurance Deliverables | C.5.6 | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Due date | 0 | 5 | 2025-04-01 | 2025-05-01 | 2025-06-02 | 2025-07-01 | 2025-08-01
Status
AAS COR accepted by
AAS COR date accepted
TPOC / Req Owner accepted by
TPOC / Req Owner date accepted
Result
F14 | Logistics Deliverables | C.5.7 | Dr. Marvina Harring (Req. Owner) | Keith Stilwell (TPOC) | Due date | 0 | 5 | 2025-04-01 | 2025-05-01 | 2025-06-02 | 2025-07-01 | 2025-08-01
Status
AAS COR accepted by
AAS COR date accepted
TPOC / Req Owner accepted by
TPOC / Req Owner date accepted
Result
Set Status, then record who accepted it and when. F01 is due the 1st calendar day of each month; F09–F14 are due "in concert with the MSR". Five reports cover April through August 2025.

## Daily Agenda
Daily Agenda – what is due, in date order
Project Plan # P018 (Deliverable 04) ¦ TO 47QFCA24F0049 LEIA ¦ Contract 47QFCA22D0032 ¦ INDOPACOM J6 ¦ 7600A 47QFCA24S0224 ¦ Signed 31 Mar 2025 ¦ PoP stated as 20MAR24 [sic] – 31JUL25
Settings (edit the yellow cells)
Due Date | Day | ID | Deliverable | Source | Status | AAS COR Accepted By | AAS COR Date Accepted | TPOC / Req Owner Accepted By | TPOC / Req Owner Date Accepted | Result | Days Until Due | Flag | Notes | Clock start (Project Kick-Off, per Section 3) | 2025-03-20
2025-03-20 | Thu | F04 | F04 – Project Plan (this document), at kick-off | One-time | [6 empty] | -572 | OVERDUE |  | End of Activity 1 (31 Jul 2025) | 2025-07-31
2025-03-20 | Thu | M01 | M01 – Project Kick-Off Meeting Briefing (O/A) | One-time | [6 empty] | -572 | OVERDUE |  | End of final period | 2025-07-31
2025-03-20 | Thu | M02 | M02 – Project Plan (O/A); F04 at kick-off | One-time | [6 empty] | -572 | OVERDUE | Signed 31 Mar 2025. | Gov inspection window (workdays, per parent TO E.2) | 15
2025-04-01 | Tue | F01 | Monthly Status Report – Mar 2025 | Monthly | [6 empty] | -560 | OVERDUE |  | Resubmission window (workdays, per parent TO E.4) | 10
2025-04-01 | Tue | F09 | C6ISR Operations Deliverables – Mar 2025 | Monthly | [6 empty] | -560 | OVERDUE |  | Today | 2026-10-13
2025-04-01 | Tue | F10 | C6ISR Solutions Deliverables – Mar 2025 | Monthly | [6 empty] | -560 | OVERDUE
2025-04-01 | Tue | F11 | Intelligence Operations Deliverables – Mar 2025 | Monthly | [6 empty] | -560 | OVERDUE |  | The Project Plan gives the PoP as "20MAR24 – 31JUL25". The start year is likely 20 Mar 2025 (kick-off date); 2025 is used.
2025-04-01 | Tue | F12 | Training Deliverables – Mar 2025 | Monthly | [6 empty] | -560 | OVERDUE |  | Dates are estimates until funds are accepted by the AAS-D COR and a modification is awarded.
2025-04-01 | Tue | F13 | Cybersecurity and Information Assurance Deliverables – Mar 2025 | Monthly | [6 empty] | -560 | OVERDUE |  | Holidays are not excluded from business-day math.
2025-04-01 | Tue | F14 | Logistics Deliverables – Mar 2025 | Monthly | [6 empty] | -560 | OVERDUE
2025-04-01 | Tue | M03 | M03 – Project Initiation and all service initiations (O/A 1 Apr 2025) | One-time | [6 empty] | -560 | OVERDUE | M03–M09 share this date.
2025-05-01 | Thu | F01 | Monthly Status Report – Apr 2025 | Monthly | [6 empty] | -530 | OVERDUE
2025-05-01 | Thu | F09 | C6ISR Operations Deliverables – Apr 2025 | Monthly | [6 empty] | -530 | OVERDUE
2025-05-01 | Thu | F10 | C6ISR Solutions Deliverables – Apr 2025 | Monthly | [6 empty] | -530 | OVERDUE
2025-05-01 | Thu | F11 | Intelligence Operations Deliverables – Apr 2025 | Monthly | [6 empty] | -530 | OVERDUE
2025-05-01 | Thu | F12 | Training Deliverables – Apr 2025 | Monthly | [6 empty] | -530 | OVERDUE
2025-05-01 | Thu | F13 | Cybersecurity and Information Assurance Deliverables – Apr 2025 | Monthly | [6 empty] | -530 | OVERDUE
2025-05-01 | Thu | F14 | Logistics Deliverables – Apr 2025 | Monthly | [6 empty] | -530 | OVERDUE
2025-06-02 | Mon | F01 | Monthly Status Report – May 2025 | Monthly | [6 empty] | -498 | OVERDUE
2025-06-02 | Mon | F09 | C6ISR Operations Deliverables – May 2025 | Monthly | [6 empty] | -498 | OVERDUE
2025-06-02 | Mon | F10 | C6ISR Solutions Deliverables – May 2025 | Monthly | [6 empty] | -498 | OVERDUE
2025-06-02 | Mon | F11 | Intelligence Operations Deliverables – May 2025 | Monthly | [6 empty] | -498 | OVERDUE
2025-06-02 | Mon | F12 | Training Deliverables – May 2025 | Monthly | [6 empty] | -498 | OVERDUE
2025-06-02 | Mon | F13 | Cybersecurity and Information Assurance Deliverables – May 2025 | Monthly | [6 empty] | -498 | OVERDUE
2025-06-02 | Mon | F14 | Logistics Deliverables – May 2025 | Monthly | [6 empty] | -498 | OVERDUE
2025-07-01 | Tue | F01 | Monthly Status Report – Jun 2025 | Monthly | [6 empty] | -469 | OVERDUE
2025-07-01 | Tue | F09 | C6ISR Operations Deliverables – Jun 2025 | Monthly | [6 empty] | -469 | OVERDUE
2025-07-01 | Tue | F10 | C6ISR Solutions Deliverables – Jun 2025 | Monthly | [6 empty] | -469 | OVERDUE
2025-07-01 | Tue | F11 | Intelligence Operations Deliverables – Jun 2025 | Monthly | [6 empty] | -469 | OVERDUE
2025-07-01 | Tue | F12 | Training Deliverables – Jun 2025 | Monthly | [6 empty] | -469 | OVERDUE
2025-07-01 | Tue | F13 | Cybersecurity and Information Assurance Deliverables – Jun 2025 | Monthly | [6 empty] | -469 | OVERDUE
2025-07-01 | Tue | F14 | Logistics Deliverables – Jun 2025 | Monthly | [6 empty] | -469 | OVERDUE
2025-08-01 | Fri | F01 | Monthly Status Report – Jul 2025 | Monthly | [6 empty] | -438 | OVERDUE
2025-08-01 | Fri | F09 | C6ISR Operations Deliverables – Jul 2025 | Monthly | [6 empty] | -438 | OVERDUE
2025-08-01 | Fri | F10 | C6ISR Solutions Deliverables – Jul 2025 | Monthly | [6 empty] | -438 | OVERDUE
2025-08-01 | Fri | F11 | Intelligence Operations Deliverables – Jul 2025 | Monthly | [6 empty] | -438 | OVERDUE
2025-08-01 | Fri | F12 | Training Deliverables – Jul 2025 | Monthly | [6 empty] | -438 | OVERDUE
2025-08-01 | Fri | F13 | Cybersecurity and Information Assurance Deliverables – Jul 2025 | Monthly | [6 empty] | -438 | OVERDUE
2025-08-01 | Fri | F14 | Logistics Deliverables – Jul 2025 | Monthly | [6 empty] | -438 | OVERDUE
2025-09-20 | Sat | P72 | P72 – Project Lead self-assessment (6 months) | One-time | [6 empty] | -388 | OVERDUE | Falls after the end of Activity 1.